## Title Page
This spreadsheet supports INSTRUCTOR analysis of the case “New York City Department of Parks and Recreation” (UVA-QA-0815).
This spreadsheet was prepared by Assistant Professor Yael Grushka-Cockayne. Copyright © 2015 by the University of Virginia Darden School Foundation, Charlottesville, VA. All rights reserved. For customer service inquiries, send an e-mail tosales@dardenbusinesspublishing.com. No part of this publication may be reproduced, stored in a retrieval system, posted to the Internet, or transmitted in any form or by any means—electronic, mechanical, photocopying, recording, or otherwise—without the permission of the Darden School Foundation.
Aug. 11, 2015

## Table of Contents
Table of Contents
| Column | Data Description
A | Project number | Project identifier
B | Project title | A brief description of the project undertaken
C | Design schedule and completion date | Date when the project’s final plans should be completed and approved
D | Design actual completion date | Date when the project’s final plans are completed and approved
E | Title request | Date that a title, including contract number and name, is obtained from the New York City DPR’s map and file office; official beginning of the contract paperwork
F | Construction registered amount | Amount of approved funding for construction (may exclude design and construction management)
G | Total budget | Total amount spent on the project
H | Registration approved; pending order-to-work date | Date the funds are registered by the New York City comptroller; date when construction may begin
I | Scheduled completion date | Target project completion date
J | Final inspection | Actual completion date
K | Status | Indicates final inspection and/or beginning of guarantee period. Final inspection marks the end of construction. If approved, the guarantee period begins, typically lasting one year from the final inspection date. During this time, the contractor is responsible for the work completed.
L | Construction unit | Team responsible for the project

## Descriptive
Days Late |  | Cost Escalations
Mean | 78.2039 | Mean | 0.43515
Standard Error | 4.506 | Standard Error | 0.02673
Median | 44 | Median | 0.29673
Mode | 0 | Mode | 0
Standard Deviation | 190.6425 | Standard Deviation | 1.1309
Sample Variance | 36344.5783 | Sample Variance | 1.279
Kurtosis | 6.6213 | Kurtosis | 494.8909
Skewness | 0.25735 | Skewness | 19.5492
Range | 2150 | Range | 33.326
Minimum | -992 | Minimum | -0.75387
Maximum | 1158 | Maximum | 32.5722
Sum | 139985 | Sum | 778.9241
Count | 1790 | Count | 1790

## Days Late Hist
Bin | Frequency
-992 | 1
-940.8095 | 2
-889.619 | 2
-838.4286 | 2
-787.2381 | 2
-736.0476 | 2
-684.8571 | 3
-633.6667 | 1
-582.4762 | 0
-531.2857 | 1
-480.0952 | 0
-428.9048 | 1
-377.7143 | 1
-326.5238 | 1
-275.3333 | 4
-224.1429 | 14
-172.9524 | 21
-121.7619 | 46
-70.5714 | 90
-19.381 | 164
31.8095 | 489
83 | 226
134.1905 | 233
185.381 | 133
236.5714 | 87
287.7619 | 65
338.9524 | 49
390.1429 | 42
441.3333 | 31
492.5238 | 26
543.7143 | 12
594.9048 | 6
646.0952 | 7
697.2857 | 6
748.4762 | 7
799.6667 | 6
850.8571 | 2
902.0476 | 1
953.2381 | 1
1004.4286 | 0
1055.619 | 2
1106.8095 | 0
More | 1

## Cost Escalation Hist
Bin | Frequency
-1 | 0
-0.9 | 0
-0.8 | 0
-0.7 | 2
-0.6 | 1
-0.5 | 0
-0.4 | 0
-0.3 | 2
-0.2 | 2
-0.1 | 3
0 | 121
0.1 | 223
0.2 | 250
0.3 | 329
0.4 | 306
0.5 | 163
0.6 | 108
0.7 | 68
0.8 | 47
0.9 | 29
1 | 26
2 | 71
3 | 17
4 | 8
More | 14

## Pivots by Unit
Row Labels | Average Days Late | Row Labels | Average Cost Escalations
Architecture | 729 | Technical Services (Randalls Island) | 69.78%
Construction Resources | 303 | Manhattan Team | 67.32%
Staten Island Team | 205 | Environmental Control Unit | 65.95%
Manhattan Team | 139.6497 | Queens Team | 59.73%
Brooklyn Team | 131.1497 | Bronx Team | 46.45%
Construction Project Manager | 123.8571 | Brooklyn Team | 43.4%
Bronx Team | 107.3929 | Construction Project Manager | 42.6%
Requirements Contract Unit | 72.9787 | Staten Island Team | 38.57%
Queens Team | 69.1101 | Construction Resources | 37.11%
Other | 64.9643 | Other | 32.85%
Technical Services (Randalls Isl.) | 55.1646 | Requirements Contract Unit | 32.08%
Croton Unit | 36.2857 | Architecture | 31.63%
Engineering | -15 | Tree Unit | 17.82%
Tree Unit | -61.0447 | Croton Unit | 12.53%
Environmental Control Unit | -424 | Engineering | 0%
Grand Total | 78.2039 | Grand Total | 43.52%

## Data for Regression
Project No. | Project Title | Design Schedule and Completion Date | Design Actual Completion Date | Title Request | Construction Registered Amount | Total Budget | Registration Approved; Pending Order-to- Work Date | Scheduled Completion Date | Final Inspection | Status | Construction Unit | Coded Unit | ln(cost) | Electrical | Tree | Landscape | Plumbing | Park | Station | Playground | Architecture | Bronx Team | Brooklyn Team | Construction Project Manager | Construction Resources | Croton Unit | Engineering | Environmental Control Unit | Manhattan Team | Queens Team | Requirements Contract Unit | Staten Island Team | Technical Services (Randalls Island) | Tree Unit | Days Late | Cost Escalations
B002-101M | AMERSFORT PARK RECONSTRUCTION | 2000-12-15 | 2001-02-22 | 2000-09-08 | 572915 | 710000 | 2001-06-18 | 2001-12-14 | 2002-01-28 | GI | B | Brooklyn Team | 13.2585 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 23.93%
B002-199 | AMERSFORT PARK - GAZEBO & SPRAY FEATURE | 2000-02-08 | 2000-03-06 | 1999-06-16 | 666792 | 933000 | 2000-08-28 | 2001-02-23 | 2001-10-24 | GI | B | Brooklyn Team | 13.4102 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 39.92%
B008-101M | BETSY HEAD PLGD - INSTALL RECREATIONAL LIGHTING F/BALLFIELDS | 2001-03-15 | 2001-04-11 | 2000-11-20 | 499619 | 650000 | 2001-09-10 | 2002-06-06 | 2002-06-04 | GI | B | Brooklyn Team | 13.1216 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 30.1%
B008-199 | BETSY HEAD PLAYGROUND - RUNNING TRACK | 1999-03-31 | 1999-04-19 | 1998-08-10 | 915549 | 1186000 | 1999-08-18 | 2000-05-23 | 2001-05-07 | GI | CPM | Construction Project Manager | 13.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 29.54%
B012-102M | BROWER PARK - RECONSTR. OF A PORTION OF PLAYGROUND | 2001-12-28 | 2002-03-01 | 2001-08-17 | 602129 | 813000 | 2002-10-15 | 2003-10-09 | 2003-10-21 | GI | B | Brooklyn Team | 13.3082 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 35.02%
B012-197/497 | BROWER PARK - CONSTR. OF COMFORT STATION | 1998-01-31 | 1998-04-04 | 1996-08-05 | 354785 | 681000 | 1998-08-10 | 1999-08-09 | 1999-12-08 | GI | B | Brooklyn Team | 12.7793 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 91.95%
B012-297 | (ELECTRICAL) CONSTR OF COMFORT STATION IN BROWER PARK | 1998-01-13 | 1998-04-02 | 1996-08-05 | 13600 | 16000 | 1998-08-10 | 1999-08-09 | 1999-12-08 | GI | B | Brooklyn Team | 9.5178 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 17.65%
B012-397 | (PLUMBING) CONSTR OF COMFORT STATION IN BROWER PARK | 1998-01-31 | 1998-04-04 | 1996-08-05 | 64422 | 65000 | 1998-08-10 | 1999-08-09 | 1999-12-08 | GI | B | Brooklyn Team | 11.0732 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 0.8972%
B012-497 | (H&V) CONSTR OF COMFORT STATION IN BROWER PARK | 1998-01-13 | 1998-04-02 | 1996-08-05 | 17620 | 18000 | 1998-08-10 | 1999-08-09 | 1999-12-08 | GI | B | Brooklyn Team | 9.7768 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 2.157%
B016-101M | MARIA HERNANDEZ PARK - PORTION OF | 2001-01-30 | 2001-04-03 | 2000-09-01 | 1496660 | 1996000 | 2001-09-17 | 2002-06-13 | 2003-03-25 | GI | B | Brooklyn Team | 14.2187 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 33.36%
B016-102M | MARIA HERNANDEZ PARK - PHASE 2 | 2002-03-15 | 2003-02-14 | 2001-11-07 | 767490 | 1066000 | 2003-09-08 | 2004-03-05 | 2004-11-09 | GI | B | Brooklyn Team | 13.5509 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 38.89%
B017-105M | BUSHWICK PLGD - DEMOLITION OF HANDBALL CT BLEACHER & RECONSTR OF BALLFIELD | 2004-11-15 | 2004-12-07 | 2004-07-26 | 1169590.4 | 1665000 | 2005-09-06 | 2006-06-02 | 2006-06-02 | GI | B | Brooklyn Team | 13.9722 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.36%
B019-100M | CARROLL PARK - BALLFIELD, BOCCI & BASKETBALL CTS. | 2000-01-21 | 2000-02-01 | 1999-09-07 | 437019 | 603000 | 2000-08-21 | 2000-12-18 | 2001-02-09 | GI | CPM | Construction Project Manager | 12.9877 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 37.98%
B021-198 | COMMODORE BARRY POOL - LINERS & FILTER SYSTEM | 1997-12-31 | 1998-01-26 | 1997-08-11 | 146632 | 220000 | 1998-06-01 | 1998-09-08 | 1998-12-22 | FI | B | Brooklyn Team | 11.8957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 50.04%
B023-197 | PLGD. @ LAFAYETTE AVE. BET. MALCOLM X BLVD. & PATCHEN AVE. | 1998-03-09 | 1998-04-08 | 1997-04-28 | 438370 | 622000 | 1998-09-08 | 1999-05-05 | 1999-09-16 | GI | CPM | Construction Project Manager | 12.9908 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 41.89%
B026-199 | CUYLER GORE PARK RECONSTR. | 1999-11-22 | 1999-11-18 | 1999-05-26 | 517799 | 777000 | 2000-04-24 | 2000-09-20 | 2001-06-21 | GI | B | Brooklyn Team | 13.1573 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 50.06%
B028-100M | DYKER BEACH PARK - TENNIS CTS @ BAY 8TH ST. | 2000-09-29 | 2000-09-26 | 2000-06-07 | 314230 | 525000 | 2001-02-20 | 2001-07-19 | 2001-06-26 | GI | R | Staten Island Team | 12.6579 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -23 | 67.08%
B028-101M | DYKER BEACH PARK - RECONSTR. BALLFIELD & CONSTR. SOCCER FIELD | 2001-02-27 | 2001-02-27 | 2000-08-02 | 1366088 | 2400000 | 2001-09-05 | 2002-06-01 | 2002-10-30 | GI | CPM | Construction Project Manager | 14.1275 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 75.68%
B028-102M | DYKER BEACH PARK - ARTIFICIAL TURF BALLFIELD | 2002-03-01 | 2002-07-11 | 2001-10-12 | 556410 | 741000 | 2003-04-01 | 2003-08-28 | 2003-10-03 | FI | CPM | Construction Project Manager | 13.2293 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 33.18%
B028-105M | DYKER BEACH PARK - TWO BOCCIE SHELTERS |  | 2004-11-05 | 2004-08-20 | 153500 | 213000 | 2006-04-10 | 2006-09-06 | 2006-10-20 | FI | B | Brooklyn Team | 11.9415 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 38.76%
B028-194 | DYKER BEACH - BAY 8TH & CROPSEY PLGD. | 1997-02-05 | 1997-03-25 | 1993-09-13 | 201173 | 393000 | 1997-09-02 | 1998-01-29 | 1998-05-01 | GI | R | Staten Island Team | 12.2119 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 92 | 95.35%
B028-298 | DYKER BEACH PARK - PLGD. @ 86TH ST. & 14TH AVE. | 1998-04-01 | 1998-04-07 | 1997-10-31 | 505499 | 672000 | 1998-12-17 | 1999-09-12 | 1999-09-08 | GI | R | Staten Island Team | 13.1333 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -4 | 32.94%
B032-196 | FT. GREENE PK.- PLGD & C.S. @ MYRTLE & ST.EDWARDS ST. | 1996-10-31 | 1996-11-04 | 1995-08-04 | 896620 | 1163000 | 1997-05-26 | 1998-02-19 | 1998-04-30 | GI | B | Brooklyn Team | 13.7064 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 29.71%
B033-195A | FT. HAMILTON PLAZA (94TH ST & 4TH AVE.) | 1998-10-23 | 1998-12-15 | 1994-09-15 | 288595 | 395000 | 1999-05-24 | 1999-09-20 | 1999-10-29 | GI | B | Brooklyn Team | 12.5728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 36.87%
B038-197 | FULTON PK - LANDSCAPE & SPRINKLER | 1997-05-15 | 1997-05-15 | 1997-05-19 | 383398 | 650000 | 1997-09-15 | 1998-05-12 | 1998-05-21 | GI | B | Brooklyn Team | 12.8568 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 69.54%
B040-101M | GRAND ARMY PLAZA - BAILEY FOUNTAIN | 2002-07-05 | 2001-09-21 | 2000-07-31 | 1541925 | 1924000 | 2002-08-26 | 2003-08-25 | 2004-07-26 | GI | B;PP | Other | 14.2485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 24.78%
B040-199 | P.P. - GRAND ARMY PLAZA - BRONZE STATUES RESTORATION | 1999-03-04 | 1999-03-04 | 1998-12-10 | 172325 | 184000 | 1999-06-01 | 1999-11-27 | 1999-11-27 | FI | A;CPF | Other | 12.0571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.775%
B042-100M | GRAVESEND PARK - ROLLER HOCKEY RINK & DEMO OF 5 TENNIS CTS. | 2000-01-31 | 2000-03-08 | 1999-10-08 | 387727 | 550000 | 2000-10-02 | 2001-01-29 | 2001-05-23 | GI | CPM | Construction Project Manager | 12.8681 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 41.85%
B042-101M | GRAVESEND PARK - PORTION | 2001-03-30 | 2001-03-13 | 2000-10-11 | 469698 | 650000 | 2001-08-20 | 2002-03-17 | 2002-03-15 | GI | CPM | Construction Project Manager | 13.0598 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 38.39%
B049-105MA | IRVING SQUARE PARK - NORTH EAST PORTION OF | 2004-02-15 | 2005-03-23 | 2005-01-05 | 1013023 | 1604000 | 2006-03-27 | 2006-12-21 | 2007-01-26 | FI | B | Brooklyn Team | 13.8284 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 58.34%
B050-100M | VAN VOORHEES PARK - TENNIS & BASKETBALL COURTS | 2000-02-28 | 2000-03-29 | 1999-10-20 | 336728 | 500000 | 2000-09-18 | 2001-02-14 | 2001-07-05 | GI | B | Brooklyn Team | 12.727 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 48.49%
B050-102M | VAN VOORHEES PARK - SYNTHETIC TURF BASEBALL FIELD | 2002-10-25 | 2002-11-06 | 2001-11-01 | 480209 | 663000 | 2003-06-02 | 2003-10-29 | 2004-02-18 | GI | B | Brooklyn Team | 13.082 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 38.06%
B050-197 | VAN VORHEES PLGD. - LOWER SECTION | 1997-11-30 | 1997-12-31 | 1996-08-06 | 653712 | 857000 | 1998-04-27 | 1998-11-22 | 1998-10-09 | GI | B | Brooklyn Team | 13.3904 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | 31.1%
B051-196 | WM. KELLY MEMORIAL PARK PLGD. | 1996-11-18 | 1997-04-01 | 1995-10-11 | 630924 | 968000 | 1997-09-22 | 1998-04-19 | 1998-06-18 | GI | B | Brooklyn Team | 13.3549 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 53.43%
B052-100M | LEIF ERICSON PARK - P.O. CHRISTOPHER HOBAN BALLFIELD - NATURAL TURF & ASPHALT | 2000-10-25 | 2000-10-26 | 2000-05-17 | 519592 | 659000 | 2001-07-02 | 2001-12-28 | 2003-01-07 | GI | B | Brooklyn Team | 13.1608 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 26.83%
B052-108M | TORNADO-DAMAGED PORTIONS OF LEIF ERICSON PK (EMERG. RECONSTR) (B052) |  | 2007-10-09 | 2007-09-05 | 723400.61 | 844000 | 2007-09-26 | 2007-12-24 | 2008-03-19 | FI | B;CR | Other | 13.4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 16.67%
B052-199 | LEIF ERICSON PK - BASKETBALL CTS. @ 66 - 67 STS BET. 4 & 5 AVE | 1999-02-26 | 1999-03-02 | 1998-09-25 | 199002 | 247000 | 1999-06-07 | 1999-11-03 | 1999-08-03 | GI | B | Brooklyn Team | 12.2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92 | 24.12%
B052-299 | LEIF ERICSON PARK - BET. 66-67 STS,8TH AV & FT. HAMILTON PKWY | 1999-02-28 | 1999-03-18 | 1998-10-05 | 491191 | 695000 | 1999-07-26 | 2000-01-21 | 2000-03-10 | GI | B | Brooklyn Team | 13.1046 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 41.49%
B054-100M | LINCOLN TERRACE PK - LIGHTING F/BASEBALL FIELD & NETBALL CTS. | 2000-01-28 | 2000-02-02 | 1999-08-18 | 229951 | 341000 | 2000-09-11 | 2001-03-09 | 2001-03-09 | GI | B | Brooklyn Team | 12.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.29%
B054-197A | LINCOLN TERRACE PARK TENNIS CT. LIGHTS & LANDSCAPE | 1997-09-02 | 1997-09-02 | 1996-09-11 | 346461 | 465000 | 1998-01-12 | 1998-07-10 | 1998-07-10 | FI | B | Brooklyn Team | 12.7555 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21%
B054-198 | LINCOLN TERRACE PARK BALLFIELD | 1999-03-27 | 1999-04-16 | 1998-04-03 | 299174 | 444000 | 1999-09-13 | 2000-04-09 | 2000-03-22 | GI | CPM | Construction Project Manager | 12.6088 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18 | 48.41%
B055-103M/403M | STERNBERG PARK - PLGD & COMFORT STATION | 2003-03-31 | 2003-07-10 | 2002-10-08 | 1649930 | 2540000 | 2004-04-05 | 2005-04-04 | 2006-06-30 | GI | B | Brooklyn Team | 14.3162 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 53.95%
B055-104M | STERNBERG PARK - BALLFIELDS | 2004-03-31 | 2004-05-05 | 2003-09-19 | 1094821 | 1300000 | 2005-01-31 | 2005-07-29 | 2005-12-14 | GI | B | Brooklyn Team | 13.9061 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 18.74%
B055-106M | F. HAMBURGER STERNBERG PK - INSTALLTN OF REC LIGHTING IN PARK |  | 2005-11-18 | 2005-09-15 | 462525 | 595000 | 2006-10-02 | 2007-06-28 | 2007-06-28 | FI | B | Brooklyn Team | 13.0445 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.64%
B055-203M | (ELECTRICAL) STERNBERG PARK - PLGD & COMFORT STATION | 2003-03-31 | 2003-04-07 | 2002-10-08 | 17640 | 18000 | 2004-04-05 | 2005-04-04 | 2006-06-30 | FI | B | Brooklyn Team | 9.7779 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 2.041%
B055-303M | (PLUMBING) STERNBERG PARK - PLGD & COMFORT STATION | 2003-03-31 | 2003-07-24 | 2002-10-08 | 79073.28 | 79073 | 2004-04-05 | 2005-04-04 | 2006-06-30 | GI | B | Brooklyn Team | 11.2781 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | -0.0003541%
B055-403M | (H&V) STERNBERG PARK - PLGD & COMFORT STATION | 2003-03-31 | 2003-07-10 | 2002-10-08 | 20133 | 21000 | 2004-04-05 | 2005-04-04 | 2006-06-30 | FI | B | Brooklyn Team | 9.9101 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 4.306%
B056-102M | DR. MARTIN LUTHER KING, JR. PARK | 2002-06-14 | 2003-01-17 | 2001-12-03 | 611220 | 929000 | 2003-07-29 | 2004-04-23 | 2004-08-04 | GI | B | Brooklyn Team | 13.3232 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 51.99%
B057-100MA | MARINE PARK PLGD @ FILLMORE AVE. & MADISON PL. ADJ TO P.S.278 | 2000-10-31 | 2001-02-09 | 2000-05-17 | 1170900 | 1661000 | 2001-10-15 | 2002-07-11 | 2002-11-26 | GI | B | Brooklyn Team | 13.9733 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 41.86%
B057-104M | MARINE PARK - CONSTR OF TOT PLGD, SKATE PARK, VOLLEYBALL & KICKBALL COURTS | 2005-10-31 | 2005-07-15 | 2005-06-21 | 925592.24 | 1349000 | 2006-09-25 | 2007-06-21 | 2007-11-05 | FI | B | Brooklyn Team | 13.7382 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 45.74%
B057-195 | MARINE PK. LANDSCAPE @ AVENUE U, 33 & BURNETT STS. | 1997-03-31 | 1997-04-10 | 1994-08-17 | 1706325 | 2164000 | 1997-09-03 | 1999-05-25 | 1999-11-12 | GI | B | Brooklyn Team | 14.3499 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 26.82%
B057-197/497A | MARINE PARK - CONSTR OF ENVIRONMENTAL CTR | 1997-03-31 | 1997-04-14 | 1997-01-13 | 1417727 | 2962000 | 1997-10-20 | 1999-07-11 | 2000-02-16 | GI | B | Brooklyn Team | 14.1646 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 108.9%
B057-198 | MARINE PARK - P.S. 277 (DR. JOHN'S) PLGD. @ AVE.X | 1998-01-30 | 1998-02-18 | 1997-09-09 | 489313 | 714000 | 1998-09-08 | 1999-06-14 | 1999-07-13 | GI | B | Brooklyn Team | 13.1008 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 45.92%
B057-199 | MARINE PK. - LENAPE PLGD. @ AVE. U & 38TH ST. | 1999-03-15 | 1999-03-31 | 1998-11-18 | 764867 | 991000 | 1999-06-28 | 2000-04-22 | 2000-03-21 | GI | B | Brooklyn Team | 13.5475 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32 | 29.57%
B057-297A1 | (ELECTRICAL) MARINE PARK - CONSTR OF ENVIRONMENTAL CTR | 1997-03-31 | 1999-01-14 | 1997-01-13 | 216700 | 217000 | 1999-05-03 | 1999-12-19 | 2000-02-16 | GI | B | Brooklyn Team | 12.2863 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0.1384%
B057-306M | MARINE PK FIELD HOUSE - EMERGENCY DEPLOYMENT OF TEMP TOILET & OFFICE FACILITIES | 2006-05-24 | 2006-05-24 | 2006-05-24 | 60830 | 60830 | 2006-06-12 | 2006-11-08 | 2007-01-30 | FI | B;CR | Other | 11.0158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0%
B057-397 | (PLUMBING) MARINE PARK - CONSTR OF ENVIRONMENTAL CTR | 1997-03-31 | 1997-04-10 | 1997-01-13 | 81523 | 82000 | 1997-10-20 | 1999-07-11 | 2000-02-16 | GI | B | Brooklyn Team | 11.3086 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0.5851%
B057-497A | (HVAC) MARINE PARK - CONSTR OF ENVIRONMENTAL CTR | 1997-03-31 | 1998-10-28 | 1997-01-13 | 165314 | 165000 | 1999-04-26 | 1999-07-24 | 2000-02-16 | GI | B | Brooklyn Team | 12.0156 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | -0.1899%
B057-698 | MARINE PARK- SHORELINE & EROSION CONTROL (EMERGENCY) | 1997-10-31 | 1997-10-06 | 1997-09-22 | 512500 | 975000 | 1997-11-10 | 1998-01-08 | 1998-05-12 | FI | B | Brooklyn Team | 13.1471 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 90.24%
B057-795 | MARINE PARK BALLFIELDS @ GERRITSEN AVE. & AVE X | 1997-08-05 | 1997-09-16 | 1995-04-24 | 319191 | 511000 | 1998-03-16 | 1998-07-13 | 1998-09-09 | GI | B | Brooklyn Team | 12.6735 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 60.09%
B057-798 | MARINE PARK BOCCI COURTS & PATHS | 1998-10-31 | 1998-11-02 | 1997-10-01 | 344434 | 610000 | 1999-04-26 | 1999-10-22 | 1999-11-17 | GI | B | Brooklyn Team | 12.7497 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 77.1%
B058-100M | MCCARREN PARK (WADING POOL & LANDSCAPE) | 2000-03-22 | 2000-03-31 | 1999-08-13 | 588114 | 755000 | 2000-09-11 | 2001-04-08 | 2001-08-02 | GI | B | Brooklyn Team | 13.2847 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 28.38%
B058-103M | MCCARREN PARK - SOCCER FIELD & RUNNING TRACK | 2003-12-31 | 2004-03-22 | 2003-10-08 | 1216929 | 1731000 | 2004-10-01 | 2005-06-27 | 2005-09-28 | GI | B | Brooklyn Team | 14.0118 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 42.24%
B058-199 | MCCARREN PARK - FATHER POPIELUSKO SQUARE | 1999-03-26 | 1999-03-29 | 1998-10-21 | 509342 | 674000 | 1999-08-16 | 2000-02-11 | 2000-04-13 | GI | B | Brooklyn Team | 13.1409 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 32.33%
B058-200M | MCCARREN PARK - HANDBALL & BOCCI COURTS | 2000-03-08 | 2000-03-24 | 1999-09-10 | 412133 | 601000 | 2000-09-25 | 2001-01-22 | 2001-07-11 | GI | CPM | Construction Project Manager | 12.9291 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 45.83%
B058-206M | MC CARREN PARK - CONSTR OF REC LIGHTING FOR A SOCCER FIELD | 2005-12-15 | 2006-03-20 | 2005-10-31 | 920071 | 1143000 | 2007-03-26 | 2007-09-21 | 2008-03-19 | FI | B | Brooklyn Team | 13.7322 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 24.23%
B058-299 | MCCARREN PARK - BALLFIELD | 2000-03-22 | 2000-03-31 | 1999-06-03 | 430300 | 560000 | 2000-09-25 | 2001-03-23 | 2001-10-10 | GI | B | Brooklyn Team | 12.9722 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 30.14%
B060-100M | MCKINLEY PARK - PLGD @ BAYRIDGE & FT.HAMILTON PKWYS & 7TH AVE. | 2000-03-31 | 2000-03-21 | 1999-09-15 | 741046 | 910000 | 2000-09-18 | 2001-04-15 | 2001-09-14 | GI | CPM | Construction Project Manager | 13.5158 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 22.8%
B060-101M | MCKINLEY PARK - PATHS & LANDSCAPE | 2001-01-19 | 2001-02-09 | 2000-08-23 | 518749 | 1477000 | 2001-09-17 | 2002-03-15 | 2003-06-20 | GI | CPM | Construction Project Manager | 13.1592 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 184.7%
B061-105M | MCLAUGHLIN PARK - BALLFIELD, SPRAY SHWR AREA, BASKETBALL & HANDBALL CTS | 2005-06-15 | 2005-08-09 | 2005-03-21 | 1926044 | 3005000 | 2006-04-24 | 2007-04-18 | 2007-01-30 | GI | B | Brooklyn Team | 14.471 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78 | 56.02%
B065-102M | OCEAN PKWY MALLS - SEA BREEZE AVE TO OCEAN VIEW AVE | 2002-08-01 | 2003-03-21 | 2001-12-19 | 303951 | 517000 | 2004-04-05 | 2004-09-01 | 2004-08-31 | FI | B | Brooklyn Team | 12.6246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 70.09%
B065-103M | OCEAN PARKWAY MALLS/BETWEEN AVENUE C & CHURCH AVE | 2003-03-16 | 2004-03-24 | 2003-09-29 | 557458 | 790000 | 2004-07-19 | 2005-01-14 | 2005-01-06 | FI | B | Brooklyn Team | 13.2311 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 41.71%
B065-198 | OCEAN PKWY MALLS - PORTIONS BETWEEN CHURCH & FOSTER AVES. | 2000-03-06 | 2000-03-18 | 1999-09-27 | 1382892 | 1806000 | 2000-09-19 | 2001-09-13 | 2001-12-14 | FI | CPM | Construction Project Manager | 14.1397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 30.6%
B066-101M | OWL'S HEAD PARK- OVERLOOK TERR, SLOPE, BRICK GATEWAY & LANDMARKED WALL | 2001-10-30 | 2002-03-27 | 2000-08-07 | 1354395 | 1852000 | 2002-10-21 | 2003-10-20 | 2004-05-17 | GI | B | Brooklyn Team | 14.1189 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 36.74%
B066-102M/402M | OWL'S HEAD PARK - COMFORT STATION | 2002-11-15 | 2003-03-27 | 2001-11-29 | 412230.12 | 1136000 | 2004-11-08 | 2005-11-07 | 2006-10-27 | GI | B | Brooklyn Team | 12.9293 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354 | 175.6%
B066-199 | OWLS HEAD PARK - SKATEBOARD FACILITY | 1999-12-22 | 2000-03-31 | 1999-05-19 | 830183 | 1150000 | 2000-09-25 | 2001-05-22 | 2001-08-08 | GI | B | Brooklyn Team | 13.6294 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 38.52%
B066-202MA | (ELECTRICAL) OWL'S HEAD PARK - COMFORT STATION | 2002-11-15 | 2003-03-27 | 2001-11-29 | 39437.84 | 40000 | 2004-03-01 | 2005-02-28 | 2006-10-27 | GI | B | Brooklyn Team | 10.5825 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606 | 1.425%
B066-302M | (PLUMBING) OWL'S HEAD PARK - COMFORT STATION | 2002-11-15 | 2003-03-27 | 2001-11-29 | 43929.6 | 44000 | 2004-03-01 | 2005-02-28 | 2006-10-27 | GI | B | Brooklyn Team | 10.6903 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606 | 0.1603%
B066-402M | (H&V) OWL'S HEAD PARK - COMFORT STATION | 2002-11-15 | 2003-03-27 | 2001-11-29 | 40700 | 40700 | 2004-03-01 | 2005-02-28 | 2006-10-27 | GI | B | Brooklyn Team | 10.614 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606 | 0%
B068-101M | PARADE GROUNDS - PORTION OF BALLFIELDS (PHASE II) | 2001-02-10 | 2001-02-12 | 2000-07-31 | 3841899 | 4500000 | 2001-08-06 | 2002-08-05 | 2004-03-25 | GI | B;PP | Other | 15.1615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598 | 17.13%
B068-102M | PARADE GROUNDS - PORTION OF BALLFIELDS (PHASE III) | 2002-03-15 | 2002-03-08 | 2001-08-15 | 4342107 | 5650000 | 2002-10-21 | 2004-04-12 | 2004-06-25 | GI | B;PP | Other | 15.2839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 30.12%
B068-105M | CATON AVENUE SIDEWALKS (PARADE GDS BKLYN SO BOUND) PRSTATEMM | 2005-08-01 | 2005-12-28 | 2005-01-03 | 152409 | 250000 | 2006-06-19 | 2006-10-16 | 2006-10-11 | FI | B;PP | Other | 11.9343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 64.03%
B068-196T | PARADE GROUND SOCCER FIELDS | 1997-06-11 | 1997-06-12 | 1995-07-19 | 162830 | 211000 | 1997-09-29 | 1998-01-26 | 1998-09-29 | GI | B;PP | Other | 12.0005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 29.58%
B068-199 | PARADE GROUNDS SPORT FIELDS & BALLFIELDS | 2000-03-22 | 2000-02-11 | 1999-07-28 | 1052062 | 1500000 | 2000-08-28 | 2001-01-09 | 2001-06-22 | GI | B;PP | Other | 13.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 42.58%
B068-201MA | PARADE GROUNDS PLAYGROUND - SOUTHEAST CORNER | 2002-09-27 | 2002-09-27 | 2000-07-31 | 1366370 | 1690000 | 2006-06-12 | 2007-06-11 | 2007-09-11 | FI | B;PP | Other | 14.1277 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 23.69%
B073-100M/400M | PROSPECT PARK - LULLWATER BOATHOUSE INTERIOR | 2000-02-15 | 2000-03-20 | 1999-06-29 | 1196666 | 1993000 | 2000-09-05 | 2001-07-11 | 2002-02-21 | GI | B;PP | Other | 13.995 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 66.55%
B073-101M | PROSPECT PARK - PERIMETER SIDEWALKS (PPW F/3RD - 5TH STS) | 2001-01-10 | 2001-01-12 | 2000-07-31 | 542000 | 643000 | 2001-07-09 | 2002-01-04 | 2002-02-28 | GI | B;PP | Other | 13.203 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 18.63%
B073-102M/402M | PROSPECT PARK - PICNIC HOUSE (PPA) | 2003-05-15 | 2003-09-30 | 2001-07-27 | 2185247 | 3171000 | 2004-03-25 | 2005-04-03 | 2005-11-18 | FI | B;PP | Other | 14.5972 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 45.11%
B073-196 | P.P. RAVINE - PHASE 2 (ERSDALE TO ROCK ARCH BRIDGE) | 1996-03-31 | 1996-04-08 | 1995-07-19 | 1282557 | 1633000 | 1996-09-03 | 1998-02-24 | 1998-08-03 | GI | B;PP | Other | 14.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 27.32%
B073-198 | P.P. - LANDSCAPING BEHIND THE ENTRANCE OF GRAND ARMY PLAZA | 1998-03-31 | 1998-01-23 | 1997-07-25 | 72771 | 101000 | 1998-05-04 | 1998-08-31 | 1999-05-05 | FI | B;PP | Other | 11.1951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 38.79%
B073-200M | (ELECTRICAL) PROSPECT PARK - LULLWATER BOATHOUSE INTERIOR | 2000-02-15 | 2000-03-20 | 1999-06-29 | 237000 | 237000 | 2000-09-05 | 2001-07-11 | 2002-05-03 | GI | B;PP | Other | 12.3758 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 0%
B073-201M | P.P. - BINNEWATER & SURROUNDING LANDSCAPE RESTORATION | 2001-08-15 | 2001-08-22 | 2000-07-31 | 942985 | 1236000 | 2002-03-18 | 2003-03-17 | 2003-01-09 | GI | B;PP | Other | 13.7568 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67 | 31.07%
B073-202M | (ELECTRICAL) PROSPECT PARK - PICNIC HOUSE |  | 2003-10-03 | 2001-07-27 | 207622 | 208000 | 2004-03-25 | 2005-04-03 | 2005-09-15 | GI | B;PP | Other | 12.2435 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 0.1821%
B073-205M | NETHERMEAD PATHS (IN PROSPECT PK) - PORTION OF | 2003-09-30 | 2005-12-01 | 2005-03-22 | 136088 | 180000 | 2006-04-24 | 2006-07-22 | 2006-08-07 | FI | B;PP | Other | 11.8211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 32.27%
B073-297 | PROSPECT PARK - PERISTYLE (GRECIAN SHELTER) | 1997-03-19 | 1997-03-31 | 1996-08-01 | 257000 | 379000 | 1997-09-02 | 1998-09-01 | 1999-05-11 | GI | B;PP | Other | 12.4568 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 47.47%
B073-298 | P.P. - PARKSIDE & OCEAN AVE. ENTRANCE & LANDSCAPE | 1998-12-30 | 1998-11-17 | 1997-07-25 | 736609 | 1025000 | 1999-04-05 | 2000-04-03 | 2000-09-19 | GI | B;PP | Other | 13.5098 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 39.15%
B073-299 | P.P. - WESTSIDE SIDEWALKS FROM 7TH ST. TO 5TH ST. | 1999-03-31 | 1999-03-12 | 1998-07-28 | 361146 | 500000 | 1999-06-28 | 1999-10-25 | 1999-12-03 | GI | B;PP | Other | 12.797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 38.45%
B073-302M | (PLUMBING) PROSPECT PARK - PICNIC HOUSE |  | 2003-09-30 | 2001-07-27 | 125000 | 125000 | 2004-03-25 | 2005-04-03 | 2005-09-15 | GI | B;PP | Other | 11.7361 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 0%
B073-396 | P.P. - BOATHOUSE & PICNIC HOUSE ROOFS | 1996-03-31 | 1996-04-09 | 1995-08-21 | 270252 | 397000 | 1996-08-05 | 1997-05-11 | 1998-05-14 | FI | B | Brooklyn Team | 12.5071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 46.9%
B073-398 | P.P. - RAVINE FROM ROCK ARCH BRIDGE TO NETHERMEAD ARCH | 1998-03-15 | 1998-02-27 | 1997-07-25 | 867559 | 1525000 | 1998-07-20 | 2000-01-10 | 1999-08-18 | GI | B;PP | Other | 13.6734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -145 | 75.78%
B073-399 | P.P. - PLGD. ADJ TO BANDSHELL BET. 9TH & 11TH STS. | 2000-06-09 | 2000-07-10 | 1998-07-28 | 1510441 | 1901000 | 2000-12-11 | 2002-01-09 | 2002-04-05 | GI | B;PP | Other | 14.2279 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 25.86%
B073-400M | (H&V) PROSPECT PARK - LULLWATER BOATHOUSE INTERIOR | 2000-02-15 | 2000-03-20 | 1999-06-29 | 71300 | 79000 | 2000-09-05 | 2001-07-11 | 2002-02-21 | GI | B;PP | Other | 11.1747 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 10.8%
B073-495/595 | P.P. - BANDSHELL & SURROUNDING LANDSCAPE | 1997-07-30 | 1997-07-30 | 1994-09-16 | 941337 | 1624000 | 1997-11-24 | 1998-07-31 | 1999-05-04 | GI | B;PP | Other | 13.7551 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 72.52%
B073-498 | P.P. - PERIMETER SIDEWALKS (MONTGOMERY-2ND & 9TH-7TH STS) | 1998-03-31 | 1998-02-11 | 1997-08-05 | 653083 | 857000 | 1998-06-01 | 1999-03-27 | 1999-03-26 | GI | B;PP | Other | 13.3895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 31.22%
B073-499A | P.P. - TENNIS HOUSE (CTR FOR URBAN ENVIRON) ROOF RECONSTR. | 1999-01-31 | 1999-03-19 | 1998-09-16 | 188970 | 250000 | 1999-08-16 | 1999-12-13 | 1999-12-10 | GI | B | Brooklyn Team | 12.1493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 32.3%
B073-500M | P.P. - CIRCLE ENTRANCE & SURROUNDING LANDSCAPE | 2000-03-22 | 2000-03-15 | 1999-07-14 | 1423508 | 1752000 | 2000-09-05 | 2001-09-04 | 2002-02-07 | GI | B;PP | Other | 14.1686 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 23.08%
B073-508M | (EMERGENCY) PROSPECT PARK - EASTWOOD COMFORT STATION |  | 2008-03-10 | 2008-03-11 | 95000 | 95000 | 2008-03-07 | 2008-04-05 | 2008-03-26 | FI | CR;B | Other | 11.4616 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0%
B073-594A | P.P. - RAVINE UPPER LAKES | 1995-01-15 | 1995-02-06 | 1994-03-21 | 2825933 | 3535000 | 1996-04-15 | 1998-09-16 | 1998-07-17 | GI | B;PP | Other | 14.8543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61 | 25.09%
B073-595 | (ELECTRICAL) P.P. BANDSHELL | 1997-07-30 | 1997-07-30 | 1994-09-16 | 95900 | 105000 | 1997-11-24 | 1998-07-31 | 1999-05-04 | GI | B;PP | Other | 11.4711 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 9.489%
B073-598/898 | P.P. - BANDSHELL & SURROUNDING LANDSCAPE | 1998-08-11 | 1998-08-11 | 1997-10-15 | 589489 | 941000 | 1999-01-18 | 1999-09-14 | 2000-03-28 | GI | B;PP | Other | 13.287 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 59.63%
B073-600M | PROSPECT PARK - WEST SIDEWALKS | 1999-11-30 | 2000-02-07 | 1999-07-16 | 447695 | 537000 | 2000-09-05 | 2001-01-27 | 2001-11-21 | FI | B;PP | Other | 13.0119 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298 | 19.95%
B073-698 | (ELECTRICAL) P.P. - BANDSHELL & SURROUNDING LANDSCAPE | 1998-08-11 | 1998-08-11 | 1997-10-15 | 118310 | 129000 | 1999-01-18 | 1999-09-14 | 2000-03-28 | GI | B;PP | Other | 11.6811 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 9.036%
B073-700M | PROSPECT PARK - LITCHFIELD VILLA STABILIZATION & RECONSTR | 2001-09-09 | 2002-03-15 | 1999-09-22 | 835068 | 1144000 | 2002-11-25 | 2003-11-24 | 2004-11-30 | GI | B;PP | Other | 13.6353 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 36.99%
B073-798 | (PLUMBING) P.P. - BANDSHELL & SURROUNDING LANDSCAPE | 1998-08-11 | 1998-08-11 | 1997-10-15 | 122500 | 123000 | 1999-01-18 | 1999-09-14 | 2000-03-28 | GI | B;PP | Other | 11.7159 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 0.4082%
B073-898 | (H&V) P.P. - BANDSHELL & SURROUNDING LANDSCAPE | 1998-08-11 | 1998-08-11 | 1997-10-15 | 114000 | 115000 | 1999-01-18 | 1999-09-14 | 2000-03-28 | GI | B;PP | Other | 11.644 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 0.8772%
B073-902M | PROSPECT PARK - BINNENWATER & SURROUNDING LANDSCAPE | 2002-09-15 | 2002-10-10 | 2002-01-28 | 1711459 | 2127000 | 2003-06-04 | 2004-06-02 | 2004-11-24 | GI | B;PP | Other | 14.3529 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 24.28%
B073-998 | P.P. - EXTERIOR OF LULLWATER BOATHOUSE | 1998-06-01 | 1999-03-02 | 1998-02-09 | 1566036 | 2303000 | 1999-08-09 | 2000-08-12 | 2001-08-22 | GI | B;PP | Other | 14.2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 47.06%
B077-195 | COFFEY PARK PLGD. & C.S. | 1996-01-25 | 1996-11-27 | 1995-05-02 | 1339990 | 1919000 | 1997-11-03 | 1998-10-28 | 1999-07-08 | GI | CPM | Construction Project Manager | 14.1082 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253 | 43.21%
B078-101M | GRACE PLAYGROUND - BALLFIELD & DRAINAGE SYSTEM | 2001-08-30 | 2001-07-09 | 2000-10-27 | 120675 | 194000 | 2002-03-04 | 2002-07-01 | 2003-03-28 | GI | B | Brooklyn Team | 11.7009 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 60.76%
B080-100M | ASSER LEVY PARK - LAWN RESTORATION @ OVAL NEAR BANDSHELL | 2000-03-01 | 2000-02-08 | 1999-09-13 | 397751 | 651000 | 2000-09-11 | 2001-01-08 | 2001-06-08 | GI | CPM | Construction Project Manager | 12.8936 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 63.67%
B080-197/397 | ASSER LEVY PK - PARTIAL BANDSHELL & LANDSCAPE RESTORATION | 1998-03-04 | 1998-10-19 | 1996-10-08 | 588136 | 900000 | 1999-03-01 | 1999-08-27 | 1999-10-22 | GI | CPM | Construction Project Manager | 13.2847 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 53.03%
B080-297 | (ELECTRICAL) ASSER LEVY PK - PARTIAL BANDSHELL & LANDSCAPE RESTORATION | 1998-03-04 | 1998-10-19 | 1996-10-08 | 97843 | 111000 | 1999-03-01 | 1999-08-27 | 1999-10-22 | GI | CPM | Construction Project Manager | 11.4911 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 13.45%
B080-397 | (MECHANICAL) ASSER LEVY PK - PARTIAL BANDSHELL & LANDSCAPE RESTORATION | 1998-03-04 | 1998-10-19 | 1996-10-08 | 62480 | 83000 | 1999-03-01 | 1999-08-27 | 1999-10-22 | GI | CPM | Construction Project Manager | 11.0426 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 32.84%
B082-100M | SHORE ROAD PK - EROSION CONTROL BET. FT. HAMILTON PKWY & 90TH ST. | 2001-02-16 | 2001-03-08 | 1999-09-27 | 818500 | 1088000 | 2001-09-17 | 2002-04-14 | 2002-06-14 | GI | CPM | Construction Project Manager | 13.6152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 32.93%
B082-202M | SHORE ROAD PARK - BETWEEN 87TH & 94TH STS.-PORTION OF (INCL.SOIL EROSION, SIDEWALK & TRELLIS) | 2002-07-23 | 2003-04-01 | 2001-10-24 | 1811142 | 2352000 | 2003-08-25 | 2004-06-19 | 2004-08-03 | GI | B | Brooklyn Team | 14.4095 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 29.86%
B082A-101M | SHORE ROAD PARK - BALLFIELDS - 74TH-77TH STREETS | 2001-03-30 | 2001-03-23 | 2000-09-26 | 745577 | 1052000 | 2001-10-08 | 2002-08-03 | 2002-11-07 | GI | CPM | Construction Project Manager | 13.5219 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 41.1%
B082A-102M | SHORE PARKWAY PROMENADE - BETWEEN BAY RIDGE AVE & BAY PARKWAY | 2001-10-15 | 2001-10-26 | 2001-07-05 | 692920 | 896000 | 2002-07-15 | 2003-01-10 | 2002-12-03 | GI | R | Staten Island Team | 13.4487 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -38 | 29.31%
B082A-105M | SHORE ROAD PARK - DUGOUTS @ BASEBALL FIELD #3 |  | 2005-09-23 | 2005-06-14 | 170164 | 230000 | 2006-05-15 | 2006-07-13 | 2006-08-10 | FI | B;CR | Other | 12.0445 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 35.16%
B082A-106M | NARROWS BOTANICAL GARDEN - FENCE | 2006-09-01 | 2006-09-22 | 2006-05-12 | 192675.6 | 294000 | 2007-07-23 | 2007-10-20 | 2008-01-17 | FI | B | Brooklyn Team | 12.1688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 52.59%
B082A-903M | SHORE ROAD PARK - 79TH STREET PLGD | 2003-03-14 | 2004-03-31 | 2003-02-25 | 844352 | 991000 | 2004-09-13 | 2005-09-12 | 2005-06-22 | GI | B | Brooklyn Team | 13.6463 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82 | 17.37%
B087-101M | SUNSET PARK - RECONSTR. OF NORTHERN PORTION | 2001-01-12 | 2001-02-28 | 2000-07-18 | 1139026 | 1403000 | 2001-09-03 | 2002-05-30 | 2002-05-30 | GI | CPM | Construction Project Manager | 13.9457 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.18%
B087-201MA1 | SUNSET PARK - BATHHOUSE (MECHANICAL SYSTEMS) | 2001-01-31 | 2002-01-02 | 1999-08-27 | 427450 | 568000 | 2002-06-03 | 2003-06-02 | 2003-06-02 | FI | TS | Technical Services (Randalls Isl.) | 12.9656 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 32.88%
B088-197 | HERBERT VON KING PARK - 2 PLGDS. | 1997-11-15 | 1997-12-08 | 1997-04-28 | 648706 | 861000 | 1998-05-04 | 1999-01-28 | 1999-04-08 | GI | B | Brooklyn Team | 13.3827 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 32.73%
B088-204M | (ELECTRICAL) VON KING CULTURAL ARTS CENTER | 2004-03-15 | 2004-05-18 | 2003-09-17 | 69680 | 70000 | 2005-06-06 | 2006-03-02 | 2006-03-03 | FI | B | Brooklyn Team | 11.1517 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.4592%
B088-304M | (PLUMBING) VON KING CULTURAL ARTS CENTER | 2004-03-15 | 2004-05-18 | 2003-09-17 | 29881 | 30000 | 2005-06-06 | 2006-03-02 | 2006-03-03 | FI | B | Brooklyn Team | 10.305 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.3982%
B088-404M | (H&V) VON KING CULTURAL ARTS CENTER | 2004-03-15 | 2004-05-18 | 2003-09-17 | 391250 | 392000 | 2005-06-06 | 2006-03-02 | 2006-03-03 | FI | B | Brooklyn Team | 12.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1917%
B090-102M | SOBEL PARK - CONSTRUCTION OF PLAYGROUND | 2002-10-31 | 2002-11-06 | 2001-11-09 | 241840 | 321000 | 2003-05-19 | 2003-09-15 | 2003-10-02 | GI | B | Brooklyn Team | 12.396 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 32.73%
B097-196 | CECIL F. SLEDGE PLGD | 1997-03-31 | 1997-03-26 | 1996-04-09 | 350787 | 504000 | 1997-07-28 | 1998-01-23 | 1998-07-08 | GI | B | Brooklyn Team | 12.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 43.68%
B100-106M | SETH LOW PLGD | 2006-02-15 | 2006-03-17 | 2005-09-14 | 1260980 | 1600000 | 2006-09-25 | 2007-09-24 | 2007-09-24 | FI | B | Brooklyn Team | 14.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.89%
B102-104M/404M | CRISPUS ATTUCKS PARK - C.S. & ROOF REPLACEMENT | 2003-12-31 | 2004-03-30 | 2003-09-15 | 478049 | 919000 | 2005-01-31 | 2005-10-17 | 2006-09-28 | FI | B | Brooklyn Team | 13.0775 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | 92.24%
B102-204M | (ELECTRICAL) CRISPUS ATTUCKS PARK - C.S. & ROOF REPLACEMENT | 2003-12-31 | 2004-03-30 | 2003-09-15 | 58905.6 | 59000 | 2005-01-31 | 2005-10-17 | 2006-05-03 | GI | B | Brooklyn Team | 10.9837 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0.1603%
B102-304M | (PLUMBING) CRISPUS ATTUCKS PARK - C.S. & ROOF REPLACEMENT | 2003-12-31 | 2004-03-30 | 2003-09-15 | 32854 | 33000 | 2005-01-31 | 2005-10-17 | 2006-05-03 | GI | B | Brooklyn Team | 10.3998 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0.4444%
B102-404M | (H&V) CRISPUS ATTUCKS PARK - C.S. & ROOF REPLACEMENT | 2003-12-31 | 2004-03-30 | 2003-09-15 | 58469 | 59000 | 2005-01-31 | 2005-10-17 | 2006-09-28 | FI | B | Brooklyn Team | 10.9763 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | 0.9082%
B107-197 | LION'S PRIDE (RIVERDALE & SNEDIKER) PLAYGROUND | 1998-03-31 | 1998-04-14 | 1996-08-05 | 584805 | 705000 | 1998-08-31 | 1999-03-28 | 1999-04-30 | GI | B | Brooklyn Team | 13.279 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 20.55%
B110-101M | MARION ST EAST OF HOPKINSON AVE PLAYGROUND RECONSTR. | 2001-09-30 | 2001-12-11 | 2000-10-05 | 656000 | 1093000 | 2002-07-29 | 2003-02-23 | 2004-05-06 | GI | B | Brooklyn Team | 13.3939 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 66.62%
B110-104M | MARION ST. EAST OF HOPKINSON AVE PLGD - PORTION OF | 2003-03-31 | 2004-07-31 | 2003-09-22 | 568842.64 | 910000 | 2005-05-16 | 2006-02-09 | 2006-06-23 | GI | B | Brooklyn Team | 13.2514 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 59.97%
B111-103M | J.J. BYRNE PARK - THREE BASKETBALL CTS & MISC. SITE WORK | 2003-01-07 | 2003-03-31 | 2001-11-01 | 406664 | 681000 | 2004-04-05 | 2004-10-01 | 2004-12-09 | GI | B | Brooklyn Team | 12.9157 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 67.46%
B113-100M | COLUMBUS PARK - BOROUGH HALL - EXTERIOR ARCHITECTURAL LIGHTING | 1999-12-30 | 2000-03-08 | 1999-08-23 | 175651 | 336000 | 2001-04-02 | 2001-09-28 | 2002-01-11 | GI | B | Brooklyn Team | 12.0763 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 91.29%
B113-105M | CADMAN PLAZA (DOWNTOWN BKLYN CIVIC CTR) MASTER PLAN & PARTIAL RECONSTR | 2005-06-15 | 2005-07-28 | 2005-03-14 | 2441660.05 | 2926000 | 2006-03-27 | 2007-03-26 | 2006-12-28 | GI | B | Brooklyn Team | 14.7082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88 | 19.84%
B113-197 | PORTION OF COLUMBUS PARK | 1996-09-30 | 1996-09-30 | 1996-07-09 | 925000 | 1214000 | 1997-04-01 | 1997-12-26 | 1998-04-10 | GI | B | Brooklyn Team | 13.7375 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 31.24%
B113-598 | BROOKLYN WAR MEMORIAL - ROOF | 1998-03-31 | 1998-03-03 | 1998-01-21 | 75424 | 109000 | 1998-08-01 | 1998-11-28 | 1998-11-25 | GI | B | Brooklyn Team | 11.2309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 44.52%
B114-100M | MCGOLRICK PARK - LANDSCAPING & DRAINAGE | 2000-02-28 | 2000-03-11 | 1999-09-27 | 432143 | 608000 | 2000-08-14 | 2000-12-11 | 2000-12-11 | GI | CPM | Construction Project Manager | 12.9765 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.69%
B114-101M/301M | MCGOLRICK PARK - SHELTER PAVILION | 2001-02-01 | 2001-04-11 | 2000-08-30 | 445545 | 958000 | 2001-09-15 | 2002-06-11 | 2004-05-04 | GI | CPM | Construction Project Manager | 13.0071 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 115%
B114-201M | (ELECTRICAL) MCGOLRICK PARK - SHELTER PAVILION | 2001-02-01 | 2001-04-11 | 2000-08-30 | 66500 | 67000 | 2001-09-15 | 2002-06-11 | 2004-05-04 | GI | CPM | Construction Project Manager | 11.105 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0.7519%
B114-301M | (PLUMBING) MCGOLRICK PARK - SHELTER PAVILION | 2001-02-01 | 2001-04-11 | 2000-08-30 | 39000 | 39000 | 2001-09-15 | 2002-06-11 | 2004-05-04 | FI | CPM | Construction Project Manager | 10.5713 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 0%
B121-100M | SULLIVAN (DODGER) PLAYGROUND | 2000-03-22 | 2000-03-31 | 1999-08-09 | 656144 | 828000 | 2000-09-25 | 2001-03-23 | 2001-11-02 | GI | B | Brooklyn Team | 13.3941 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 26.19%
B124-198/498 | WM. SHERIDAN (DE DIEGO - PS 84) PLGD. & C.S. | 1997-09-24 | 1998-08-06 | 1996-10-18 | 700901 | 1032000 | 1999-02-08 | 1999-11-04 | 2000-04-20 | GI | CPM | Construction Project Manager | 13.4601 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 47.24%
B124-298 | (ELECTRICAL) WM. SHERIDAN (DE DIEGO-PS 84) PLGD & C.S. | 1997-09-24 | 1998-08-06 | 1996-10-18 | 27456 | 33000 | 1999-02-08 | 1999-11-04 | 2000-04-20 | GI | CPM | Construction Project Manager | 10.2203 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 20.19%
B124-398 | (PLUMBING) WM. SHERIDAN (DE DIEGO-PS 84) PLGD & C.S. | 1997-09-24 | 1998-08-06 | 1996-10-18 | 35100 | 35000 | 1999-02-08 | 1999-11-04 | 2000-04-20 | GI | CPM | Construction Project Manager | 10.466 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | -0.2849%
B124-498 | (H&V) WM. SHERIDAN (DE DIEGO-PS 84) PLGD & C.S. | 1997-09-24 | 1998-08-06 | 1996-10-18 | 33263 | 33000 | 1999-02-08 | 1999-11-04 | 2000-04-20 | GI | CPM | Construction Project Manager | 10.4122 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | -0.7907%
B125-198/498 | DREIER-OFFERMAN (CALVERT/VAUX) PLGD & COMFORT STATION | 1998-06-30 | 1999-04-05 | 1997-10-01 | 1267982 | 1880000 | 1999-08-11 | 2000-08-09 | 2000-11-21 | GI | CPM | Construction Project Manager | 14.0529 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 48.27%
B125-298 | (ELECTRICAL) DREIER-OFFERMAN PLGD & C.S. | 1998-06-30 | 1999-04-05 | 1997-10-01 | 26000 | 26000 | 1999-08-11 | 2000-08-09 | 2000-11-21 | GI | CPM | Construction Project Manager | 10.1659 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 0%
B125-398 | (PLUMBING) DREIER-OFFERMAN PLGD & C.S. | 1998-06-30 | 1999-04-06 | 1997-10-01 | 51000 | 51000 | 1999-08-11 | 2000-08-09 | 2000-11-21 | GI | CPM | Construction Project Manager | 10.8396 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 0%
B125-498 | (H&V) DREIER-OFFERMAN PLGD & C.S. | 1998-06-30 | 1999-04-06 | 1997-10-01 | 15142 | 15000 | 1999-08-11 | 2000-08-09 | 2000-11-21 | GI | CPM | Construction Project Manager | 9.6252 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | -0.9378%
B126-101M | RED HOOK REC. AREA - SOCCER FIELD @ CLINTON, BAY & COURT STS. | 2001-02-09 | 2001-03-26 | 2000-08-21 | 1135007 | 1516000 | 2001-11-05 | 2002-08-31 | 2002-12-19 | GI | CPM | Construction Project Manager | 13.9421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 33.57%
B126-196/496 | RED HOOK RECREATION AREA C.S. | 1996-03-31 | 1997-03-04 | 1995-09-25 | 519240 | 791000 | 1997-10-20 | 1998-08-15 | 1998-11-17 | GI | CPM | Construction Project Manager | 13.1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 52.34%
B126-296 | (ELECTRICAL) RED HOOK RECREATION AREA C.S. | 1996-03-31 | 1997-03-17 | 1995-09-25 | 31500 | 32000 | 1997-10-20 | 1998-08-15 | 1998-11-17 | GI | CPM | Construction Project Manager | 10.3577 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1.587%
B126-396 | (PLUMBING) RED HOOK RECREATION AREA C.S. | 1996-03-31 | 1996-04-02 | 1995-09-25 | 85888 | 88000 | 1997-10-20 | 1998-08-15 | 1998-11-17 | GI | CPM | Construction Project Manager | 11.3608 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 2.459%
B128-102M | COLONEL MARCUS PARK - PLGD @ AVE P BET OCEAN PKWY & 5TH ST | 2002-03-29 | 2002-11-04 | 2002-01-08 | 730512 | 984000 | 2003-06-12 | 2004-02-06 | 2004-05-04 | GI | B | Brooklyn Team | 13.5015 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 34.7%
B128-106M | COLONEL DAVID MARCUS MEM PLGD - BALLFIELDS | 2006-01-15 | 2006-05-24 | 2005-08-12 | 553325.75 | 739000 | 2007-06-18 | 2007-10-15 | 2007-09-06 | FI | B | Brooklyn Team | 13.2237 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39 | 33.56%
B129-103M | KAISER PARK - TRACK & FIELD | 2003-03-28 | 2004-08-24 | 2004-03-26 | 2544190 | 3217000 | 2005-01-24 | 2005-09-20 | 2005-12-12 | GI | B | Brooklyn Team | 14.7493 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 26.44%
B129-205M | KAISER PARK - CONSTR OF REC LIGHTING AT TRACK & FIELD | 2005-03-15 | 2006-03-09 | 2006-01-12 | 865642 | 1038000 | 2007-04-16 | 2007-10-12 | 2008-03-05 | FI | B | Brooklyn Team | 13.6712 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 19.91%
B132-199 | MCKIBBIN PARK @ MCKIBBIN & WHITE | 2000-01-21 | 2000-02-08 | 1998-10-26 | 1113534 | 1435000 | 2000-08-28 | 2001-08-27 | 2002-01-17 | GI | B | Brooklyn Team | 13.923 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 28.87%
B141-197A/497 | EAST NEW YORK VOC. H.S. - COMFORT STATION | 1997-03-31 | 1997-05-29 | 1996-08-14 | 302133 | 554000 | 1998-03-02 | 1999-03-01 | 2000-01-28 | GI | CPM | Construction Project Manager | 12.6186 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 83.36%
B141-199 | E.N.Y. VOCATIONAL H.S. PLGD - BASEBALL FIELD REC. LIGHTING | 1998-12-15 | 1999-02-08 | 1998-09-25 | 194000 | 326000 | 1999-09-16 | 2000-03-13 | 2000-04-04 | GI | B | Brooklyn Team | 12.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 68.04%
B141-297 | (ELECTRICAL) CONSTR OF COMFORT STATION @ E.N.Y. VOC. H.S. PLGD | 1997-03-31 | 1997-04-01 | 1996-08-14 | 16932 | 24000 | 1998-03-02 | 1999-03-01 | 2000-01-28 | GI | CPM | Construction Project Manager | 9.737 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 41.74%
B141-397 | (PLUMBING) CONSTR OF COMFORT STATION @ E.N.Y. VOC. H.S. PLGD | 1997-03-31 | 1997-04-01 | 1996-08-14 | 44000 | 44000 | 1998-03-02 | 1999-03-01 | 2000-01-28 | GI | CPM | Construction Project Manager | 10.6919 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 0%
B141-497 | (H&V) CONSTR OF COMFORT STATION @ E.N.Y. VOC. H.S. PLGD | 1997-03-31 | 1997-04-01 | 1996-08-14 | 12300 | 12000 | 1998-03-02 | 1999-03-01 | 2000-01-28 | GI | CPM | Construction Project Manager | 9.4174 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | -2.439%
B142-199 | BEDFORD PLAYGROUND | 1999-03-31 | 1999-04-20 | 1998-10-02 | 944387 | 1225000 | 1999-07-26 | 2000-03-21 | 2000-04-18 | GI | CPM | Construction Project Manager | 13.7583 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 29.71%
B147-198 | MSGR. CRAWFORD ATHLETIC FIELD | 1998-05-13 | 1999-04-06 | 1997-09-17 | 444801 | 586000 | 1999-09-06 | 2000-03-03 | 2000-02-24 | GI | CPM | Construction Project Manager | 13.0054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 31.74%
B148-197 | ROLF HENRY (MCKINNEY STEWARD) PLGD. | 1997-07-28 | 1998-04-13 | 1996-12-19 | 159113 | 245000 | 1998-09-14 | 1999-01-11 | 1999-02-08 | GI | CPM | Construction Project Manager | 11.9774 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 53.98%
B152-100M | BETTY K. RAPPAPORT PLGD | 2000-03-08 | 2000-03-20 | 1999-10-08 | 679995 | 881000 | 2001-01-15 | 2001-06-13 | 2001-06-22 | GI | CPM | Construction Project Manager | 13.4298 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 29.56%
B152-101M | BETTY K. RAPPAPORT PLGD - ROLLER HOCKEY RINK | 2001-03-30 | 2001-03-26 | 2000-10-23 | 653690 | 897000 | 2002-03-11 | 2002-09-06 | 2002-11-27 | GI | CPM | Construction Project Manager | 13.3904 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 37.22%
B153-100M | KINGSBOROUGH (PACIFIC) PLAYGROUND - PORTION OF | 2000-02-28 | 2000-03-12 | 1999-09-28 | 399856 | 603000 | 2000-08-22 | 2001-01-08 | 2001-02-21 | GI | CPM | Construction Project Manager | 12.8989 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 50.8%
B153-101M | SOUTH PACIFIC PLAYGROUND - EASTERN PORTION (SIDEWALKS, ETC.) | 2001-01-12 | 2001-01-29 | 2000-07-28 | 497735 | 658000 | 2001-09-04 | 2002-03-02 | 2002-03-01 | GI | CPM | Construction Project Manager | 13.1178 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 32.2%
B153-197 | KINGSBOROUGH (SOUTH PACIFIC) PLGD. | 1998-03-01 | 1998-03-24 | 1997-06-06 | 454500 | 619000 | 1998-09-14 | 1999-03-12 | 1999-06-02 | GI | CPM | Construction Project Manager | 13.027 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 36.19%
B154-199 | STRAWBERRY PLAYGROUND | 1999-08-30 | 1999-08-19 | 1999-01-05 | 421000 | 613000 | 2000-02-01 | 2000-07-29 | 2000-07-24 | GI | CPM | Construction Project Manager | 12.9504 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 45.61%
B159-101MD/301M | MT. PROSPECT PARK - COMFORT STATION | 2001-08-31 | 2001-09-30 | 2000-10-06 | 167356 | 556000 | 2004-02-02 | 2004-09-28 | 2004-09-23 | GI | B | Brooklyn Team | 12.0279 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 232.2%
B159-196 | MT. PROSPECT PARK - ASPHALT PATHS | 1996-06-06 | 1997-04-01 | 1995-10-11 | 743344 | 967000 | 1997-08-18 | 1998-04-24 | 1998-07-08 | GI | B | Brooklyn Team | 13.5189 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 30.09%
B159-201M | (ELECTRICAL) MT. PROSPECT PARK - COMFORT STATION | 2001-08-31 | 2001-09-30 | 2000-10-06 | 8320 | 9000 | 2002-07-15 | 2003-05-10 | 2004-09-23 | GI | B | Brooklyn Team | 9.0264 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502 | 8.173%
B159-301M | (PLUMBING) MT. PROSPECT PARK - COMFORT STATION | 2001-08-31 | 2001-09-30 | 2000-10-06 | 46995 | 47000 | 2002-07-15 | 2003-05-10 | 2004-10-04 | GI | B | Brooklyn Team | 10.7578 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0.01064%
B161-102MA2 | UNDERHILL PLAYGROUND | 2002-10-30 | 2003-06-10 | 2001-10-03 | 754073 | 1283000 | 2005-09-06 | 2006-06-02 | 2007-07-20 | FI | B | Brooklyn Team | 13.5332 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 70.14%
B164-199 | BATH BEACH PARK | 1999-03-23 | 1999-03-30 | 1998-11-04 | 463565 | 658000 | 1999-08-02 | 2000-01-28 | 2000-05-15 | GI | CPM | Construction Project Manager | 13.0467 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 41.94%
B166-105M | SHORE PARKWAY SEAWALL - EMERGENCY RECONSTR. |  | 2005-05-27 | 2005-05-17 | 11338315 | 20100000 | 2005-06-15 | 2006-04-10 | 2006-11-01 | GI | R;CR | Other | 16.2437 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 77.28%
B166-194/494 | JOSEPH T. MCGUIRE PARK - PARK HOUSE & BALLFIELD (BERGEN BEACH) | 2000-03-31 | 2000-02-24 | 1993-08-05 | 1977000 | 5416000 | 2000-09-18 | 2001-10-17 | 2002-10-03 | GI | B | Brooklyn Team | 14.4971 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 174%
B166-196 | SHORE PKWY BICYCLE PATHS - PA AVE TO WEST OF JFK | 2002-09-21 | 2005-10-01 | 2005-10-18 | 1473000 | 2585000 | 2007-04-02 | 2007-09-28 | 2007-10-03 | FI | B | Brooklyn Team | 14.2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 75.49%
B166-197 | JOS.T.MCGUIRE PK - TENNIS & VOLLEYBALL CTS. | 1997-09-07 | 1998-11-23 | 1996-08-01 | 749975 | 1142000 | 1999-05-10 | 1999-11-05 | 2000-01-21 | GI | CPM | Construction Project Manager | 13.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 52.27%
B166-199 | C.I. RECREATION AREA - 6 BALLFIELDS | 1999-03-31 | 1999-04-06 | 1998-12-11 | 686483 | 1050000 | 1999-09-01 | 2000-03-28 | 2000-04-07 | GI | CPM | Construction Project Manager | 13.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 52.95%
B166-294 | (ELECTRICAL) JOSEPH T. MCGUIRE PARK - PARK HOUSE | 2000-03-31 | 2000-02-25 | 1993-08-05 | 229000 | 329000 | 2000-09-18 | 2001-10-17 | 2002-10-03 | GI | B | Brooklyn Team | 12.3415 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 43.67%
B166-298 | BERGEN BEACH BALLFIELDS - FENCING | 1998-03-31 | 1998-02-04 | 1998-01-27 | 128771 | 200000 | 1998-04-08 | 1998-05-22 | 1998-07-02 | GI | R | Staten Island Team | 11.7658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 41 | 55.31%
B166-394 | (PLUMBING) JOSEPH T. MCGUIRE PARK - PARK HOUSE | 2000-03-31 | 2000-02-25 | 1993-08-05 | 136421 | 229000 | 2000-09-18 | 2001-10-17 | 2002-10-03 | GI | B | Brooklyn Team | 11.8235 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 67.86%
B166-494 | (HVAC) JOSEPH T. MCGUIRE PARK - PARK HOUSE | 2000-03-31 | 2000-02-25 | 1993-08-05 | 125000 | 165000 | 2000-09-18 | 2001-10-17 | 2002-10-03 | GI | B | Brooklyn Team | 11.7361 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 32%
B169-100MA | CONEY ISLAND BOARDWALK - RECONSTR BDWLK, RAILINGS, RAMPS ETC. | 2000-01-30 | 2001-03-05 | 1999-08-19 | 912130 | 1395000 | 2001-10-15 | 2002-10-14 | 2003-01-17 | FI | R | Staten Island Team | 13.7235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 95 | 52.94%
B169-105M | ABE STARK RINK - EMERGENCY RECONSTR OF ROOF |  | 2004-11-24 | 2004-09-03 | 575544 | 692000 | 2004-12-02 | 2005-01-10 | 2005-04-05 | GI | CR | Construction Resources | 13.2631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 20.23%
B169-195 | C.I.- BRIGHTON 2ND ST.PLGD. (HANDICAP ACCESS F/DISABLE) | 1996-12-31 | 1997-02-06 | 1994-09-23 | 832178 | 1043000 | 1997-07-07 | 1998-02-16 | 1998-06-15 | GI | R | Staten Island Team | 13.6318 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 119 | 25.33%
B169-305M | CONEY ISLAND - BOARDWALK LIGHTS | 2005-01-15 | 2005-04-05 | 2004-11-15 | 1053000 | 1582000 | 2006-04-17 | 2006-11-12 | 2007-03-15 | FI | R;B | Other | 13.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 50.24%
B173-103MA | FRASER SQUARE GREENSTREETS | 2003-02-28 | 2004-07-15 | 2003-03-05 | 486384.25 | 613000 | 2006-05-30 | 2007-02-23 | 2007-06-21 | FI | B | Brooklyn Team | 13.0948 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 26.03%
B184-102M | AVENUE R MALLS - B/T E. 7TH ST AND CONEY ISLAND AVENUE | 2001-12-01 | 2002-05-07 | 2001-09-12 | 262042 | 390000 | 2002-11-25 | 2003-05-23 | 2003-05-23 | GI | B | Brooklyn Team | 12.4763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.83%
B192-100M | FT. HAMILTON H.S. ATHLETIC FIELD (ADJ TO R.PEDERSON PLGD) | 2000-03-17 | 2000-02-21 | 1999-09-24 | 1417808 | 1788000 | 2000-08-30 | 2001-02-25 | 2001-10-26 | GI | CPM | Construction Project Manager | 14.1646 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 26.11%
B192-200M | RUSSELL PEDERSON PLGD | 2000-12-29 | 2001-02-12 | 2000-06-06 | 885158 | 1075000 | 2001-07-16 | 2002-05-11 | 2002-05-10 | GI | B | Brooklyn Team | 13.6935 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 21.45%
B193-104M | HAMILTON-METZ PLAYGROUND | 2003-12-15 | 2004-07-23 | 2003-03-18 | 1210585 | 1570000 | 2005-06-27 | 2005-12-23 | 2006-04-06 | GI | B | Brooklyn Team | 14.0066 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 29.69%
B194-198 | HARMONY (ARLINGTON) TRIANGLE | 1998-03-30 | 1998-04-13 | 1997-09-09 | 167867 | 339000 | 1998-08-17 | 1999-02-12 | 1999-04-02 | GI | B | Brooklyn Team | 12.0309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 101.9%
B200-197 | FULTON PARK EAST PLGD. | 1999-01-15 | 1999-01-19 | 1997-04-28 | 411795 | 583000 | 1999-06-28 | 1999-12-24 | 2000-02-17 | GI | B | Brooklyn Team | 12.9283 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 41.58%
B207-197 | EUGENE SARSFIELD PLGD. & COMFORT STATION | 1996-12-31 | 1997-02-12 | 1996-09-10 | 696577 | 975000 | 1997-06-16 | 1997-12-12 | 1998-01-27 | FI | CPM | Construction Project Manager | 13.4539 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 39.97%
B208-106M | PFC NORTON MEMORIAL PLAYGROUND | 2006-03-01 | 2006-03-15 | 2005-08-29 | 738383.06 | 800000 | 2006-10-02 | 2007-03-30 | 2007-06-21 | FI | B | Brooklyn Team | 13.5122 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 8.345%
B210-197 | THIRD AVE (JHS 136) PLGD & A BALLFIELD | 1997-08-13 | 1997-10-08 | 1997-05-28 | 538988 | 724000 | 1998-03-30 | 1998-09-25 | 1998-09-25 | GI | CPM | Construction Project Manager | 13.1974 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.33%
B212-198 | CAMPUS RD. TOT LOT & SITTING AREA | 1999-03-25 | 1999-04-05 | 1998-03-09 | 399000 | 532000 | 1999-08-17 | 2000-02-12 | 2000-04-21 | GI | CPM | Construction Project Manager | 12.8967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 33.33%
B214-103M | LINDEN (GERSHWIN/JHS 166) PARK - RUNNING TRACK & INFIELD, ETC. | 2003-05-01 | 2004-04-07 | 2003-07-09 | 2742081 | 3425000 | 2005-02-28 | 2005-11-24 | 2005-11-16 | GI | B | Brooklyn Team | 14.8242 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 24.91%
B216-102M | P.S. 44 (PUTNAM) PLAYGROUND | 2002-03-29 | 2003-04-11 | 2001-09-14 | 1098160 | 1776000 | 2004-03-22 | 2004-12-16 | 2005-08-11 | GI | B | Brooklyn Team | 13.9091 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 61.73%
B218-102M/402M | PAERDEGAT PARK - COMFORT STATION | 2002-01-15 | 2002-02-06 | 2001-10-12 | 148060 | 483000 | 2002-10-15 | 2003-04-12 | 2003-07-31 | GI | B | Brooklyn Team | 11.9054 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 226.2%
B218-198 | PAERDEGAT PARK | 1998-04-08 | 1998-04-14 | 1997-08-05 | 1100290 | 1471000 | 1998-11-03 | 1999-10-28 | 2000-03-24 | GI | CPM | Construction Project Manager | 13.9111 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 33.69%
B218-202M | (ELECTRICAL) PAERDEGAT PARK - COMFORT STATION | 2002-01-15 | 2002-02-06 | 2001-10-12 | 26000 | 26000 | 2002-10-15 | 2003-04-12 | 2003-07-31 | GI | B | Brooklyn Team | 10.1659 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0%
B218-302M | (PLUMBING) PAERDEGAT PARK - COMFORT STATION | 2002-01-15 | 2002-02-06 | 2001-10-12 | 60000 | 60000 | 2002-10-15 | 2003-04-12 | 2003-07-31 | GI | B | Brooklyn Team | 11.0021 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0%
B218-402M | (H&V) PAERDEGAT PARK - COMFORT STATION | 2002-01-15 | 2002-02-06 | 2001-10-12 | 17888 | 18000 | 2002-10-15 | 2003-04-12 | 2003-07-31 | GI | B | Brooklyn Team | 9.7919 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0.6261%
B221-197 | STEUBEN PLAYGROUND | 1998-01-15 | 1998-02-18 | 1997-06-05 | 710441 | 951000 | 1999-04-05 | 1999-10-31 | 2000-01-05 | GI | B | Brooklyn Team | 13.4736 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 33.86%
B223-100M | BROOKLYN HEIGHTS PROMENADE - COBBLESTONE & BENCHES | 2000-03-15 | 2000-03-06 | 1999-09-07 | 946566 | 1230000 | 2000-11-01 | 2001-06-28 | 2001-06-26 | GI | CPM | Construction Project Manager | 13.7606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 29.94%
B223-101M | RODNEY PLAYGROUND SOUTH RECONSTRUCTION | 2001-03-01 | 2001-02-22 | 2000-07-26 | 520172 | 692000 | 2001-07-09 | 2002-01-04 | 2002-07-05 | GI | B | Brooklyn Team | 13.1619 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 33.03%
B223-105M | DIMATTINA PARK - BALLFIELD LIGHTING | 2005-01-15 | 2005-03-23 | 2004-10-28 | 407156.4 | 654000 | 2006-03-20 | 2006-12-14 | 2007-02-26 | GI | B | Brooklyn Team | 12.917 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 60.63%
B223-196 | PENN STREET TRIANGLE | 1997-10-30 | 1997-11-18 | 1996-06-10 | 221622 | 303000 | 1998-06-01 | 1998-11-27 | 1998-11-30 | GI | B | Brooklyn Team | 12.3087 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 36.72%
B223-197 | BROOKLYN BRIDGE ANCHORAGE PLAZA - PORTION @ BASE OF BRIDGE | 1999-10-30 | 1999-11-06 | 1996-11-04 | 251059 | 416000 | 2000-10-02 | 2001-03-30 | 2001-05-15 | GI | B | Brooklyn Team | 12.4334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 65.7%
B223-199 | HARRY CHAPIN PARK | 2000-09-14 | 2000-10-17 | 1999-06-02 | 370342 | 644000 | 2001-06-18 | 2002-01-13 | 2002-08-12 | GI | B | Brooklyn Team | 12.8222 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 73.89%
B223-201M | DIMATTINA PARK - BASEBALL FIELD | 2001-02-02 | 2001-01-30 | 2000-08-17 | 587007 | 760000 | 2001-07-24 | 2001-12-20 | 2002-10-25 | GI | CPM | Construction Project Manager | 13.2828 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 29.47%
B223-295 | PALMETTO PARK (STATE ST.& ATLANTIC AVE. PLGD.) | 1998-04-01 | 1998-04-15 | 1995-04-18 | 785102 | 987000 | 1998-10-19 | 1999-10-18 | 1999-09-29 | GI | CPM | Construction Project Manager | 13.5736 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 25.72%
B223-299 | DIMATTINA PARK PLGD & DOG RUN | 1999-12-31 | 2000-02-07 | 1999-06-09 | 554219 | 808000 | 2000-08-14 | 2000-12-11 | 2001-05-18 | GI | CPM | Construction Project Manager | 13.2253 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 45.79%
B223-301M | BROOKLYN HEIGHTS PROMENADE - PORTION BET. PIERREPONT & ORANGE STS | 2001-03-30 | 2001-03-30 | 2000-10-23 | 1187875 | 1433000 | 2001-09-15 | 2002-05-12 | 2002-06-14 | GI | CPM | Construction Project Manager | 13.9877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 20.64%
B224-102M | P.O. RINALDO SALGADO (PS 309) PLGD - SYNTHETIC TURF BALLFIELD | 2002-08-30 | 2002-09-15 | 2002-04-30 | 736496 | 898000 | 2003-05-05 | 2003-10-31 | 2003-10-07 | GI | B | Brooklyn Team | 13.5097 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24 | 21.93%
B224-106M | P.S. 309 (SALGADO) PLGD - CONSTR OF BASKETBALL COURTS | 2006-02-01 | 2006-03-21 | 2005-11-14 | 222050.48 | 300000 | 2007-04-30 | 2007-08-27 | 2007-11-14 | FI | B | Brooklyn Team | 12.3107 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 35.1%
B224-197 | P.O. REINALDO SALGADO (P.S. 309) PLAYGROUND | 1997-11-30 | 1997-12-02 | 1996-08-27 | 792097 | 974000 | 1998-04-13 | 1998-10-09 | 1998-12-01 | GI | B | Brooklyn Team | 13.5824 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 22.96%
B234-197 | TILDEN PLAYGROUND | 1997-10-30 | 1997-10-31 | 1996-09-26 | 757233 | 894000 | 1998-04-30 | 1998-11-25 | 1998-10-08 | GI | B | Brooklyn Team | 13.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48 | 18.06%
B235-197 | HERMAN DOLGON PLGD. - PARTIAL RECONSTR. | 1998-03-02 | 1998-03-10 | 1997-06-24 | 405283 | 519000 | 1998-07-01 | 1998-11-27 | 1999-01-12 | GI | CPM | Construction Project Manager | 12.9123 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28.06%
B237-100M | JEFFERSON (P.S.3) PLGD. | 2000-02-22 | 2000-02-09 | 1999-08-17 | 781937 | 1018000 | 2000-07-31 | 2001-01-26 | 2001-07-24 | GI | B | Brooklyn Team | 13.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 30.19%
B239-100M | SHEEPSHEAD (PS 52) PLAYGROUND - SOUTHERN PORTION | 2000-10-30 | 2000-10-24 | 2000-05-22 | 491221 | 700000 | 2001-03-26 | 2001-09-21 | 2001-09-04 | GI | B | Brooklyn Team | 13.1046 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17 | 42.5%
B239-199 | P.S. 52 PLGD. (AVE Z) - PORTION OF | 1999-04-30 | 1999-04-22 | 1998-10-07 | 1026686 | 1401000 | 1999-11-01 | 2000-08-26 | 2000-09-19 | GI | B | Brooklyn Team | 13.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36.46%
B243-197 | ASHFORD PLAYGROUND | 1999-01-31 | 1999-03-18 | 1997-06-18 | 491472 | 649000 | 1999-08-30 | 2000-05-25 | 2000-07-14 | GI | B | Brooklyn Team | 13.1052 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 32.05%
B244-197 | MCDONALD PARK TENNIS COURTS | 1997-12-30 | 1998-01-29 | 1997-06-27 | 701131 | 894000 | 1998-06-01 | 1998-12-27 | 1998-12-11 | GI | B | Brooklyn Team | 13.4605 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 27.51%
B245-100MA | ST. JOHN'S RECREATION CTR. - MECHANICAL SYSTEMS | 2000-01-28 | 2000-02-10 | 1999-09-09 | 509966 | 761000 | 2000-11-20 | 2001-08-16 | 2002-08-23 | GI | B | Brooklyn Team | 13.1421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 49.23%
B245-104M/404M | ST. JOHN'S RECREATION CENTER | 2004-03-31 | 2004-02-28 | 2003-09-15 | 99860 | 716000 | 2005-02-07 | 2005-11-03 | 2006-01-20 | GI | B | Brooklyn Team | 11.5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 617%
B245-105MA | ADJACENT ST. JOHN'S RECREATION CENTER - PORTION OF PLAYGROUND | 2005-02-15 | 2005-07-28 | 2004-09-22 | 1135271 | 1290000 | 2006-06-12 | 2007-03-08 | 2007-07-31 | FI | B | Brooklyn Team | 13.9424 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 13.63%
B245-204M | (ELECTRICAL) ST. JOHN'S RECREATION CENTER | 2004-03-31 | 2004-04-07 | 2004-09-15 | 224619 | 225000 | 2005-02-07 | 2005-11-03 | 2005-10-31 | GI | B | Brooklyn Team | 12.3222 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 0.1696%
B246-195 | P.S. 273 (JEROME) PLGD | 1997-03-30 | 1997-04-02 | 1995-04-24 | 283288 | 366000 | 1997-08-25 | 1998-02-20 | 1998-06-18 | GI | B | Brooklyn Team | 12.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 29.2%
B247-100M | BREUKELEN (P.S.260) PLAYGROUND - BALLFIELDS | 2000-11-15 | 2001-04-06 | 2000-06-19 | 858193 | 1060000 | 2001-10-09 | 2002-04-06 | 2003-03-27 | GI | B | Brooklyn Team | 13.6626 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 23.52%
B248-100M | DAVID A. FOX (P.S. 251) PLAYGROUND | 2000-03-22 | 2000-03-31 | 1999-08-02 | 743170 | 904000 | 2000-10-16 | 2001-07-12 | 2001-09-25 | GI | B | Brooklyn Team | 13.5187 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 21.64%
B249-198 | VAN DYKE PLGD. - PORTION OF | 1998-12-15 | 1998-12-18 | 1998-04-03 | 348737 | 520000 | 1999-06-07 | 1999-12-03 | 1999-11-23 | GI | B | Brooklyn Team | 12.7621 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 49.11%
B251-100M/400M | MANHATTAN BEACH PARK - PARLATO PLGD COMFORT STATION | 2000-02-29 | 2000-03-21 | 1999-10-13 | 89856 | 350000 | 2000-10-10 | 2001-05-27 | 2001-07-02 | GI | R | Staten Island Team | 11.406 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 36 | 289.5%
B251-199 | MANHATTAN BEACH - TENNIS CTS @ ORIENTAL BLVD & MACKENZIE ST | 1999-03-31 | 1999-04-02 | 1998-08-11 | 501760 | 695000 | 1999-09-08 | 2000-02-04 | 2000-06-12 | GI | R | Staten Island Team | 13.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 129 | 38.51%
B251-200M | (ELECTRICAL) MANHATTAN BEACH PARK/PARLATTO PLGD - C.S. | 2000-02-29 | 2000-03-21 | 1999-10-13 | 9825 | 10000 | 2000-10-10 | 2001-05-27 | 2001-07-02 | GI | R | Staten Island Team | 9.1927 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 36 | 1.781%
B251-300M | (PLUMBING) MANHATTAN BEACH PARK/PARLATTO PLGD - C.S. | 2000-02-29 | 2000-03-21 | 1999-10-13 | 33911 | 34000 | 2000-10-10 | 2001-05-27 | 2001-07-02 | GI | R | Staten Island Team | 10.4315 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 36 | 0.2625%
B251-400M | (H&V) MANHATTAN BEACH PARK/PARLATTO PLGD - C.S. | 2000-02-29 | 2000-03-21 | 1999-10-13 | 14000 | 14000 | 2000-10-10 | 2001-05-27 | 2001-07-02 | GI | R | Staten Island Team | 9.5468 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 36 | 0%
B257-198 | FROST (COOPER HOUSES) PLGD | 1998-10-30 | 1998-11-19 | 1998-03-25 | 593605 | 739000 | 1999-04-12 | 1999-10-08 | 1999-11-23 | GI | B | Brooklyn Team | 13.294 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 24.49%
B266-196 | PORTIONS OF STAR SPANGLED (FRANCIS SCOTT KEY-I.S.117) PLGD. | 1996-10-31 | 1996-12-03 | 1996-05-28 | 643228 | 805000 | 1997-04-14 | 1997-12-14 | 1998-04-24 | GI | CPM | Construction Project Manager | 13.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 25.15%
B268-102M | NAUTILUS PLAYGROUND (CONEY ISLAND PLGD) @ W.29TH & W.32 STS. | 2002-03-29 | 2002-10-03 | 2001-09-14 | 858522 | 1229000 | 2003-06-30 | 2004-03-25 | 2004-09-16 | GI | R | Staten Island Team | 13.663 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 175 | 43.15%
B270-198 | BROWNSVILLE REC CTR - SECURITY LIGHTING & PORTIONS OF ROOF | 1997-07-30 | 1997-08-20 | 1997-05-20 | 621418 | 1060000 | 1998-01-15 | 1998-06-13 | 1998-08-11 | GI | CPM | Construction Project Manager | 13.3398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 70.58%
B270-298 | BROWNSVILLE REC CTR - HVAC EQUIP FOR ROOF | 1997-09-05 | 1997-09-09 | 1997-05-20 | 165360 | 265000 | 1998-01-15 | 1998-06-13 | 1998-06-12 | GI | CPM | Construction Project Manager | 12.0159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 60.26%
B270-398,599,699 | BROWNSVILLE REC CTR - HVAC EQUIPMENT F/GYM ROOF | 1998-11-15 | 1999-01-27 | 1998-05-05 | 114067 | 310000 | 1999-06-07 | 1999-11-03 | 2000-05-17 | GI | B | Brooklyn Team | 11.6445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 171.8%
B270-599 | BROWNSVILLE REC CTR - ELECTRICAL WORK F/HVAC SYSTEM | 1999-01-31 | 1999-01-27 | 1998-09-29 | 39745 | 47000 | 1999-06-07 | 1999-11-03 | 2000-05-17 | GI | B | Brooklyn Team | 10.5902 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 18.25%
B270-699 | BROWNSVILLE REC CTR - PORTION OF ROOF | 1999-01-15 | 1999-01-14 | 1998-11-04 | 123213 | 157000 | 1999-08-02 | 1999-12-29 | 2000-05-17 | GI | B | Brooklyn Team | 11.7217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 27.42%
B271-197 | DITMAS PLAYGROUND | 1997-11-30 | 1997-12-03 | 1997-05-01 | 792947 | 953000 | 1998-04-06 | 1998-11-01 | 1998-11-24 | GI | B | Brooklyn Team | 13.5835 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 20.18%
B285-103M | HARRY MAZE MEMORIAL PARK - PLGD AREA | 2003-02-28 | 2003-03-17 | 2002-09-12 | 713950 | 1008000 | 2004-03-22 | 2004-12-16 | 2005-05-19 | GI | B | Brooklyn Team | 13.4786 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 41.19%
B287-198 | ANDRIES (JHS 240-HUDDE) PLAYGROUND | 1998-03-22 | 1998-04-02 | 1997-11-03 | 493900 | 638000 | 1998-10-19 | 1999-03-17 | 1999-07-20 | GI | CPM | Construction Project Manager | 13.1101 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 29.18%
B291-196 | JAMES MARSHALL POWER PLGD. & ASPHALT BALLFIELD | 1996-11-30 | 1996-12-04 | 1995-08-17 | 769702 | 1003000 | 1997-03-10 | 1997-10-20 | 1998-01-28 | FI | CPM | Construction Project Manager | 13.5538 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 30.31%
B292-100M | PRATT PLAYGROUND | 2000-03-22 | 2000-03-31 | 1999-09-13 | 795940 | 963000 | 2001-04-16 | 2002-01-10 | 2002-05-21 | GI | B | Brooklyn Team | 13.5873 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 20.99%
B293-199 | P.S. 270 (CLASSON) PLAYGROUND - ASPHALT PLAYING FIELDS | 2000-01-30 | 2000-02-08 | 1999-05-03 | 560707 | 733000 | 2000-08-28 | 2001-02-23 | 2001-06-07 | GI | B | Brooklyn Team | 13.237 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 30.73%
B295-101M | PORTLAND/OXPORT (JHS 265) PLAYGROUND - PORTION OF | 2001-03-30 | 2001-03-30 | 2000-12-07 | 534332 | 800000 | 2001-08-01 | 2002-01-27 | 2001-12-24 | GI | CPM | Construction Project Manager | 13.1888 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34 | 49.72%
B295-196 | PORTLAND (JHS 265) PLAYGROUND | 1996-12-31 | 1997-01-16 | 1996-04-18 | 405845 | 541000 | 1997-06-30 | 1997-12-29 | 1998-04-29 | GI | B | Brooklyn Team | 12.9137 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 33.3%
B297-105MA | ALBEMARLE (ADJ TO PS 230) PLGD - PORTION OF | 2005-01-15 | 2005-04-06 | 2004-10-20 | 540472.4 | 808000 | 2006-07-24 | 2007-04-19 | 2007-07-19 | FI | B | Brooklyn Team | 13.2002 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 49.5%
B304-101M | KENNEDY KING (P.S. 219) PLAYGROUND | 2002-02-15 | 2002-03-11 | 2000-11-16 | 591223 | 722000 | 2003-03-17 | 2003-12-11 | 2004-04-28 | GI | B | Brooklyn Team | 13.2899 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 22.12%
B307-199 | TIGER (HALSEY -JHS 296) PLAYGROUND | 2000-01-22 | 2000-02-15 | 1998-12-07 | 497309 | 689000 | 2000-09-11 | 2001-02-07 | 2001-06-06 | GI | CPM | Construction Project Manager | 13.117 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 38.55%
B310-197 | BUSHWICK HOUSES PLGD | 1998-03-22 | 1998-03-30 | 1997-06-24 | 614816 | 756000 | 1998-09-09 | 1999-04-06 | 1999-06-21 | GI | CPM | Construction Project Manager | 13.3291 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 22.96%
B321-100MAT | RONALD EDMONDS (JHS 294) PLGD. - BASKETBALL CT & FENCING | 2001-12-31 | 2001-12-17 | 1999-07-20 | 233310 | 308000 | 2002-07-01 | 2003-01-16 | 2002-09-25 | GI | B | Brooklyn Team | 12.3601 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -113 | 32.01%
B323-101M | HATTIE CARTHAN (PS 305) PLAYGROUND - BALLFIELDS | 2001-03-31 | 2001-03-31 | 2000-08-09 | 377130 | 481000 | 2001-07-23 | 2001-11-19 | 2001-12-05 | GI | CPM | Construction Project Manager | 12.8403 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 27.54%
B323-199 | P.S. 305 (HATTIE CARTHAN) PLGD. | 1999-03-31 | 1999-03-31 | 1998-10-05 | 458235 | 653000 | 1999-08-30 | 2000-02-25 | 2000-03-28 | GI | B | Brooklyn Team | 13.0351 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 42.5%
B324-198 | JACOB JOFFE PARK BALLFIELDS | 1999-10-31 | 1999-12-08 | 1998-04-03 | 397304 | 550000 | 2000-05-22 | 2000-09-28 | 2000-09-28 | GI | B | Brooklyn Team | 12.8925 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.43%
B325-105MA | (JHS 271) FISH PLAYGROUND - BASKETBALL COURTS & MISC SITEWORK | 2005-02-15 | 2005-03-21 | 2004-09-20 | 657942 | 927000 | 2006-07-17 | 2006-12-13 | 2007-05-16 | FI | B | Brooklyn Team | 13.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 40.89%
B332-101M | EVERGREEN (PS 45) PLAYGROUND | 2001-03-04 | 2001-03-19 | 2000-10-12 | 754817 | 975000 | 2001-07-16 | 2002-03-12 | 2002-05-03 | GI | CPM | Construction Project Manager | 13.5342 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 29.17%
B334-199 | FERMI (IS 111) PLGD. | 2000-02-23 | 2000-02-27 | 1998-10-26 | 819001 | 1131000 | 2000-08-23 | 2001-02-18 | 2001-04-12 | GI | CPM | Construction Project Manager | 13.6158 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 38.1%
B337-198 | WEST BRIGHTON (CENTURY - PS 100) PLAYGROUND | 1998-11-30 | 1998-12-30 | 1997-09-08 | 501670 | 700000 | 1999-04-19 | 1999-10-15 | 1999-12-15 | GI | B | Brooklyn Team | 13.1257 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 39.53%
B347-101M | CARVER (P.S. 40) PLAYGROUND - RECONSTR. OF PORTION | 2001-03-30 | 2001-03-15 | 2000-10-03 | 387324 | 540000 | 2001-08-13 | 2002-01-09 | 2002-01-09 | GI | CPM | Construction Project Manager | 12.867 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.42%
B349-198 | BATH 24 (JHS 281) PLAYGROUND | 1998-03-04 | 1998-03-27 | 1997-08-11 | 262739 | 385000 | 1998-09-14 | 1999-01-11 | 1999-09-15 | GI | CPM | Construction Project Manager | 12.4789 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 46.53%
B352-102M/402M | SAM CURTIS PARK RECONST. & COMFORT STATION CONSTR. | 2002-07-04 | 2003-04-16 | 2001-10-04 | 2000389 | 2619000 | 2004-03-29 | 2005-03-23 | 2005-06-23 | FI | B | Brooklyn Team | 14.5089 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 30.92%
B352-202M | (ELECTRICAL) SAM CURTIS PARK & COMFORT STATION | 2002-07-04 | 2003-04-16 | 2001-10-04 | 14875 | 31000 | 2004-03-29 | 2005-03-23 | 2005-08-12 | FI | B | Brooklyn Team | 9.6074 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 108.4%
B352-302M | (PLUMBING) SAM CURTIS PARK & COMFORT STATION | 2002-07-04 | 2003-04-16 | 2001-10-04 | 64578 | 65000 | 2004-03-29 | 2005-03-23 | 2005-08-12 | FI | B | Brooklyn Team | 11.0756 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 0.6535%
B352-402M | (H&V) SAM CURTIS PARK & COMFORT STATION | 2002-07-04 | 2003-04-16 | 2001-10-04 | 35400 | 36000 | 2004-03-29 | 2005-03-23 | 2005-06-23 | FI | B | Brooklyn Team | 10.4745 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1.695%
B357-198A | JACKIE ROBINSON (IS 320) PLGD. | 1998-04-16 | 1998-09-10 | 1997-09-17 | 487856 | 656000 | 1999-02-22 | 1999-08-20 | 1999-10-06 | GI | CPM | Construction Project Manager | 13.0978 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 34.47%
B361-199 | JHS 6 - BOERUM PARK | 1999-11-22 | 1999-12-10 | 1999-06-09 | 871858 | 1150000 | 2000-07-03 | 2001-02-27 | 2001-08-31 | GI | B | Brooklyn Team | 13.6784 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 31.9%
B362-196 | P.S. 327 (CHESTER/OSBORN) PLGD. | 1996-02-28 | 1996-03-26 | 1995-08-04 | 1211130 | 1565000 | 1996-08-26 | 1997-06-01 | 1998-06-19 | GI | B | Brooklyn Team | 14.0071 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383 | 29.22%
B369-199 | STEEPLECHASE PARK - STABILIZATION OF PARACHUTE JUMP (EMERGENCY_ | 1999-03-23 | 1999-03-24 | 1999-03-22 | 24336 | 67000 | 1999-03-25 | 1999-04-24 | 1999-04-23 | GI | R | Staten Island Team | 10.0997 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 175.3%
B372-104M | FRIENDS FIELD PARK - PLGD | 2003-12-31 | 2003-12-31 | 2003-07-17 | 875254 | 1289000 | 2005-04-25 | 2006-01-19 | 2006-04-14 | FI | B | Brooklyn Team | 13.6823 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 47.27%
B372-106M | FRIENDS FIELD PARK - TENNIS COURTS | 2006-01-15 | 2006-02-17 | 2005-08-26 | 287915 | 474000 | 2006-10-10 | 2007-03-08 | 2007-07-17 | FI | B | Brooklyn Team | 12.5704 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 64.63%
B376-102MA1 | WYCKOFF HOUSE PARK - LANDSCAPING & IRRIGATION SYSTEM | 2002-07-30 | 2003-06-04 | 2001-12-11 | 393414 | 705000 | 2004-04-19 | 2005-01-13 | 2004-12-03 | GI | B | Brooklyn Team | 12.8826 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41 | 79.2%
B377-197 | FLOYD PATTERSON PARK BALLFIELDS | 1997-07-23 | 1997-09-16 | 1996-12-03 | 623836 | 885000 | 1998-03-05 | 1998-08-31 | 1998-11-16 | GI | CPM | Construction Project Manager | 13.3436 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 41.86%
B379-100M | BAYVIEW ECOLOGICAL REDEVELOPMENT | 2001-09-30 | 2001-11-26 | 2000-02-15 | 520361 | 718000 | 2003-02-24 | 2003-08-22 | 2006-06-29 | FI | R | Staten Island Team | 13.1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1042 | 37.98%
B382-196T | PORTIONS OF (JACOB'S LADDER) PARK @ CLYMER ST. | 1996-03-31 | 1998-02-09 | 1996-01-12 | 754000 | 1088000 | 1998-08-03 | 1999-04-29 | 1999-08-17 | GI | B | Brooklyn Team | 13.5331 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 44.3%
B385-102M | WNYC PIER - EMERGENCY DEMOLITION & REMOVAL OF TRAMSMITTER TOWERS | 2002-07-19 | 2002-07-01 | 2002-06-13 | 904074 | 1195000 | 2002-07-29 | 2002-11-25 | 2003-06-13 | GI | CPM | Construction Project Manager | 13.7147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 32.18%
B393-103M | SHEEPSHEAD BAY PIERS - ELECTRICAL SVCE & DISTRIB SYSTEM (EMERGENCY) |  | 2003-05-09 | 2003-04-30 | 800000 | 916000 | 2003-06-09 | 2003-11-05 | 2003-11-03 | GI | CR | Construction Resources | 13.5924 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 14.5%
B393-104M | SHEEPSHEAD BAY PIERS - CONSTR OF SECURITY GUARD BOOTH | 2004-10-15 | 2005-01-04 | 2004-12-10 | 149925 | 280000 | 2006-03-15 | 2006-08-11 | 2006-06-28 | FI | B;E | Other | 11.9179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | 86.76%
B393-105M | SHEEPSHEAD BAY PIERS - PERIMETER SIDEWALKS ALONG EMMONS AVE | 2005-02-15 | 2005-04-05 | 2004-12-29 | 819910 | 1554000 | 2006-03-27 | 2006-09-22 | 2006-06-28 | GI | B | Brooklyn Team | 13.6169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -86 | 89.53%
B394-100MA | FOUR SPARROW MARSH PRESERVE - SALT MARSH | 2001-01-26 | 2001-06-01 | 2000-05-04 | 604642 | 814000 | 2002-04-18 | 2002-10-14 | 2003-08-08 | GI | B | Brooklyn Team | 13.3124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298 | 34.63%
B395-196 | 1 BALLFIELD & SITTING AREA ON NOLL ST.BET.EVERGREEN & CENTRAL AV. | 1997-02-28 | 1997-03-17 | 1996-01-22 | 1389079 | 1922000 | 1997-07-28 | 1998-07-27 | 1999-04-30 | GI | B | Brooklyn Team | 14.1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 38.37%
B395-198 | GREEN CENTRAL KNOLL (BUSHWICK GREEN) PLGD | 1998-03-31 | 1998-04-09 | 1997-10-27 | 690617 | 953000 | 1998-08-17 | 1999-02-12 | 1999-08-23 | GI | B | Brooklyn Team | 13.4453 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 37.99%
B402-199 | VERONA (WYONA STREET - P.S.76) PLAYGROUND | 2000-02-19 | 2000-02-23 | 1998-11-05 | 974446 | 1268000 | 2000-09-18 | 2001-06-14 | 2001-09-06 | GI | CPM | Construction Project Manager | 13.7896 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 30.13%
B407-100MD | SO. OXFORD REC. CTR - DEMO OF TENNIS BLDG. ONLY | 2001-03-30 | 2001-04-20 | 1999-11-08 | 126568 | 150000 | 2001-09-24 | 2002-01-21 | 2002-02-28 | GI | B | Brooklyn Team | 11.7485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 18.51%
B407-104M | SOUTH OXFORD PARK - CONSTR OF PARK-INCL OPEN FIELD & TENNIS CT | 2004-11-15 | 2004-10-01 | 2003-09-26 | 1778878.25 | 2237000 | 2005-08-22 | 2006-08-16 | 2006-06-14 | GI | B | Brooklyn Team | 14.3915 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -63 | 25.75%
B418-101MA1 | LOUIS J. VALENTINO, JR. PARK & PIER 39 | 2002-02-28 | 2003-01-21 | 2000-07-19 | 477000 | 692000 | 2004-05-10 | 2004-11-05 | 2005-06-16 | FI | B | Brooklyn Team | 13.0753 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 45.07%
B429-101M | KNICKERBOCKER PARK - RECONSTRUCTION | 2001-08-30 | 2001-09-17 | 2001-09-12 | 363112 | 500000 | 2002-07-22 | 2003-01-17 | 2003-06-30 | GI | B | Brooklyn Team | 12.8025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 37.7%
B433-103MA | HENDRICK I. LOTT HOUSE | 2003-03-31 | 2004-08-30 | 2002-08-20 | 797563 | 1276000 | 2005-10-03 | 2006-10-02 | 2007-07-31 | FI | B | Brooklyn Team | 13.5893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 59.99%
BG-100M | BOILERS & HEATING SYSTEMS BOROWIDE | 1999-11-30 | 1999-12-29 | 1999-06-22 | 276600 | 277000 | 2000-07-31 | 2001-01-26 | 2001-12-05 | GI | B | Brooklyn Team | 12.5303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 0.1446%
BG-101M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-07-17 | 263488 | 291000 | 2001-03-12 | 2001-09-07 | 2001-08-23 | GI | T | Tree Unit | 12.4818 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -15 | 10.44%
BG-101MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-07-17 | 206955 | 228000 | 2002-03-18 | 2002-09-13 | 2002-06-28 | GI | T | Tree Unit | 12.2403 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -77 | 10.17%
BG-102M | BOILERS & HEATING SYSTEMS - 2 BROOKLYN SITES | 2001-12-05 | 2002-01-16 | 2001-07-13 | 162472 | 182000 | 2003-05-03 | 2004-01-27 | 2003-11-06 | GI | B;E | Other | 11.9983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82 | 12.02%
BG-103M | STREET TREE PLANTING - C.B. 1-9 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 453570 | 660000 | 2003-04-14 | 2003-10-10 | 2003-09-15 | GI | T | Tree Unit | 13.0249 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -25 | 45.51%
BG-103MR | STREET TREE PLANTING - C.B. 1-9 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 190000 | 120000 | 2004-04-12 | 2004-10-08 | 2004-09-01 | GI | T | Tree Unit | 12.1548 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -37 | -36.84%
BG-104M | STREET TREES - COMMUNITY BOARDS 10-18 | 2004-03-22 | 2004-03-22 | 2003-07-01 | 280297 | 352000 | 2004-11-01 | 2005-10-31 | 2005-07-28 | FI | T | Tree Unit | 12.5436 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -95 | 25.58%
BG-105M | P.E., S.S., HANDBALL CTS, BASKETBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 900000 | 1080000 | 2005-11-01 | 2006-10-31 | 2006-10-20 | FI | RCU | Requirements Contract Unit | 13.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -11 | 20%
BG-105MR | P.E., S.S., HANDBALL CTS, BASKETBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 900000 | 1080000 | 2006-09-05 | 2007-09-04 | 2007-07-12 | FI | RCU | Requirements Contract Unit | 13.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -54 | 20%
BG-106M | OCEAN PKWY MALLS AVE L AVE O (B065) & SARATOGA PK SDWLK (B079) | 2006-02-01 | 2006-03-13 | 2005-08-30 | 992223 | 1335000 | 2006-07-31 | 2007-01-26 | 2007-01-26 | FI | B | Brooklyn Team | 13.8077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.55%
BG-107M | STREETS TREES - CB 1-9 BROOKLYN |  | 2007-01-05 | 2006-09-14 | 389000 | 428000 | 2007-05-03 | 2007-10-29 | 2007-10-25 | FI | T | Tree Unit | 12.8713 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -4 | 10.03%
BG-1097 | PLAY EQUIP, SAFETY SURFACE, HANDBALL CTS, & GENERAL SITEWORK | 1997-01-31 | 1997-01-31 | 1996-12-23 | 597640 | 675000 | 1997-05-05 | 1998-05-04 | 1998-04-21 | GI | RCU | Requirements Contract Unit | 13.3007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -13 | 12.94%
BG-1099 | PLAY EQUIP, S.S.,HANDBALL CTS & SITE WORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-02-12 | 1999-03-10 | 1999-01-20 | 502565 | 697000 | 1999-06-07 | 2000-06-05 | 2000-09-28 | GI | RCU | Requirements Contract Unit | 13.1275 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 115 | 38.69%
BG-1197 | PLAY EQUIP,S.S., PAVEMTS, FENCES & GENERAL SITEWORK IN VARIOUS PARKS & PLGDS | 1997-04-15 | 1997-04-15 | 1997-03-10 | 701035 | 701000 | 1997-08-04 | 1998-01-30 | 1998-01-30 | FI | RCU | Requirements Contract Unit | 13.4603 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -0.004993%
BG-1198 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-26 | 1997-09-15 | 722038 | 840000 | 1998-05-26 | 1999-05-25 | 1999-04-22 | GI | RCU | Requirements Contract Unit | 13.4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -33 | 16.34%
BG-1198R | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1999-01-29 | 1999-02-11 | 1997-09-15 | 722038 | 836000 | 1999-05-17 | 2000-05-15 | 1999-12-20 | GI | RCU | Requirements Contract Unit | 13.4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -147 | 15.78%
BG-1205M | PERIMETER SIDEWALKS AT SUNSET PARK & AMERSFORT PARK | 2005-02-01 | 2005-04-13 | 2004-10-29 | 879730 | 1050000 | 2006-03-27 | 2006-09-22 | 2006-12-18 | FI | B | Brooklyn Team | 13.6874 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 19.35%
BG-1250-100M | HOLOCAUST MEMORIAL PARK - CONSTR. OF IRRIGATION SYSTEM | 1999-10-30 | 1999-11-19 | 1999-07-21 | 66477 | 201000 | 2000-05-02 | 2000-10-28 | 2000-12-05 | GI | B | Brooklyn Team | 11.1046 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 202.4%
BG-1298 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-26 | 1997-09-29 | 762583 | 958000 | 1998-06-18 | 1999-06-17 | 1999-07-07 | GI | RCU | Requirements Contract Unit | 13.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20 | 25.63%
BG-1299 | PLAY EQUIPMENT, S.S., HANDBALL CTS & SITE WORK | 1999-06-30 | 1999-06-09 | 1999-04-09 | 650224 | 875000 | 1999-11-15 | 2000-11-13 | 2001-05-25 | GI | RCU | Requirements Contract Unit | 13.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 193 | 34.57%
BG-1299R | PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 650224 | 846000 | 2000-11-08 | 2001-11-07 | 2002-02-12 | GI | RCU | Requirements Contract Unit | 13.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 97 | 30.11%
BG-1399 | PLAY EQUIPMENT, S.S., HANDBALL CTS & GENERAL SITE WORK | 1999-06-30 | 1999-06-09 | 1999-04-09 | 720000 | 940000 | 2000-01-15 | 2001-01-13 | 2001-06-28 | GI | RCU | Requirements Contract Unit | 13.487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 166 | 30.56%
BG-1399R | PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 684189 | 910000 | 2001-03-05 | 2002-03-04 | 2002-03-29 | GI | RCU | Requirements Contract Unit | 13.436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 25 | 33%
BG-1498 | STREET TREE PLANTING F.Y. 1998 - C.B. 1-9 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 265076 | 287000 | 1998-04-13 | 1999-04-12 | 1998-11-12 | GI | T | Tree Unit | 12.4878 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -151 | 8.271%
BG-1499 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL COURTS & SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 556000 | 711000 | 2000-01-03 | 2001-01-01 | 2001-05-03 | GI | RCU | Requirements Contract Unit | 13.2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 122 | 27.88%
BG-1499R | PLAY EQUIP, S.S., HANDBALL CTS & SITEWORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 556000 | 793000 | 2001-02-12 | 2002-02-11 | 2003-04-09 | GI | RCU | Requirements Contract Unit | 13.2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 422 | 42.63%
BG-1598 | STREET TREE PLANTING F.Y. 1998 - C.B. 10-18 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 262886 | 285000 | 1998-04-06 | 1999-04-05 | 1999-02-09 | GI | T | Tree Unit | 12.4795 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -55 | 8.412%
BG-1599 | SIDEWALKS, PAVEMENTS, LAWNS, GREENSTREETS & SITEWORK | 1999-06-30 | 1999-06-14 | 1999-04-09 | 492068 | 560000 | 1999-11-29 | 2000-11-27 | 2000-10-05 | GI | RCU | Requirements Contract Unit | 13.1064 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -53 | 13.81%
BG-1599R | SIDEWALKS, PAVEMENTS, LAWNS, GREENSTREETS & SITEWORK | 2000-03-28 | 2000-03-28 | 1999-04-09 | 492068 | 742000 | 2000-10-04 | 2001-10-03 | 2002-04-11 | FI | RCU | Requirements Contract Unit | 13.1064 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 190 | 50.79%
BG-1697 | FLOWERING STREET TREE PLANTING IN CB#1 GREENSTREET TRIANGLES | 1997-04-18 | 1997-04-22 | 1997-03-28 | 948850 | 1133000 | 1997-09-02 | 1999-02-23 | 1999-02-22 | GI | T | Tree Unit | 13.763 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 19.41%
BG-1698 | REMOVAL OF DEAD STREET TREES & STUMPS FY 1998 | 1998-01-31 | 1998-01-27 | 1998-01-05 | 198000 | 259000 | 1998-06-08 | 1998-08-16 | 1998-08-16 | FI | T | Tree Unit | 12.196 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 30.81%
BG-1699 | SIDEWALKS, PAVEMENTS, LAWNS, GREENSTREETS & SITE WORK | 1999-06-30 | 1999-06-22 | 1999-04-09 | 494500 | 567000 | 1999-11-29 | 2000-11-27 | 2000-10-05 | GI | RCU | Requirements Contract Unit | 13.1113 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -53 | 14.66%
BG-1699R | SIDEWALKS, PAVEMENTS, LAWNS GREENSTREETS & SITEWORK | 2000-03-28 | 2000-03-28 | 1999-04-09 | 494500 | 744000 | 2000-10-05 | 2001-10-04 | 2002-04-11 | FI | RCU | Requirements Contract Unit | 13.1113 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 189 | 50.46%
BG-1799 | RECONSTR. OF FENCES, GUIDERAILS, & GENERAL SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 336019 | 417000 | 1999-12-15 | 2000-09-09 | 2000-09-16 | GI | RCU | Requirements Contract Unit | 12.7249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 7 | 24.1%
BG-1799R | FENCES, GUIDERAILS, & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 336019 | 436000 | 2000-11-01 | 2001-07-28 | 2003-04-10 | GI | RCU | Requirements Contract Unit | 12.7249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 621 | 29.75%
BG-198 | STREET TREE PLANTING F/FY 1998 | 1997-08-28 | 1997-08-28 | 1997-07-03 | 393980 | 439000 | 1998-02-17 | 1999-02-16 | 1999-02-15 | GI | T | Tree Unit | 12.8841 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 11.43%
BG-199 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-23 | 1998-07-09 | 389800 | 430000 | 1999-02-16 | 2000-02-15 | 1999-08-16 | GI | T | Tree Unit | 12.8734 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -183 | 10.31%
BG-199R | STREET TREE PLANTING - F.Y. 2000 | 1999-08-23 | 1999-08-17 | 1998-07-09 | 389800 | 416000 | 1999-10-27 | 2000-10-25 | 2000-05-26 | GI | T | Tree Unit | 12.8734 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -152 | 6.721%
BG-201M | DE HOSTOS (I.S. 318) PLGD (B358) & PROJECT ROOTS (B423) | 2001-01-25 | 2001-02-07 | 2000-09-21 | 858639 | 1005000 | 2001-09-24 | 2002-06-20 | 2002-06-18 | GI | B | Brooklyn Team | 13.6631 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 17.05%
BG-203M | STREET TREE PLANTING - C.B. 10 - 18 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 386188 | 426000 | 2003-03-24 | 2003-09-19 | 2003-07-31 | GI | T | Tree Unit | 12.8641 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -50 | 10.31%
BG-203MR | STREET TREE PLANTING - CB 10-18 BROOKLYN | 2002-10-01 | 2002-10-18 | 2002-07-16 | 335000 | 335000 | 2004-04-12 | 2004-10-08 | 2004-09-20 | GI | T | Tree Unit | 12.7219 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -18 | 0%
BG-205M | P.E., S.S., & GENERAL SITEWORK |  | 2005-04-08 | 2004-07-30 | 600000 | 677000 | 2005-08-15 | 2006-08-14 | 2006-10-03 | FI | RCU | Requirements Contract Unit | 13.3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 50 | 12.83%
BG-205MR | P.E., S.S., & GENERAL SITEWORK |  | 2005-04-08 | 2004-07-30 | 600000 | 720000 | 2006-07-31 | 2007-07-30 | 2007-09-21 | FI | RCU | Requirements Contract Unit | 13.3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 53 | 20%
BG-206M | PLANTING OF NEW & REPLACEMENT ST. TREES, EXPANSION OF SIDEWALK TREE PITS & INSTALLATION OF TREE PIT GUARDS IN CB 1-9 |  | 2006-01-17 | 2005-11-25 | 834000 | 917000 | 2006-05-22 | 2007-05-21 | 2007-01-30 | FI | T | Tree Unit | 13.634 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -111 | 9.952%
BG-207M | STREET TREES - CB 10-18 BROOKLYN |  | 2007-01-05 | 2006-09-14 | 403000 | 448000 | 2007-04-16 | 2007-10-12 | 2007-09-29 | FI | T | Tree Unit | 12.9067 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -13 | 11.17%
BG-297 | PLANTING NEW & REPLACEMENT OF STREET TREES IN CB 1-18 | 1996-12-27 | 1997-02-24 | 1996-09-06 | 758100 | 890000 | 1997-06-16 | 1998-06-15 | 1998-06-12 | GI | T | Tree Unit | 13.5386 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -3 | 17.4%
BG-298 | STREET TREE PLANTING F/FY 1998 | 1997-08-28 | 1997-08-28 | 1997-07-03 | 441545 | 530000 | 1997-11-20 | 1998-11-19 | 1998-07-08 | GI | T | Tree Unit | 12.998 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -134 | 20.03%
BG-299 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-23 | 1998-07-09 | 347855 | 377000 | 1999-02-16 | 2000-02-15 | 1999-07-19 | GI | T | Tree Unit | 12.7595 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -211 | 8.378%
BG-299R | STREET TREE PLANTING - F.Y. 2000 | 1999-08-23 | 1999-08-17 | 1998-07-09 | 347855 | 407000 | 1999-10-28 | 2000-10-26 | 2000-05-25 | GI | T | Tree Unit | 12.7595 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -154 | 17%
BG-300M | PLAY EQUIP, S.S., PAVING, FENCING, LAWNS & SITE WORK | 1999-11-30 | 2000-02-01 | 1999-10-12 | 838379 | 990000 | 2000-07-31 | 2001-07-30 | 2001-12-21 | FI | RCU | Requirements Contract Unit | 13.6392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 144 | 18.09%
BG-301M | PAVEMENTS, HANDBALL CTS, LANDSCAPED AREAS & SITE WORK | 2001-04-30 | 2001-04-23 | 2001-04-18 | 700000 | 910000 | 2002-01-10 | 2003-01-09 | 2002-11-14 | GI | RCU | Requirements Contract Unit | 13.4588 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -56 | 30%
BG-301MR | PAVEMENTS, HANDBALL CTS, LANDSCAPED AREAS & SITE WORK | 2002-09-30 | 2002-09-30 | 2001-04-18 | 700000 | 840000 | 2003-04-16 | 2004-04-14 | 2004-09-17 | GI | RCU | Requirements Contract Unit | 13.4588 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 156 | 20%
BG-302M | STREET TREE PLANTING - CB 1-9 | 2002-06-30 | 2002-06-21 | 2002-04-23 | 516430 | 629000 | 2002-10-31 | 2003-07-27 | 2003-06-10 | GI | T | Tree Unit | 13.1547 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -47 | 21.8%
BG-303M | PLAY EQUIP, S.S., HANDBALL CTS, & GENERAL SITE WORK | 2002-11-30 | 2002-11-19 | 2002-07-15 | 650000 | 845000 | 2003-05-19 | 2004-05-17 | 2005-01-14 | GI | RCU | Requirements Contract Unit | 13.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 242 | 30%
BG-303MR | PLAY EQUIP, S.S., HANDBALL CTS, & GENERAL SITE WORK | 2002-11-30 | 2002-11-19 | 2002-07-15 | 400000 | 650000 | 2004-08-30 | 2005-08-29 | 2005-11-04 | GI | RCU | Requirements Contract Unit | 12.8992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 67 | 62.5%
BG-304M | PRATT, GREENWOOD, & ST. ANDREW'S PLGDS |  | 2003-12-31 | 2003-09-16 | 873100 | 1094000 | 2004-10-18 | 2005-07-14 | 2005-10-05 | GI | B | Brooklyn Team | 13.6798 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 25.3%
BG-305M | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 380000 | 426000 | 2005-08-09 | 2006-08-08 | 2006-05-12 | GI | RCU | Requirements Contract Unit | 12.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -88 | 12.11%
BG-305MR | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 380000 | 456000 | 2006-07-17 | 2007-07-16 | 2007-06-26 | FI | RCU | Requirements Contract Unit | 12.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -20 | 20%
BG-306M | PLANTING OF NEW & REPLACEMENT ST. TREES IN CB 10-18 BROOKLYN |  | 2006-01-11 | 2005-11-25 | 738000 | 812000 | 2006-10-02 | 2007-10-01 | 2007-10-01 | FI | T | Tree Unit | 13.5117 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10.03%
BG-37625-101M | BABI YAR TRIANGLE PARK RECONSTRUCTION | 2001-03-31 | 2001-03-28 | 2000-10-05 | 470889 | 597000 | 2001-07-05 | 2001-12-01 | 2001-12-21 | GI | B | Brooklyn Team | 13.0624 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26.78%
BG-37900-196 | GRAND FERRY PARK | 1996-10-31 | 1996-12-18 | 1995-09-05 | 299567 | 400000 | 1997-06-09 | 1997-10-26 | 1998-01-14 | GI | B | Brooklyn Team | 12.6101 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 33.53%
BG-38000-198 | BARBEY ST & SUTTER, SCHENCK, BELMONT AVES BALLFIELDS (2) | 1998-11-30 | 1998-12-02 | 1998-05-14 | 1060599 | 1700000 | 1999-08-12 | 2000-02-07 | 2000-05-12 | GI | CPM | Construction Project Manager | 13.8743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 60.29%
BG-38050-199 | SAINT MARKS AVE. STREETBED PARK | 2000-11-29 | 2001-02-15 | 1999-02-09 | 799483 | 928000 | 2001-10-15 | 2002-05-22 | 2003-01-24 | GI | B | Brooklyn Team | 13.5917 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 16.08%
BG-38150-101M | BROOKLYN BRIDGE PARK - PORTION OF (PHASE I) | 2001-03-30 | 2001-02-26 | 2000-08-01 | 5639171 | 6520000 | 2001-06-11 | 2002-06-05 | 2003-08-27 | GI | B | Brooklyn Team | 15.5452 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 15.62%
BG-38150-102M | BROOKLYN BRIDGE PARK - CONSTRUCTION OF A PORTION - PHASE 2 | 2001-12-15 | 2003-02-27 | 2001-07-10 | 2368837 | 3168000 | 2003-10-06 | 2004-10-04 | 2005-06-20 | GI | B | Brooklyn Team | 14.6779 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 33.74%
BG-397 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & SITEWORK | 1996-10-15 | 1996-11-04 | 1996-09-20 | 778572 | 857000 | 1997-03-24 | 1998-03-23 | 1998-07-10 | GI | RCU | Requirements Contract Unit | 13.5652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 109 | 10.07%
BG-398 | STREET & FLOWERING TREE PLANTING IN GREENSTREET TRIANGLES | 1997-09-08 | 1997-09-09 | 1997-07-10 | 246447 | 323000 | 1997-11-25 | 1998-08-21 | 1998-06-05 | GI | T | Tree Unit | 12.4149 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -77 | 31.06%
BG-399 | STREET TREE PLANTING - F.Y. 1999 - LONG HORNED BEETLE ZONE | 1999-01-29 | 1998-12-29 | 1998-11-02 | 989400 | 1058000 | 1999-05-14 | 2000-11-03 | 2000-11-14 | GI | T | Tree Unit | 13.8049 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 6.933%
BG-400MA | DYKER BEACH & MARINE PARK GOLF COURSES - IRRIGATION SYSTEMS | 1999-12-14 | 1999-12-20 | 1999-10-22 | 3941365 | 4643000 | 2000-10-16 | 2001-04-13 | 2002-06-13 | GI | CPM | Construction Project Manager | 15.187 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426 | 17.8%
BG-402M | STREET TREE PLANTING - CB 10-18 | 2002-06-30 | 2002-06-21 | 2002-04-23 | 371230 | 412000 | 2002-10-31 | 2003-07-27 | 2003-07-11 | GI | T | Tree Unit | 12.8246 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -16 | 10.98%
BG-402MR | STREET TREE PLANTING - CB 10-18 BROOKLYN | 2002-06-30 | 2002-06-21 | 2002-04-23 | 371230 | 450000 | 2003-10-20 | 2004-07-15 | 2004-07-15 | GI | T | Tree Unit | 12.8246 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 21.22%
BG-403M | PAVEMENTS, SIDEWALKS, HANDBALL CTS. & GENERAL SITE WORK | 2002-11-30 | 2002-10-29 | 2002-07-15 | 660000 | 660000 | 2003-05-12 | 2004-05-10 | 2004-11-16 | GI | RCU | Requirements Contract Unit | 13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 190 | 0%
BG-403MR | PAVEMENTS, SIDEWALKS, HANDBALL CTS. & GENERAL SITE WORK | 2002-11-30 | 2002-10-29 | 2002-07-15 | 436470 | 437000 | 2004-11-30 | 2005-11-29 | 2005-11-04 | GI | RCU | Requirements Contract Unit | 12.9865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -25 | 0.1214%
BG-404M | BOILERS & HEATING SYSTEMS - BROOKLYN (FY2003) |  | 2005-01-14 | 2003-09-29 | 233200 | 408000 | 2005-09-08 | 2006-06-04 | 2006-06-02 | FI | B;E | Other | 12.3597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 74.96%
BG-405M | PAVEMENTS, SIDEWALKS, WALLS, STEPS & GENERAL SITEWORK |  | 2005-04-01 | 2004-06-21 | 920000 | 1070000 | 2005-08-22 | 2006-08-21 | 2006-06-30 | GI | RCU | Requirements Contract Unit | 13.7321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -52 | 16.3%
BG-405MR | PAVEMENTS, SIDEWALKS, WALLS, STEPS & GENERAL SITEWORK |  | 2005-04-01 | 2004-06-21 | 920000 | 1104000 | 2006-07-31 | 2007-07-30 | 2007-06-27 | FI | RCU | Requirements Contract Unit | 13.7321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -33 | 20%
BG-406M | PLANTING OF NEW & REPLACEMENT ST. TREES, EXPANSION OF SIDEWALK TREE PITS & INSTALLATION OF TREE PIT GUARDS IN CB 10-18 |  | 2006-01-17 | 2005-11-25 | 834000 | 917000 | 2006-06-12 | 2007-06-11 | 2007-03-01 | FI | T | Tree Unit | 13.634 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -102 | 9.952%
BG-406MR | PLANTING OF NEW & REPLACEMENT ST. TREES, EXPANSION OF SIDEWALK TREE PITS & INSTALLATION OF TREE PIT GUARDS IN CB 10-18 |  | 2006-01-17 | 2005-11-25 | 850000 | 850000 | 2007-01-29 | 2008-01-28 | 2008-02-28 | FI | T | Tree Unit | 13.653 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 31 | 0%
BG-497 | RECONSTR.OF PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & SITEWORK | 1996-10-15 | 1996-11-07 | 1996-09-20 | 744700 | 819000 | 1997-03-17 | 1998-03-16 | 1998-07-01 | GI | RCU | Requirements Contract Unit | 13.5207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 107 | 9.977%
BG-499 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 437555 | 468000 | 1999-07-19 | 2000-07-17 | 2000-06-15 | GI | T | Tree Unit | 12.989 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -32 | 6.958%
BG-499R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 265000 | 265000 | 2000-03-13 | 2001-03-12 | 2001-02-22 | GI | T | Tree Unit | 12.4875 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -18 | 0%
BG-501M | PLAY EQUIP, S.S., HANDBALL CTS., BASEBALL DUGOUTS & SITE WORK | 2002-06-30 | 2002-10-31 | 2001-04-25 | 932000 | 986000 | 2003-05-19 | 2004-05-17 | 2005-03-08 | GI | RCU | Requirements Contract Unit | 13.7451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 295 | 5.794%
BG-503M | PLAY EQUIP, S.S., HANDBALL CTS & SITEWORK IN BKLYN |  | 2003-02-06 | 2002-10-22 | 740000 | 840000 | 2003-10-13 | 2004-10-11 | 2005-06-23 | FI | RCU | Requirements Contract Unit | 13.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 255 | 13.51%
BG-504M | FENCES, BENCHES, PLANTINGS & GENERAL SITE WORK |  | 2004-03-30 | 2003-10-29 | 648000 | 839000 | 2004-09-08 | 2005-09-07 | 2005-09-15 | FI | RCU | Requirements Contract Unit | 13.3816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 29.48%
BG-505M | STREET TREES - CB 1-9 BKLYN | 2004-08-05 | 2004-08-05 | 2004-07-06 | 446000 | 485000 | 2005-04-11 | 2005-10-07 | 2005-08-30 | FI | T | Tree Unit | 13.0081 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -38 | 8.744%
BG-505MR | STREET TREES - CB 1-9 BKLYN | 2004-08-05 | 2004-08-05 | 2004-07-06 | 357000 | 393000 | 2006-03-20 | 2006-09-15 | 2006-09-15 | FI | T | Tree Unit | 12.7855 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10.08%
BG-597 | SIDEWALKS, PATHS, PAVEMENTS, & GENERAL SITEWORK | 1996-11-30 | 1996-12-05 | 1996-09-20 | 495435 | 545000 | 1997-03-17 | 1998-03-16 | 1998-01-13 | FI | RCU | Requirements Contract Unit | 13.1132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -62 | 10%
BG-597R | RECONSTR. OF SIDEWALKS & PAVEMENTS - PHASE 2 RENEWAL | 1997-10-03 | 1997-10-06 | 1998-10-03 | 495435 | 595000 | 1998-02-16 | 1999-02-15 | 1999-02-15 | GI | RCU | Requirements Contract Unit | 13.1132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20.1%
BG-599 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 378780 | 405000 | 1999-09-07 | 2000-09-05 | 2000-09-01 | GI | T | Tree Unit | 12.8447 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -4 | 6.922%
BG-599R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 265000 | 318000 | 2000-04-03 | 2001-04-02 | 2001-02-12 | GI | T | Tree Unit | 12.4875 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -49 | 20%
BG-600M | STREET TREE PLANTING - FY 2001 | 2000-07-15 | 2000-07-13 | 2000-05-11 | 263520 | 291000 | 2000-11-08 | 2001-08-04 | 2001-03-20 | GI | T | Tree Unit | 12.4819 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -137 | 10.43%
BG-600MR | STREET TREE PLANTING - FY 2002 | 2001-07-31 | 2001-06-13 | 2000-05-11 | 206955 | 225000 | 2001-10-01 | 2002-06-27 | 2002-02-05 | GI | T | Tree Unit | 12.2403 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -142 | 8.719%
BG-601M | PLAY EQUIP, S.S. HANDBALL CTS. & GENERAL SITE WORK | 2001-08-31 | 2001-08-22 | 2001-04-25 | 740000 | 768000 | 2002-08-19 | 2003-08-18 | 2003-06-18 | FI | RCU | Requirements Contract Unit | 13.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -61 | 3.784%
BG-605M | STREET TREES - CB 10-18 BKLYN | 2004-08-05 | 2004-08-05 | 2004-07-06 | 462000 | 495000 | 2005-04-11 | 2005-10-07 | 2005-10-13 | GI | T | Tree Unit | 13.0433 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 7.143%
BG-605MR | STREET TREES - CB 10-18 BKLYN | 2004-08-05 | 2004-08-05 | 2004-07-06 | 563000 | 619000 | 2006-03-20 | 2006-09-15 | 2006-09-14 | FI | T | Tree Unit | 13.241 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 9.947%
BG-697 | SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1996-11-30 | 1996-12-05 | 1996-09-20 | 532610 | 586000 | 1997-03-31 | 1998-03-30 | 1998-05-29 | GI | RCU | Requirements Contract Unit | 13.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 60 | 10.02%
BG-699A1 | BOILERS & HEATINGS SYSTEMS IN BROOKLYN | 1999-10-15 | 1999-10-21 | 1998-07-13 | 523718 | 663000 | 2000-05-19 | 2000-11-14 | 2000-11-14 | GI | B | Brooklyn Team | 13.1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.59%
BG-700M | STREET TREE PLANTING - FY 2001 | 2000-07-15 | 2000-07-13 | 2000-05-11 | 263610 | 291000 | 2000-11-06 | 2001-08-02 | 2001-06-22 | GI | T | Tree Unit | 12.4822 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -41 | 10.39%
BG-700MR | STREET TREE PLANTING - FY 2002 | 2001-07-31 | 2001-06-13 | 2000-05-11 | 205955 | 225000 | 2001-10-15 | 2002-07-11 | 2002-01-24 | GI | T | Tree Unit | 12.2354 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -168 | 9.247%
BG-701M | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2001-06-30 | 2001-06-07 | 2001-04-25 | 500000 | 736000 | 2001-12-03 | 2002-08-29 | 2003-02-03 | GI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 158 | 47.2%
BG-701MR | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2002-09-30 | 2002-09-30 | 2001-04-25 | 500000 | 600000 | 2003-04-28 | 2004-01-22 | 2004-04-14 | GI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 83 | 20%
BG-704M | STREET TREES - CB 1-9 BKLYN |  | 2004-05-25 | 2004-03-24 | 363000 | 400000 | 2004-11-01 | 2005-07-28 | 2005-04-27 | GI | T | Tree Unit | 12.8022 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -92 | 10.19%
BG-704MR | STREET TREES - CB 1-9 BKLYN |  | 2005-07-20 | 2004-03-24 | 497000 | 547000 | 2005-10-17 | 2006-07-13 | 2006-01-17 | FI | T | Tree Unit | 13.1163 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -177 | 10.06%
BG-705MA | STREET TREES - CB 1-9 BKLYN | 2004-08-10 | 2004-08-10 | 2004-08-04 | 416000 | 500000 | 2005-04-11 | 2006-04-10 | 2005-09-15 | GI | T | Tree Unit | 12.9384 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -207 | 20.19%
BG-705MAR | STREET TREES - CB 1-9 BKLYN | 2004-08-10 | 2004-08-10 | 2004-08-04 | 416000 | 458000 | 2006-03-13 | 2007-03-12 | 2007-04-09 | FI | T | Tree Unit | 12.9384 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 28 | 10.1%
BG-706M | CB 1-9 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 330000 | 330000 | 2006-10-23 | 2007-07-19 | 2007-07-17 | FI | T | Tree Unit | 12.7068 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 0%
BG-797R | CHAIN LINK FENCES, GUIDERAILS, & STEEL FENCES - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 369339 | 443000 | 1998-01-19 | 1998-10-15 | 1999-01-13 | GI | RCU | Requirements Contract Unit | 12.8195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 90 | 19.94%
BG-799 | SIDEWALKS, PAVEMENTS, LAWNS & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-15 | 1999-03-12 | 1999-01-20 | 513000 | 634000 | 1999-06-28 | 2000-03-23 | 2000-04-21 | GI | RCU | Requirements Contract Unit | 13.148 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 29 | 23.59%
BG-799R | SIDEWALKS, PAVEMENTS, & GENERAL SITE WORK | 2000-03-31 | 2000-02-11 | 1999-01-20 | 450000 | 682000 | 2000-05-08 | 2001-02-01 | 2002-03-19 | FI | RCU | Requirements Contract Unit | 13.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 411 | 51.56%
BG-800M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-05-11 | 263455 | 291000 | 2001-03-12 | 2001-09-07 | 2001-08-30 | GI | T | Tree Unit | 12.4816 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -8 | 10.46%
BG-800MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-05-11 | 206955 | 228000 | 2002-03-18 | 2002-09-13 | 2002-06-27 | GI | T | Tree Unit | 12.2403 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -78 | 10.17%
BG-804M | STREET TREES - CB 10-18 BKLYN |  | 2004-05-25 | 2004-03-24 | 544000 | 488000 | 2004-10-25 | 2005-07-21 | 2005-07-21 | GI | T | Tree Unit | 13.2067 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -10.29%
BG-804MR | STREET TREES - CB 10-18 BKLYN |  | 2005-07-20 | 2004-03-24 | 400000 | 440000 | 2005-10-17 | 2006-07-13 | 2006-07-27 | FI | T | Tree Unit | 12.8992 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 14 | 10%
BG-805M | STREET TREES - CB 10-18 BKLYN | 2004-08-10 | 2004-08-10 | 2004-08-04 | 416000 | 500000 | 2005-04-25 | 2006-04-24 | 2005-08-23 | GI | T | Tree Unit | 12.9384 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -244 | 20.19%
BG-805MR | STREET TREES - CB 10-18 BKLYN | 2004-08-10 | 2004-08-10 | 2004-08-04 | 416000 | 458000 | 2006-02-09 | 2007-02-08 | 2006-07-13 | GI | T | Tree Unit | 12.9384 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -210 | 10.1%
BG-806M | CB 10-18 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 420000 | 420000 | 2006-10-23 | 2007-07-19 | 2007-07-17 | FI | T | Tree Unit | 12.948 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 0%
BG-898 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-23 | 1997-09-15 | 672210 | 840000 | 1998-05-29 | 1999-05-28 | 1999-04-23 | GI | RCU | Requirements Contract Unit | 13.4183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -35 | 24.96%
BG-898R | PLAY EQUIP, S.S.,HANDBALL CTS.,& SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-28 | 1997-09-15 | 672209 | 672000 | 1999-05-24 | 2000-05-22 | 2000-07-21 | GI | RCU | Requirements Contract Unit | 13.4183 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 60 | -0.03109%
BG-899 | FENCES, GUIDERAILS, & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-10 | 1999-01-20 | 358408 | 415000 | 1999-06-14 | 2000-03-09 | 2000-02-01 | GI | RCU | Requirements Contract Unit | 12.7894 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -37 | 15.79%
BG-900M | BOILERS & HEATING SYSTEMS @ MCCARREN, J.J. CARTY, LEIF ERICKSON C.S. | 2001-01-05 | 2001-02-06 | 2000-08-22 | 328812 | 406000 | 2001-07-16 | 2002-04-11 | 2002-07-30 | GI | CPM | Construction Project Manager | 12.7032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 23.47%
BG-997 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS & GENERAL SITEWORK | 1997-01-31 | 1997-01-27 | 1996-12-23 | 555935 | 750000 | 1997-04-28 | 1998-04-27 | 1998-04-23 | GI | RCU | Requirements Contract Unit | 13.2284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -4 | 34.91%
BG-998 | SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1998-03-31 | 1998-02-23 | 1997-09-15 | 511867 | 643000 | 1998-05-29 | 1999-05-28 | 1999-06-17 | GI | RCU | Requirements Contract Unit | 13.1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20 | 25.62%
BG-998R | SIDEWALKS, PATHS, PAVEMENTS & SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-11 | 1997-09-15 | 511867 | 643000 | 1999-05-24 | 2000-05-22 | 1999-09-28 | GI | RCU | Requirements Contract Unit | 13.1458 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -237 | 25.62%
BG-999D | PLAY EQUIPMENT, PAVEMENTS, FENCES AND GENERAL SITE WORK | 1999-02-15 | 1999-09-03 | 1999-01-06 | 732891 | 1093000 | 2000-02-28 | 2001-02-26 | 2001-10-05 | GI | RCU | Requirements Contract Unit | 13.5048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 221 | 49.14%
CNYG-1002M | CITYWIDE - COMFORT STATIONS & FACILITIES (HVAC) | 2001-12-31 | 2002-02-04 | 2001-12-04 | 150000 | 194000 | 2002-06-24 | 2003-06-23 | 2003-05-02 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -52 | 29.33%
CNYG-1002MR | CITYWIDE - COMFORT STATIONS & FACILITIES (HVAC) | 2001-12-31 | 2002-02-04 | 2001-12-04 | 150000 | 554000 | 2004-02-26 | 2005-02-24 | 2006-11-03 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 617 | 269.3%
CNYG-1003M | STREET TREE REMOVALS IN BKLYN, MANHATTAN, S.I. & THE BRONX - FY 2003 |  | 2003-03-18 | 2002-10-08 | 286649 | 270000 | 2003-11-03 | 2004-07-29 | 2004-08-06 | GI | T | Tree Unit | 12.566 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | -5.808%
CNYG-1004M | CITYWIDE - ASBESTOS REMOVAL & DISPOSAL | 2003-07-24 | 2003-08-07 | 2003-07-09 | 179583 | 272000 | 2004-06-29 | 2007-06-28 | 2004-11-05 | GI | EN | Environmental Control Unit | 12.0984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -965 | 51.46%
CNYG-100M | CITYWIDE - ASBESTOS ABATEMENT | 1999-07-19 | 1999-07-19 | 1999-06-29 | 87625 | 174000 | 1999-12-17 | 2002-12-15 | 2000-12-15 | GI | EN | Environmental Control Unit | 11.3808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -730 | 98.57%
CNYG-101M | ASBESTOS (ACM) REMOVAL & DISPOSALS | 2000-08-02 | 2000-08-02 | 2000-07-28 | 92550 | 395000 | 2001-04-02 | 2004-03-31 | 2001-10-22 | GI | EN | Environmental Control Unit | 11.4355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -891 | 326.8%
CNYG-102M | CITYWIDE - ASBESTOS REMOVAL & DISPOSAL | 2001-08-31 | 2001-08-14 | 2001-07-19 | 219825 | 685000 | 2002-01-28 | 2005-01-26 | 2002-11-04 | FI | EN | Environmental Control Unit | 12.3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -814 | 211.6%
CNYG-103MA | INDOOR AIR QUALITY TESTING | 2002-08-30 | 2003-03-24 | 2002-08-14 | 154600 | 155000 | 2003-08-11 | 2006-08-09 | 2006-10-10 | GI | EN | Environmental Control Unit | 11.9486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0.2587%
CNYG-1095 | CSU SVS. - SURVEY ACM @ VARIOUS CONSTRUCTION SITES | 1994-06-30 | 1994-08-09 | 1994-07-27 | 32050 | 32000 | 1995-03-13 | 1998-03-11 | 1998-03-12 | FI | AS | Other | 10.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -0.156%
CNYG-1097A | BUILT-UP FIBERGLASS SHINGLES & BITUMINOUS ROOFING CITYWIDE | 1998-02-28 | 1998-01-07 | 1997-01-08 | 1886690 | 2616000 | 1998-05-11 | 1999-05-10 | 1999-03-17 | GI | TS | Technical Services (Randalls Isl.) | 14.4503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -54 | 38.66%
CNYG-1097AR | BUILT-UP FIBERGLASS SHINGLES & BITUMINOUS ROOFING CITYWIDE | 1999-05-05 | 1999-05-05 | 1997-01-08 | 450000 | 1966000 | 1999-10-14 | 2000-10-12 | 2000-10-12 | GI | TS | Technical Services (Randalls Isl.) | 13.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 336.9%
CNYG-1099 | CITYWIDE - COMFORT STATIONS - ELEC. REQ. CONTRACT | 1999-02-08 | 1999-02-08 | 1998-07-27 | 150000 | 260000 | 2000-06-12 | 2001-06-11 | 2001-10-30 | GI | X | Bronx Team | 11.9184 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 73.33%
CNYG-1100M | POOL FACILITIES ELECTRICAL SYSTEMS IN THE BRONX & MANHATTAN | 1999-09-30 | 1999-10-04 | 1999-08-12 | 147530 | 215000 | 2000-03-31 | 2001-03-30 | 2001-03-22 | GI | TS | Technical Services (Randalls Isl.) | 11.9018 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -8 | 45.73%
CNYG-1100MR | POOL FACILITIES ELECTRICAL SYSTEMS IN THE BRONX & MANHATTAN | 1999-09-30 | 2001-01-04 | 1999-08-12 | 147531 | 215000 | 2001-04-09 | 2002-04-08 | 2002-04-22 | FI | TS | Technical Services (Randalls Isl.) | 11.9018 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14 | 45.73%
CNYG-1101M | IN-KIND PLUMBING SVS. F/POOLS IN MANHATTAN & THE BRONX | 2000-09-20 | 2001-03-23 | 2000-11-01 | 188410 | 234000 | 2001-07-23 | 2002-07-22 | 2002-09-13 | FI | TS | Technical Services (Randalls Isl.) | 12.1464 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 53 | 24.2%
CNYG-1102MA | 5 WELLS IN MANHATTAN, BRONX, S.I. & 2 LAKE LIFTS IN QUEENS & BRONX (EMERGENCY) | 2002-05-22 | 2002-06-03 | 2002-04-23 | 570000 | 1409000 | 2002-06-24 | 2002-08-23 | 2003-06-27 | GI | CR | Construction Resources | 13.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 147.2%
CNYG-1197 | SLATE, METAL & CEDAR SHAKE ROOFING CITY-WIDE | 1997-05-30 | 1997-06-02 | 1997-01-08 | 862400 | 1069000 | 1997-10-10 | 1998-10-09 | 1998-10-07 | GI | TS | Technical Services (Randalls Isl.) | 13.6675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -2 | 23.96%
CNYG-1198 | IN-KIND POOL FACILITIES ELECTRICAL SYSTEMS IN BRONX & MANHATTAN | 1998-01-31 | 1998-02-26 | 1997-10-29 | 100000 | 178000 | 1998-05-20 | 1998-11-15 | 1998-09-25 | FI | P | Other | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51 | 78%
CNYG-1198R | IN-KIND POOL FACILITIES ELECTRICAL SYSTEMS IN BRONX & MANHATTAN | 1999-01-07 | 1999-01-07 | 1997-10-29 | 100000 | 100000 | 1999-04-26 | 1999-10-22 | 1999-07-29 | FI | TS | Technical Services (Randalls Isl.) | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -85 | 0%
CNYG-1199 | CITYWIDE - COMFORT STATIONS - PLUMBING REQ. CONTRACT | 1999-09-13 | 1999-09-13 | 1998-07-27 | 150000 | 348000 | 2000-06-12 | 2001-06-11 | 2001-10-30 | GI | X | Bronx Team | 11.9184 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 132%
CNYG-1200M | POOL FACILITIES ELECTRICAL SYSTEMS IN BKLYN, QUEENS, S.I. | 1999-09-30 | 1999-10-04 | 1999-08-12 | 147558 | 296000 | 2000-03-28 | 2001-03-27 | 2001-03-20 | GI | TS | Technical Services (Randalls Isl.) | 11.902 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -7 | 100.6%
CNYG-1200MR | POOL FACILITIES ELECTRICAL SYSTEMS IN BKLYN, QUEENS, S.I. | 1999-09-30 | 2001-01-04 | 1999-08-12 | 147558 | 190000 | 2001-04-09 | 2002-04-08 | 2002-04-01 | FI | TS | Technical Services (Randalls Isl.) | 11.902 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -7 | 28.76%
CNYG-1202M | STREET & FLOWERING TREE PLANTING - CITYWIDE | 2002-07-31 | 2002-07-11 | 2002-04-30 | 396345 | 477000 | 2002-10-31 | 2003-07-27 | 2003-07-27 | GI | T | Tree Unit | 12.89 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 20.35%
CNYG-1202MR | STREET & FLOWERING TREE PLANTING - CITYWIDE | 2002-07-31 | 2002-07-11 | 2002-04-30 | 396345 | 437000 | 2003-10-20 | 2004-10-18 | 2004-05-13 | GI | T | Tree Unit | 12.89 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -158 | 10.26%
CNYG-1203M | CITYWIDE - BOARDWALKS | 2003-02-15 | 2003-03-14 | 2002-10-29 | 780000 | 930000 | 2003-09-15 | 2004-06-10 | 2006-06-22 | FI | R | Staten Island Team | 13.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 742 | 19.23%
CNYG-1298 | POOL FACILITIES ELECTRICAL SYSTEMS IN BKLYN, QNS, & S.I. | 1998-01-31 | 1998-02-26 | 1997-10-29 | 100000 | 169000 | 1998-05-11 | 1998-11-06 | 1998-11-06 | FI | P | Other | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69%
CNYG-1298R | POOL FACILITIES ELECTRICAL SYSTEMS IN BKLYN, QNS, & S.I. | 1999-01-31 | 1999-02-11 | 1997-10-29 | 100000 | 125000 | 1999-05-12 | 1999-11-07 | 1999-10-18 | FI | TS | Technical Services (Randalls Isl.) | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -20 | 25%
CNYG-1299A | CITYWIDE - COMFORT STATIONS - HVAC REQ. CONTRACT | 1999-09-30 | 1999-09-22 | 1998-07-27 | 150000 | 262000 | 2000-06-12 | 2001-06-11 | 2001-10-30 | GI | X | Bronx Team | 11.9184 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 74.67%
CNYG-1300MA | POOL FACILITIES PLUMBING SYSTEMS IN THE BRONX & MANHATTAN | 1999-09-30 | 2000-01-31 | 1999-08-12 | 202100 | 262000 | 2000-07-17 | 2001-07-16 | 2001-10-30 | GI | TS | Technical Services (Randalls Isl.) | 12.2165 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 106 | 29.64%
CNYG-1301MA | IN-KIND STRUCTUAL SVS. F/POOLS IN MANHATTAN & THE BRONX | 2000-09-20 | 2001-03-22 | 2000-11-01 | 189810 | 250000 | 2002-02-01 | 2003-01-31 | 2003-01-23 | FI | TS | Technical Services (Randalls Isl.) | 12.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -8 | 31.71%
CNYG-1302M | STREET & FLOWERING TREE PLANTING - BK & SI | 2002-10-01 | 2002-11-06 | 2002-09-05 | 250000 | 360000 | 2003-04-14 | 2004-04-12 | 2003-07-27 | GI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -260 | 44%
CNYG-1302MR | STREET & FLOWERING TREE PLANTING - BK & SI | 2002-10-01 | 2002-11-06 | 2002-09-05 | 250000 | 360000 | 2003-10-20 | 2004-10-18 | 2004-09-30 | GI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -18 | 44%
CNYG-1398 | POOL FACILITIES PLUMBING SYSTEMS IN BRONX & MANHATTAN | 1998-01-31 | 1998-02-26 | 1997-10-29 | 150000 | 191000 | 1998-05-18 | 1998-11-13 | 1999-02-02 | FI | P | Other | 11.9184 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 27.33%
CNYG-1398R | POOL FACILITIES PLUMBING SYSTEMS IN BRONX & MANHATTAN | 1999-01-31 | 1999-02-11 | 1997-10-29 | 150000 | 180000 | 1999-05-12 | 1999-11-07 | 1999-10-13 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -25 | 20%
CNYG-1401M | IN-KIND STRUCTUAL SVS. F/POOLS IN BKLYN, QUEENS & S.I. | 2000-09-20 | 2001-03-15 | 2000-11-01 | 177030 | 256000 | 2001-07-17 | 2002-07-16 | 2002-07-15 | FI | TS | Technical Services (Randalls Isl.) | 12.0841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -1 | 44.61%
CNYG-1402M | ASBESTOS CONTAINING MATERIALS - REMOVAL & DISPOSAL | 2002-08-30 | 2002-08-23 | 2002-08-19 | 192700 | 253000 | 2003-03-25 | 2006-03-23 | 2003-12-29 | GI | EN | Environmental Control Unit | 12.1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -815 | 31.29%
CNYG-1497 | CITYWIDE - SUBSURFACE INVESTIGATIONS | 1997-03-31 | 1997-04-04 | 1997-03-05 | 107335 | 150000 | 1997-10-15 | 1998-10-14 | 1998-10-14 | FI | S&E | Other | 11.5837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.75%
CNYG-1498 | POOL FACILITIES PLUMBING SYSTEMS IN BKLYN, QNS, & S.I. | 1998-01-31 | 1998-02-26 | 1997-10-29 | 150000 | 191000 | 1998-05-18 | 1998-11-13 | 1998-11-05 | FI | P | Other | 11.9184 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 27.33%
CNYG-1498R | POOL FACILITIES PLUMBING SYSTEMS IN BKLYN, QNS, & S.I. | 1999-01-07 | 1999-01-07 | 1997-10-29 | 150000 | 180000 | 1999-05-12 | 1999-11-07 | 1999-10-14 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -24 | 20%
CNYG-1500M | POOL FACILITIES STRUCTURAL SYSTEMS IN BRONX & MANHATTAN | 1999-09-30 | 1999-09-27 | 1999-08-12 | 154029 | 245000 | 2000-03-11 | 2001-03-10 | 2001-03-24 | FI | TS | Technical Services (Randalls Isl.) | 11.9449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14 | 59.06%
CNYG-1501M | CITYWIDE ROOFING | 2001-03-30 | 2001-03-29 | 2000-11-27 | 638000 | 3149000 | 2001-07-30 | 2002-07-29 | 2003-07-28 | FI | TS | Technical Services (Randalls Isl.) | 13.3661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 364 | 393.6%
CNYG-1501MR | CITYWIDE ROOFING | 2002-06-26 | 2002-06-26 | 2000-11-27 | 337000 | 3000000 | 2003-02-20 | 2004-02-19 | 2005-06-22 | FI | TS | Technical Services (Randalls Isl.) | 12.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 489 | 790.2%
CNYG-1503M | CITYWIDE - COMFORT STATIONS & BUILDING FACILITIES |  | 2003-02-27 | 2003-02-12 | 775000 | 1527620 | 2004-06-01 | 2005-05-31 | 2006-05-12 | FI | TS | Technical Services (Randalls Isl.) | 13.5606 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 346 | 97.11%
CNYG-1505M | STREET TREES - BROOKLYN, BRONX & STATEN ISLAND | 2004-08-06 | 2004-08-06 | 2004-07-06 | 314000 | 411000 | 2005-04-18 | 2006-04-17 | 2005-09-01 | FI | T | Tree Unit | 12.6571 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -228 | 30.89%
CNYG-1505MR | STREET TREES - BROOKLYN, BRONX & STATEN ISLAND | 2004-08-06 | 2004-08-06 | 2004-07-06 | 583000 | 583000 | 2006-05-08 | 2007-05-07 | 2007-04-03 | FI | T | Tree Unit | 13.2759 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -34 | 0%
CNYG-1598 | POOL FACILITIES STRUCTURAL SYSTEMS IN BRONX & MANHATTAN | 1998-01-31 | 1998-01-23 | 1997-10-29 | 226000 | 280000 | 1998-05-11 | 1998-11-06 | 1998-11-06 | FI | P | Other | 12.3283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.89%
CNYG-1598R | POOL FACILITIES STRUCTURAL SYSTEMS IN BRONX & MANHATTAN | 1999-01-07 | 1999-01-07 | 1997-10-29 | 226000 | 258000 | 1999-05-20 | 1999-11-15 | 1999-11-10 | FI | TS | Technical Services (Randalls Isl.) | 12.3283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -5 | 14.16%
CNYG-1599 | ASBESTOS REMOVAL & DISPOSAL CITYWIDE | 1998-09-30 | 1998-10-13 | 1998-08-13 | 205014 | 285000 | 1999-05-03 | 2002-05-01 | 2001-01-11 | GI | EN | Environmental Control Unit | 12.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -475 | 39.01%
CNYG-1600M | POOL FACILITIES STRUCTURAL SYSTEMS IN BKLYN, QUEENS, S.I. | 1999-09-30 | 1999-09-27 | 1999-08-12 | 159403 | 192000 | 2000-03-31 | 2001-03-30 | 2001-03-02 | FI | TS | Technical Services (Randalls Isl.) | 11.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -28 | 20.45%
CNYG-1601MA1 | CITYWIDE - IN-KIND SERVICES FOR MINI-POOLS | 2000-09-20 | 2001-10-19 | 2000-11-27 | 718446 | 929000 | 2002-07-15 | 2003-07-14 | 2003-07-11 | FI | TS | Technical Services (Randalls Isl.) | 13.4848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -3 | 29.31%
CNYG-1604MA | STREET TREES - CB4/BKLYN & CB5/QUEENS |  | 2004-07-22 | 2004-01-06 | 490000 | 587000 | 2004-11-01 | 2005-10-31 | 2005-08-25 | FI | T | Tree Unit | 13.1022 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -67 | 19.8%
CNYG-1605M | STREET TREES - MANHATTAN & QUEENS | 2004-08-06 | 2004-08-06 | 2004-07-06 | 313000 | 344000 | 2005-04-18 | 2006-04-17 | 2005-09-01 | FI | T | Tree Unit | 12.654 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -228 | 9.904%
CNYG-1698 | POOL FACILITIES STRUCTURAL SYSTEMS IN BKLYN, QNS, & S.I. | 1998-01-31 | 1998-02-26 | 1997-10-29 | 200000 | 254000 | 1998-05-20 | 1998-11-15 | 1999-01-15 | FI | P | Other | 12.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 27%
CNYG-1698R | POOL FACILITIES STRUCTURAL SYSTEMS IN BKLYN, QNS, & S.I. | 1999-01-31 | 1999-02-11 | 1997-10-29 | 200000 | 222000 | 1999-05-20 | 1999-11-15 | 1999-11-29 | FI | TS | Technical Services (Randalls Isl.) | 12.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 14 | 11%
CNYG-1699 | LEAD REMOVAL & DISPOSAL CITYWIDE | 1998-11-30 | 1998-11-13 | 1998-08-13 | 145700 | 239000 | 1999-07-27 | 2002-07-25 | 2000-08-29 | GI | AS | Other | 11.8893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -695 | 64.04%
CNYG-1700M | CELLULAR RADIOPHONES FOR FIELD ENGINEERS | 1999-10-26 | 1999-10-26 | 1999-10-26 | 96500 | 100000 | 2000-03-22 | 2001-03-21 | 2003-03-24 | FI | CR | Construction Resources | 11.4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 3.627%
CNYG-1701M | PLAY EQUIPMENT, S.S., FENCING, SITE WORK - BKLYN & S.I. | 2000-12-30 | 2001-01-18 | 2000-12-11 | 557126 | 725000 | 2001-06-06 | 2002-03-02 | 2002-04-24 | GI | RCU | Requirements Contract Unit | 13.2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 53 | 30.13%
CNYG-1704M | STREET TREES & FLOWERING TREES - MANHATTAN & QUEENS |  | 2004-07-28 | 2004-03-24 | 250000 | 375000 | 2004-10-25 | 2005-07-21 | 2005-06-06 | FI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -45 | 50%
CNYG-1705M | CITYWIDE - REMOVAL OF TIMBER PLAY EQUIPMT & RECONSTR OF P.E.,S.S., PAVEMENTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-30 | 2701000 | 3271000 | 2005-10-18 | 2007-04-18 | 2007-07-30 | FI | RCU | Requirements Contract Unit | 14.8091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 103 | 21.1%
CNYG-1706M | CITYWIDE - REMOVAL & DISPOSAL OF LEAD-CONTAINING MATERIALS @ DPR FACILITIES |  | 2005-12-14 | 2005-10-19 | 206450 | 206450 | 2006-10-30 | 2009-10-28 | 2007-02-09 | GI | EN | Environmental Control Unit | 12.2378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -992 | 0%
CNYG-1796 | BULK SAMPLING FOR ACM AIR MONITORING & REPORTING | 1996-08-21 | 1996-08-21 | 1996-07-15 | 62400 | 76000 | 1997-03-03 | 1999-03-02 | 1998-06-05 | FI | AS | Other | 11.0413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -270 | 21.79%
CNYG-1799 | CITYWIDE - SUBSURFACE INVESTIGATIONS | 1999-10-30 | 1999-10-21 | 1998-09-14 | 113865 | 252000 | 2000-08-01 | 2001-07-31 | 2001-08-29 | FI | EN | Environmental Control Unit | 11.6428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 121.3%
CNYG-1800M | STREET & FLOWERING TREES IN GREENSTREET TRIANGLES - MAN & BX | 1999-11-03 | 1999-11-03 | 1999-10-18 | 405075 | 478000 | 2000-04-05 | 2000-12-30 | 2000-07-25 | GI | T | Tree Unit | 12.9118 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -158 | 18%
CNYG-1800MR | STREET & FLOWERING TREES IN GREENSTREET TRIANGLES - MAN & BX | 2000-07-14 | 2000-07-14 | 1999-10-18 | 405075 | 447000 | 2000-10-16 | 2001-07-12 | 2001-06-28 | GI | T | Tree Unit | 12.9118 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -14 | 10.35%
CNYG-1801M | SUBSURFACE INVESTIGATION - CITYWIDE | 2001-06-30 | 2001-05-10 | 2001-03-02 | 211350 | 269000 | 2002-03-25 | 2003-03-24 | 2004-06-30 | GI | EN | Environmental Control Unit | 12.2613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 27.28%
CNYG-1803M | CITYWIDE - REMOVAL & DISPOSAL OF LEAD-CONTAINING MATERIALS |  | 2003-03-26 | 2003-03-12 | 134550 | 182780 | 2003-11-17 | 2006-11-15 | 2004-11-30 | GI | EN | Environmental Control Unit | 11.8097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -715 | 35.85%
CNYG-1804M | STREET TREES & FLOWERING TREES-BKLYN,BRONX & S.I. |  | 2004-06-10 | 2004-03-24 | 250000 | 275000 | 2004-10-25 | 2005-07-21 | 2005-03-21 | FI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -122 | 10%
CNYG-1804MR | STREET TREES & FLOWERING TREES - BKLYN, BRONX & S.I. |  | 2005-07-20 | 2004-03-24 | 250000 | 275000 | 2005-10-11 | 2006-07-07 | 2006-07-07 | FI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10%
CNYG-1805M | REMOVAL & DISPOSAL OF ASBESTOS - CITYWIDE |  | 2004-08-10 | 2004-07-26 | 177690 | 177690 | 2005-07-18 | 2008-07-16 | 2006-10-10 | GI | EN | Environmental Control Unit | 12.0878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -645 | 0%
CNYG-1897 | CITY WIDE PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & GENERAL SITEWORK | 1997-05-31 | 1997-05-23 | 1997-04-30 | 799845 | 1035000 | 1997-09-15 | 1998-09-14 | 1999-04-30 | GI | RCU | Requirements Contract Unit | 13.5922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 228 | 29.4%
CNYG-1899 | REMOVAL OF STUMPS FY99 IN BKLYN, MAN, S.I., BX. | 1998-11-15 | 1998-11-10 | 1998-10-28 | 265950 | 283000 | 1999-04-22 | 1999-09-18 | 1999-09-15 | GI | T | Tree Unit | 12.4911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -3 | 6.411%
CNYG-1899R | REMOVAL OF STUMPS FY2000 IN BKLYN, MAN, S.I., BX. | 1999-10-30 | 1999-10-27 | 1998-10-28 | 250000 | 300000 | 2000-03-27 | 2000-08-23 | 2000-11-13 | FI | T | Tree Unit | 12.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 82 | 20%
CNYG-1900M | STREET & FLOWERING TREES IN GREENSTREET TRIANGLES - BK & S.I | 1999-11-03 | 1999-11-03 | 1999-10-18 | 330653 | 395000 | 2000-09-18 | 2001-06-14 | 2001-06-06 | FI | T | Tree Unit | 12.7088 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -8 | 19.46%
CNYG-1901M | STREET TREE PLANTING IN GREENSTREET TRIANGLES - CITYWIDE | 2001-06-18 | 2001-06-18 | 2001-05-30 | 257156 | 334000 | 2002-04-11 | 2003-04-10 | 2003-04-10 | GI | T | Tree Unit | 12.4574 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 29.88%
CNYG-1904MA | SIDEWALKS DAMAGED BY ADJ CITY-OWNED TREES - BX & MANH | 2004-07-26 | 2004-07-26 | 2005-05-26 | 555000 | 610000 | 2006-02-01 | 2007-01-31 | 2007-06-04 | FI | T | Tree Unit | 13.2267 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 124 | 9.91%
CNYG-197 | RECONSTR. OF DETERIORATED, STORM & FIRE DAMAGED PORTIONS OF BOARDWALKS, WATERFRONT PROMENADES & GENERAL SITE WORK | 1997-02-28 | 1997-02-20 | 1996-10-01 | 625426 | 812000 | 1997-06-18 | 1998-03-14 | 1998-06-26 | GI | RCU | Requirements Contract Unit | 13.3462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 104 | 29.83%
CNYG-197R | DETERIORATED, STORM & FIRE DAMAGED BOARDWALKS, WATERFRONT PROMENADES, ETC. | 1997-02-28 | 1998-05-01 | 1996-10-01 | 639410 | 815000 | 1998-07-15 | 1999-04-10 | 1999-03-25 | GI | R | Staten Island Team | 13.3683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -16 | 27.46%
CNYG-198 | ACM BULK SAMPLING, MONITORING & REPORTING | 1997-10-15 | 1997-11-03 | 1997-07-29 | 73675 | 90000 | 1998-06-01 | 2000-05-30 | 2000-10-12 | GI | EN | Environmental Control Unit | 11.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 22.16%
CNYG-1996 | REMOVAL & DISPOSAL OF ACM IN BKLYN & S.I. | 1996-11-30 | 1996-11-29 | 1996-07-15 | 89812 | 107000 | 1997-08-22 | 1999-08-21 | 2000-06-07 | GI | AS | Other | 11.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 19.14%
CNYG-1997 | CITYWIDE PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & GENERAL SITEWORK | 1997-05-31 | 1997-05-23 | 1997-04-30 | 579895 | 685000 | 1997-09-15 | 1998-09-14 | 1998-07-22 | GI | RCU | Requirements Contract Unit | 13.2706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -54 | 18.12%
CNYG-1998 | STREET TREE PLANTING F/FY 1998 | 1998-01-30 | 1998-03-14 | 1998-11-28 | 743260 | 877000 | 1998-06-29 | 1999-06-28 | 1999-06-27 | GI | T | Tree Unit | 13.5188 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 17.99%
CNYG-1999 | REMOVAL OF DEAD STREET TREES - F.Y. 1999 | 1998-11-30 | 1998-11-13 | 1998-10-28 | 240856 | 268000 | 1999-03-29 | 1999-08-25 | 1999-10-28 | FI | T | Tree Unit | 12.392 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 64 | 11.27%
CNYG-2004M | SIDEWALKS DAMAGED BY ADJ CITY-OWNED TREES - BKLYN & S.I. | 2004-07-27 | 2004-07-27 | 2004-05-25 | 1054000 | 1159000 | 2005-06-06 | 2006-06-05 | 2006-10-12 | GI | T | Tree Unit | 13.8681 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 129 | 9.962%
CNYG-2005M | CITYWIDE - REMOVAL & DISPOSAL OF LEAD-CONTAINING MATERIALS |  | 2004-08-18 | 2004-08-10 | 126650 | 126650 | 2005-07-18 | 2008-07-16 | 2005-12-12 | GI | EN | Environmental Control Unit | 11.7492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -947 | 0%
CNYG-200M | LEAD REMOVAL & DISPOSAL CITYWIDE | 1999-07-19 | 1999-07-19 | 1999-07-07 | 57840 | 93000 | 2000-01-06 | 2003-01-04 | 2000-06-30 | GI | EN | Environmental Control Unit | 10.9654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -918 | 60.79%
CNYG-201M | CITYWIDE - BOARDWALKS | 2001-01-15 | 2001-01-17 | 2000-07-19 | 1620650 | 2225000 | 2001-05-07 | 2002-05-06 | 2002-11-14 | GI | R | Staten Island Team | 14.2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 192 | 37.29%
CNYG-205M | CITYWIDE - COMFORT STATIONS & FACILITIES |  | 2004-11-10 | 2004-07-01 | 1000000 | 1200000 | 2005-07-15 | 2006-07-14 | 2006-06-20 | FI | TS | Technical Services (Randalls Isl.) | 13.8155 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -24 | 20%
CNYG-207M | CITYWIDE - EMERGENCY RECONSTR & STABILIZATION OF RETAINING WALLS @ VARIOUS DPR FACILITIES |  | 2006-07-31 | 2006-07-21 | 635740 | 1120000 | 2006-08-17 | 2007-02-16 | 2007-06-12 | FI | E;CR | Other | 13.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 76.17%
CNYG-2099 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-15 | 1998-11-16 | 1998-10-28 | 383208 | 492000 | 1999-03-29 | 2000-03-27 | 2000-01-12 | GI | T | Tree Unit | 12.8563 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -75 | 28.39%
CNYG-2099R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-10-28 | 383208 | 500000 | 2000-08-07 | 2001-08-06 | 2001-07-05 | GI | T | Tree Unit | 12.8563 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -32 | 30.48%
CNYG-2101MA | IN-KIND - POOL ELECTRICAL SYSTEMS IN BRONX & MANHATTAN | 2001-07-31 | 2002-01-30 | 2001-06-13 | 100000 | 120000 | 2002-07-11 | 2003-07-10 | 2003-07-10 | FI | TS | Technical Services (Randalls Isl.) | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20%
CNYG-2106M | CITYWIDE - REMOVAL & DISPOSAL OF ASBESTOS-CONTAINING MATERIALS |  | 2006-01-31 | 2006-01-18 | 199350 | 329000 | 2007-04-02 | 2010-03-31 | 2007-10-25 | GI | EN | Environmental Control Unit | 12.2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -888 | 65.04%
CNYG-2197 | CITYWIDE SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1997-05-31 | 1997-05-23 | 1997-04-30 | 637594 | 847000 | 1997-09-10 | 1998-09-09 | 1998-09-08 | GI | RCU | Requirements Contract Unit | 13.3655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -1 | 32.84%
CNYG-2198 | DETERIORATED, STORM & FIRE DAMAGED BOARDWALKS, WATERFRONT PROMENADES ETC. | 1998-03-31 | 1998-02-26 | 1998-01-14 | 734785 | 882000 | 1998-05-20 | 1999-02-13 | 1999-01-19 | GI | RCU | Requirements Contract Unit | 13.5073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -25 | 20.04%
CNYG-2199 | PLAY EQUIPMENT, PAVEMENTS, FENCES & SITE WORK IN QUEENS & BROOKLYN | 1999-02-15 | 1999-03-10 | 1998-12-28 | 1121310 | 1618000 | 1999-08-02 | 2000-07-31 | 2000-08-31 | GI | RCU | Requirements Contract Unit | 13.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 31 | 44.3%
CNYG-2201MA | IN-KIND - POOL ELECTRICAL SYSTEMS IN BKLYN, QUEENS & S.I. | 2001-07-31 | 2002-01-30 | 2001-06-13 | 100000 | 130000 | 2002-07-15 | 2003-07-14 | 2003-07-14 | FI | TS | Technical Services (Randalls Isl.) | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30%
CNYG-2299 | PLAY EQUIPMENT, PAVEMENTS, FENCES AND GENERAL SITE WORK | 1999-02-15 | 1999-03-01 | 1999-01-06 | 603922 | 750000 | 1999-08-02 | 2000-07-31 | 2001-10-25 | GI | RCU | Requirements Contract Unit | 13.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 451 | 24.19%
CNYG-2398 | REMOVAL OF DEAD STREET TREES & STUMPS FY 1998 - BX,MAN,S.I. | 1998-01-31 | 1998-01-27 | 1998-01-05 | 280122 | 313000 | 1998-04-20 | 1998-06-28 | 1998-06-28 | FI | T | Tree Unit | 12.543 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 11.74%
CNYG-2399 | GREENSTREET TRIANGLES - FY 99 TREE PLANTING | 1999-03-31 | 1999-04-15 | 1999-03-16 | 336325 | 406000 | 1999-08-02 | 2000-07-31 | 2000-06-20 | GI | T | Tree Unit | 12.7258 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -41 | 20.72%
CNYG-2399R | GREENSTREET TRIANGLES - FY 01 TREE PLANTING | 2000-07-14 | 2000-07-14 | 1999-03-16 | 326425 | 358000 | 2000-10-23 | 2001-07-19 | 2001-04-17 | FI | T | Tree Unit | 12.696 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -93 | 9.673%
CNYG-2401MA | IN-KIND - POOL PLUMBING SYSTEMS IN THE BRONX & MANHATTAN | 2001-07-31 | 2002-01-30 | 2001-06-13 | 200000 | 260000 | 2002-06-17 | 2003-06-16 | 2003-06-16 | FI | TS | Technical Services (Randalls Isl.) | 12.2061 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30%
CNYG-2501M | IN-KIND - POOL PLUMBING SYSTEMS IN BKLYN, QUEENS & S.I. | 2001-07-31 | 2001-08-07 | 2001-06-13 | 200000 | 260000 | 2002-04-01 | 2003-03-31 | 2003-01-10 | FI | TS | Technical Services (Randalls Isl.) | 12.2061 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -80 | 30%
CNYG-2598 | PLAY EQUIPMENT, FENCES, PAVEMENTS & GENERAL SITEWORK | 1998-03-31 | 1998-03-18 | 1998-03-06 | 639000 | 700000 | 1998-07-13 | 1999-02-07 | 1999-06-08 | FI | RCU | Requirements Contract Unit | 13.3677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 121 | 9.546%
CNYG-2601MA | IN-KIND - POOL STRUCTUAL SYSTEMS IN THE BRONX & MANHATTAN | 2001-07-31 | 2002-01-30 | 2001-06-13 | 150000 | 195000 | 2002-06-17 | 2003-06-16 | 2003-04-24 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -53 | 30%
CNYG-2605M | DEAD TREES & STUMP REMOVALS - BKLYN, MANH, SI, BRONX | 2004-12-06 | 2004-12-06 | 2004-10-29 | 249975 | 275000 | 2005-05-16 | 2006-02-09 | 2005-09-27 | FI | T | Tree Unit | 12.4291 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -135 | 10.01%
CNYG-2605MR | DEAD TREES & STUMP REMOVALS - BKLYN, MANH, SI, BRONX | 2004-12-06 | 2004-12-06 | 2004-10-29 | 249975 | 275000 | 2006-01-24 | 2006-10-20 | 2006-08-02 | FI | T | Tree Unit | 12.4291 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -79 | 10.01%
CNYG-2698 | SPRAY SHOWERS & WADING POOLS @ ASTORIA, RED HOOK & LYONS POOLS | 1998-03-31 | 1998-04-24 | 1998-02-06 | 572537 | 718000 | 1998-07-17 | 1999-04-12 | 1999-07-20 | GI | TS | Technical Services (Randalls Isl.) | 13.2578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 99 | 25.41%
CNYG-2701M | IN-KIND - POOL STRUCTUAL SYSTEMS IN BKLYN, QUEENS & S.I. | 2001-07-31 | 2001-07-31 | 2001-06-13 | 150000 | 195000 | 2002-03-25 | 2003-03-24 | 2003-03-17 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -7 | 30%
CNYG-2798 | FENCING & PAVEMENTS @ LOCATIONS IN THE BRONX & MANHATTAN | 1998-03-27 | 1998-04-03 | 1998-02-09 | 634980 | 970000 | 1998-07-20 | 1999-01-15 | 1999-03-01 | GI | X;M | Other | 13.3613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 52.76%
CNYG-2798R | PAVEMENTS @ LOCATIONS IN THE BRONX | 1999-05-10 | 1999-05-10 | 1998-02-09 | 150000 | 150000 | 2000-04-24 | 2000-10-20 | 2000-09-13 | GI | X | Bronx Team | 11.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37 | 0%
CNYG-297 | STREET TREE PLANTING FY 97 (1125 TREES & PRUNING) | 1997-01-15 | 1997-02-24 | 1996-09-03 | 840000 | 1000000 | 1997-06-06 | 1998-06-05 | 1998-06-05 | GI | T | Tree Unit | 13.6412 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 19.05%
CNYG-298 | ACM REMOVAL & REPLACEMENT - THE BRONX & QUEENS | 1997-10-15 | 1997-10-09 | 1997-07-29 | 68570 | 100000 | 1998-02-02 | 2000-02-01 | 1999-01-27 | GI | AS | Other | 11.1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -370 | 45.84%
CNYG-299 | CITYWIDE ELECTRIC FEEDERS | 1998-11-12 | 1998-11-12 | 1998-06-30 | 95200 | 144000 | 2000-03-01 | 2001-02-28 | 2001-02-21 | GI | X | Bronx Team | 11.4637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 51.26%
CNYG-3005M | TREE PLANTINGS - MANHATTAN & QUEENS |  | 2005-07-14 | 2005-06-21 | 250000 | 275000 | 2005-10-24 | 2006-10-23 | 2006-10-23 | FI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10%
CNYG-3005MR | TREE PLANTINGS - MANHATTAN & QUEENS |  | 2005-07-14 | 2005-06-21 | 450000 | 450000 | 2006-10-30 | 2007-10-29 | 2007-10-27 | FI | T | Tree Unit | 13.017 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 0%
CNYG-300M | STREET TREE PLANTING FY 2000 - MANHATTAN & THE BRONX | 1999-07-28 | 1999-07-28 | 1999-10-18 | 373405 | 467000 | 2000-01-05 | 2000-09-30 | 2000-09-28 | GI | T | Tree Unit | 12.8304 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 25.07%
CNYG-300MR | STREET TREE PLANTING FY 2001 - MANHATTAN & THE BRONX | 2000-12-31 | 2000-12-11 | 1999-10-18 | 373430 | 406000 | 2001-04-16 | 2002-01-10 | 2002-01-09 | GI | T | Tree Unit | 12.8305 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 8.722%
CNYG-301M | STREET TREE REMOVALS - FY 2001 | 2000-10-15 | 2000-10-31 | 2000-07-17 | 249881 | 275000 | 2001-04-02 | 2001-12-27 | 2001-12-26 | FI | T | Tree Unit | 12.4287 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 10.05%
CNYG-303M | IN-KIND POOL FACILITIES ELECTRICAL SYSTEMS IN BRONX & MANHATTAN |  | 2003-02-12 | 2002-09-24 | 100000 | 130000 | 2003-07-15 | 2004-07-13 | 2004-09-15 | FI | TS | Technical Services (Randalls Isl.) | 11.5129 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 64 | 30%
CNYG-304M | COMFORT STATIONS & FACILITIES - CITYWIDE - ELECTRICAL WORK | 2003-09-30 | 2003-10-23 | 2003-07-02 | 100000 | 375000 | 2004-07-26 | 2005-07-25 | 2006-09-25 | FI | TS | Technical Services (Randalls Isl.) | 11.5129 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 427 | 275%
CNYG-305M | CITYWIDE - (ELECTRICAL SYS) COMFORT STATIONS & FACILITIES |  | 2004-09-17 | 2004-07-01 | 300000 | 675000 | 2005-06-21 | 2006-06-20 | 2006-12-27 | FI | TS | Technical Services (Randalls Isl.) | 12.6115 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 190 | 125%
CNYG-3098 | SUBSURFACE INVESTIGATIONS FOR FY 1998 | 1998-03-31 | 1998-03-06 | 1998-02-17 | 121647 | 220000 | 1998-12-07 | 1999-12-06 | 2000-05-31 | FI | EN | Environmental Control Unit | 11.7089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 80.85%
CNYG-3197 | BOARDWALKS CITYWIDE - DETERIORATED, STORM & FIRE DAMAGED | 1997-12-31 | 1998-02-26 | 1997-06-06 | 666367 | 830000 | 1998-08-06 | 1999-05-02 | 1999-01-19 | GI | RCU | Requirements Contract Unit | 13.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -103 | 24.56%
CNYG-3197R | BOARDWALKS CITYWIDE - DETERIORATED, STORM & FIRE DAMAGED | 1999-01-31 | 1999-01-31 | 1997-06-06 | 666367 | 720000 | 1999-04-08 | 2000-01-02 | 1999-12-22 | GI | R | Staten Island Team | 13.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -11 | 8.049%
CNYG-3398 | STREET & FLOWERING TREE PLANTING IN GREENSTREETS TRIANGLES | 1998-04-20 | 1998-04-20 | 1998-04-06 | 411725 | 500000 | 1998-08-10 | 1999-08-09 | 1999-08-09 | GI | T | Tree Unit | 12.9281 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 21.44%
CNYG-3498 | CITYWIDE FIBERGLASS SHINGLE & BITUMINOUS ROLL ROOFING | 1998-04-30 | 1998-05-06 | 1998-04-16 | 1962390 | 2619000 | 1999-02-09 | 2000-02-08 | 1999-09-02 | GI | TS | Technical Services (Randalls Isl.) | 14.4897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -159 | 33.46%
CNYG-3598 | CITYWIDE SLATE, METAL & CEDAR SHAKE ROOFING | 1998-04-30 | 1998-05-06 | 1998-04-16 | 946850 | 1280000 | 1998-11-09 | 1999-11-08 | 1999-06-16 | FI | TS | Technical Services (Randalls Isl.) | 13.7609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -145 | 35.19%
CNYG-3798 | ACM & LEAD BULK SAMPLING, AIR MONITORING & REPORTING | 1998-06-17 | 1998-06-17 | 1998-05-05 | 291650 | 212000 | 1998-11-30 | 2001-11-28 | 2001-11-28 | GI | EN | Environmental Control Unit | 12.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27.31%
CNYG-3800M | BROOKLYN & STATEN ISLAND FLAGPOLES (EMERGENCY) | 2000-07-30 | 2000-07-21 | 2000-04-20 | 657245 | 1152000 | 2000-08-28 | 2000-12-25 | 2000-12-24 | GI | CPM | Construction Project Manager | 13.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 75.28%
CNYG-3900M | CITYWIDE - LEAD REMOVAL | 2000-06-21 | 2000-06-21 | 2000-05-12 | 172035 | 292000 | 2001-03-06 | 2004-03-04 | 2001-11-13 | GI | EN | Environmental Control Unit | 12.0555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -842 | 69.73%
CNYG-398 | ACM REMOVAL & REPLACEMENT - MANHATTAN, BKLYN, & S.I. | 1997-10-15 | 1997-10-09 | 1997-07-29 | 98460 | 144000 | 1998-01-09 | 2000-01-08 | 1998-06-30 | FI | AS | Other | 11.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -557 | 46.25%
CNYG-4000M | CITYWIDE - ASBESTOS ABATEMENT | 2000-05-26 | 2000-05-26 | 2000-05-12 | 159000 | 263000 | 2000-12-01 | 2003-11-30 | 2001-10-22 | GI | EN | Environmental Control Unit | 11.9767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -769 | 65.41%
CNYG-400M | STREET TREE PLANTING FY 2000 - BKLYN & S.I. | 1999-07-29 | 1999-07-29 | 1999-10-18 | 409475 | 433000 | 2000-01-18 | 2000-10-13 | 2000-07-13 | GI | T | Tree Unit | 12.9226 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -92 | 5.745%
CNYG-400MR | STREET TREE PLANTING FY 2001 - BKLYN & S.I. | 2000-07-14 | 2000-07-14 |  | 409475 | 528000 | 2000-10-16 | 2001-07-12 | 2001-03-30 | GI | T | Tree Unit | 12.9226 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -104 | 28.95%
CNYG-401M | ASBESTOS (ACM) & LEAD BULK SAMPLING, MONITORING & REPORTING | 2000-08-02 | 2000-08-02 | 2000-07-28 | 166900 | 403000 | 2001-02-05 | 2004-02-04 | 2005-04-28 | GI | EN | Environmental Control Unit | 12.0252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 449 | 141.5%
CNYG-402M | CITYWIDE - COMFORT STATIONS & FACILITIES | 2001-10-15 | 2001-11-30 | 2001-09-13 | 1175000 | 1806000 | 2002-07-15 | 2003-07-14 | 2004-05-28 | FI | TS | Technical Services (Randalls Isl.) | 13.9768 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 319 | 53.7%
CNYG-404M | COMFORT STATIONS & FACILITIES - CITYWIDE - PLUMBING WORK | 2003-09-30 | 2003-10-22 | 2003-07-02 | 200000 | 240000 | 2004-07-26 | 2005-07-25 | 2005-04-26 | FI | TS | Technical Services (Randalls Isl.) | 12.2061 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -90 | 20%
CNYG-4098 | ACM & LEAD BULK SAMPLING & AIR MONITORING - CITYWIDE | 1998-09-30 | 1998-10-13 | 1998-06-23 | 92900 | 174000 | 1999-06-01 | 2002-05-30 | 2002-10-24 | GI | EN | Environmental Control Unit | 11.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 87.3%
CNYG-498 | BOILERS & HEATING SYSTEMS IN THE BRONX, MANHATTEN & S.I. | 1997-10-31 | 1997-12-08 | 1997-10-24 | 527383 | 793000 | 1998-05-11 | 1999-02-04 | 1999-11-23 | GI | CPM | Construction Project Manager | 13.1757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292 | 50.37%
CNYG-499 | GREENSTREET TRIANGLES - FY99 TREE PLANTING - BKLYN & S.I. | 1999-01-29 | 1999-01-11 | 1998-11-02 | 279181 | 302000 | 1999-04-15 | 2000-04-13 | 1999-09-15 | GI | T | Tree Unit | 12.5396 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -211 | 8.174%
CNYG-501M | STREET TREE (GREENSTREET PLANTING) FY 2001 MANHATTAN & BRONX | 2000-09-29 | 2000-10-31 | 2000-08-08 | 399909 | 540000 | 2001-03-19 | 2002-03-18 | 2002-01-21 | GI | T | Tree Unit | 12.899 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -56 | 35.03%
CNYG-501MR | STREET TREE (GREENSTREET PLANTING) FY 2002 MANHATTAN & BRONX | 2001-07-30 | 2001-07-11 | 2000-08-08 | 399909 | 440000 | 2001-10-01 | 2002-09-30 | 2002-05-22 | GI | T | Tree Unit | 12.899 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -131 | 10.03%
CNYG-503M | IN-KIND POOL FACILITIES PLUMBING SYSTEMS IN THE BRONX & MANHATTAN |  | 2003-02-14 | 2002-09-24 | 180000 | 200000 | 2003-08-06 | 2004-08-04 | 2004-08-04 | FI | TS | Technical Services (Randalls Isl.) | 12.1007 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 11.11%
CNYG-504M | COMFORT STATIONS & FACILITIES - CITYWIDE - HVAC WORK | 2003-09-30 | 2003-10-22 | 2003-07-02 | 170000 | 499000 | 2004-08-04 | 2005-08-03 | 2007-06-29 | FI | TS | Technical Services (Randalls Isl.) | 12.0436 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 695 | 193.5%
CNYG-599 | GREENSTREET TRIANGLES -FY 99 TREE PLANTING- MAN & BX | 1999-01-29 | 1999-01-05 | 1998-11-02 | 288797 | 311000 | 1999-05-05 | 2000-05-03 | 2000-02-21 | GI | T | Tree Unit | 12.5735 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -72 | 7.688%
CNYG-601M | STREET TREE (GREENSTREET PLANTING) CITYWIDE F/FY 2001 | 2000-09-29 | 2000-10-31 | 2000-08-08 | 329521 | 463000 | 2001-04-09 | 2002-04-08 | 2002-02-01 | GI | T | Tree Unit | 12.7054 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -66 | 40.51%
CNYG-601MR | STREET TREE (GREENSTREET PLANTING) CITYWIDE F/FY 2002 | 2001-07-30 | 2001-08-06 | 2000-08-08 | 329521 | 359000 | 2001-10-04 | 2002-10-03 | 2002-07-17 | GI | T | Tree Unit | 12.7054 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -78 | 8.946%
CNYG-602M | REMOVAL OF STUMPS & TREE REPLACEMENT | 2001-12-30 | 2001-12-12 | 2001-11-19 | 280238 | 300000 | 2002-09-30 | 2003-06-26 | 2003-06-17 | FI | T | Tree Unit | 12.5434 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -9 | 7.052%
CNYG-603M | IN-KIND POOL FACILITIES PLUMBING SYSTEMS IN BROOKLYN, QUEENS & STATEN ISLAND |  | 2003-02-14 | 2002-09-24 | 180000 | 234000 | 2003-08-27 | 2004-08-25 | 2004-08-25 | FI | TS | Technical Services (Randalls Isl.) | 12.1007 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30%
CNYG-604M | IN-KIND ELECTRICAL SYSTEMS F/POOL FACILITIES - CITYWIDE | 2003-09-30 | 2003-10-10 | 2003-07-02 | 200000 | 200000 | 2004-03-30 | 2005-03-29 | 2005-03-28 | FI | TS | Technical Services (Randalls Isl.) | 12.2061 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -1 | 0%
CNYG-605M | CITYWIDE - POOLS - ELECTRICAL SYSTEMS |  | 2004-09-13 | 2004-07-01 | 550000 | 660000 | 2005-04-07 | 2006-04-06 | 2006-06-23 | FI | TS | Technical Services (Randalls Isl.) | 13.2177 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 78 | 20%
CNYG-607M | CITYWIDE - REMOVAL OF DEAD TREES & STUMPS |  | 2006-12-29 | 2006-09-25 | 800000 | 880000 | 2007-06-04 | 2008-06-02 | 2008-02-05 | FI | T | Tree Unit | 13.5924 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -118 | 10%
CNYG-697 | RECONSTR. OF FENCES,GUIDERAILS & GENERAL SITEWORK | 1997-01-31 | 1997-01-31 | 1996-12-24 | 492555 | 620000 | 1997-04-28 | 1998-01-22 | 1998-01-15 | GI | RCU | Requirements Contract Unit | 13.1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -7 | 25.87%
CNYG-701M | STREET TREE (GREENSTREET PLANTING) IN BKLYN & S.I. F/FY 2001 | 2000-09-29 | 2000-10-31 | 2000-08-08 | 394311 | 432000 | 2001-04-04 | 2002-04-03 | 2002-01-29 | FI | T | Tree Unit | 12.8849 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -64 | 9.558%
CNYG-701MR | STREET TREE (GREENSTREET PLANTING) IN BKLYN & S.I. F/FY 2002 | 2001-07-30 | 2001-06-13 | 2000-08-08 | 394311 | 434000 | 2001-10-01 | 2002-09-30 | 2002-02-01 | FI | T | Tree Unit | 12.8849 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -241 | 10.07%
CNYG-704M | IN-KIND PLUMBING SYSTEMS F/POOL FACILITIES - CITYWIDE | 2003-09-30 | 2003-10-10 | 2003-07-02 | 300000 | 300000 | 2004-03-30 | 2005-03-29 | 2005-05-20 | FI | TS | Technical Services (Randalls Isl.) | 12.6115 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 52 | 0%
CNYG-797 | RECONSTR.OF SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1997-01-31 | 1997-01-27 | 1996-12-24 | 396196 | 500000 | 1997-05-05 | 1998-05-04 | 1998-06-04 | GI | RCU | Requirements Contract Unit | 12.8897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 31 | 26.2%
CNYG-801M | CITYWIDE - LEAD REMOVAL | 2000-10-30 | 2000-10-05 | 2000-08-31 | 131600 | 183000 | 2001-05-31 | 2004-05-29 | 2003-12-31 | GI | EN | Environmental Control Unit | 11.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -150 | 39.06%
CNYG-802M | CITYWIDE - COMFORT STATIONS & FACILITIES (PARTIAL ELECTRICAL) | 2001-12-31 | 2001-12-19 | 2001-12-04 | 150000 | 194000 | 2002-06-24 | 2003-06-23 | 2003-06-23 | GI | TS | Technical Services (Randalls Isl.) | 11.9184 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 29.33%
CNYG-802MR | CITYWIDE - COMFORT STATIONS & FACILITIES (PARTIAL ELECTRICAL) | 2001-12-31 | 2001-12-19 | 2001-12-04 | 150000 | 320000 | 2004-03-15 | 2005-03-14 | 2006-04-03 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 385 | 113.3%
CNYG-803M | IN-KIND POOL FACILITIES STRUCTURAL SYSTEMS IN BROOKLYN, QUEENS & STATEN ISLAND |  | 2003-02-19 | 2002-09-24 | 135000 | 163000 | 2003-07-16 | 2004-07-14 | 2004-07-14 | FI | TS | Technical Services (Randalls Isl.) | 11.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20.74%
CNYG-805M | CITYWIDE - POOLS - STRUCTURAL SYSTEMS |  | 2004-09-13 | 2004-07-01 | 550000 | 660000 | 2005-05-18 | 2006-05-17 | 2006-05-16 | FI | TS | Technical Services (Randalls Isl.) | 13.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -1 | 20%
CNYG-897 | PLAY EQUIPMENT,SAFETY SURFACE,HANDBALL CTS.& GENERAL SITEWORK | 1997-01-31 | 1997-01-27 | 1996-12-24 | 769779 | 1000000 | 1997-05-12 | 1998-05-11 | 1998-02-10 | GI | RCU | Requirements Contract Unit | 13.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -90 | 29.91%
CNYG-897R | PLAY EQUIPMENT,SAFETY SURFACE,HANDBALL CTS.& GENERAL SITEWORK | 1998-03-31 | 1998-03-31 | 1996-12-24 | 769779 | 901000 | 1998-07-06 | 1999-07-05 | 1999-09-08 | FI | RCU | Requirements Contract Unit | 13.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 65 | 17.05%
CNYG-899A | CITYWIDE - COMFORT STATIONS REQ. CONTRACT | 1999-09-30 | 1999-09-16 | 1998-07-14 | 550000 | 1786000 | 2000-06-12 | 2001-06-11 | 2001-10-30 | GI | X | Bronx Team | 13.2177 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 224.7%
CNYG-902M | CITYWIDE - COMFORT STATIONS & FACILITIES (PARTIAL PLUMBING) | 2001-12-31 | 2002-01-29 | 2001-12-04 | 150000 | 194000 | 2002-06-24 | 2003-06-23 | 2003-04-18 | FI | TS | Technical Services (Randalls Isl.) | 11.9184 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -66 | 29.33%
CNYG-902MR | CITYWIDE - COMFORT STATIONS & FACILITIES (PARTIAL PLUMBING) | 2001-12-31 | 2002-01-29 | 2001-12-04 | 350000 | 395000 | 2004-02-26 | 2005-02-24 | 2004-07-06 | FI | TS | Technical Services (Randalls Isl.) | 12.7657 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -233 | 12.86%
CNYG-903M | STREET & FLOWERING TREE PLANTING - BX, M, Q - FY 2003 |  | 2002-11-06 | 2002-10-08 | 350000 | 360000 | 2003-04-14 | 2004-04-12 | 2003-07-27 | GI | T | Tree Unit | 12.7657 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -260 | 2.857%
CNYG-903MR | STREET & FLOWERING TREE PLANTING - BX, M, Q - FY 2003 |  | 2002-11-06 | 2002-10-08 | 300000 | 399000 | 2004-04-12 | 2005-04-11 | 2004-09-29 | GI | T | Tree Unit | 12.6115 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -194 | 33%
CNYG-998 | BOILERS & HEATING SYSTEMS IN BROOKLYN & QUEENS | 1997-11-30 | 1997-12-29 | 1997-10-24 | 561890 | 607000 | 1998-05-26 | 1999-02-19 | 1999-07-16 | GI | CPM | Construction Project Manager | 13.2391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 8.028%
M001-102M | ABINGDON SQUARE PARK | 2003-03-16 | 2003-03-17 | 2001-10-04 | 586801 | 828000 | 2003-08-25 | 2004-05-20 | 2004-06-14 | GI | M | Manhattan Team | 13.2824 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 25 | 41.1%
M005-104M | SPIRAL FOUNTAIN @ THE BOSQUE/BATTERY PARK - CONSTR OF (PHASE II) |  | 2004-04-14 | 2004-02-09 | 1371932 | 7713000 | 2004-12-13 | 2005-06-10 | 2005-07-29 | GI | M | Manhattan Team | 14.1317 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 49 | 462.2%
M005-199 | BATTERY PARK - UPPER PROMENADE | 1999-08-31 | 1999-10-14 | 1999-05-25 | 4859994 | 6121000 | 2000-09-11 | 2001-10-21 | 2002-02-07 | GI | M | Manhattan Team | 15.3965 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 109 | 25.95%
M005-203M | CONSTR OF BOSQUE GARDENS - BATTERY PARK | 2003-09-15 | 2004-02-02 | 2003-09-11 | 4193042 | 7713000 | 2004-05-06 | 2004-12-05 | 2005-06-30 | GI | M | Manhattan Team | 15.2489 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 207 | 83.95%
M006-104M | TRIBECA PARK - PERIMETER SIDEWALKS |  | 2003-12-24 | 2003-11-19 | 174175 | 306000 | 2004-06-07 | 2004-09-04 | 2004-11-12 | GI | M | Manhattan Team | 12.0678 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 69 | 75.69%
M010-100M | CENTRAL PARK - SUMMERSTAGE SOUND & LIGHTING SYSTEM | 2000-03-31 | 2000-03-31 | 2000-02-28 | 400000 | 600000 | 2000-08-02 | 2000-11-29 | 2000-09-12 | GI | SS | Other | 12.8992 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78 | 50%
M010-105M | THE ARSENAL - BASEMENT & EXTERIOR ACCESSIBILITY |  |  | 2004-10-25 | 650000 | 1000000 | 2005-01-18 | 2005-07-28 | 2005-07-28 | GI | A;CPF | Other | 13.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85%
M010-1095 | C.P. - NO. MEADOW BALLFIELDS & ADJ LDSCAPE | 1997-10-24 | 1997-12-08 | 1995-02-03 | 4288330 | 5207000 | 1998-06-01 | 2000-05-30 | 1999-09-02 | FI | M;CPC | Other | 15.2714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -271 | 21.42%
M010-1196 | C.P. - TENNIS HOUSE ROOF @ 95TH ST. | 1996-11-15 | 1997-03-03 | 1996-01-11 | 539465 | 696000 | 1997-07-07 | 1998-02-01 | 1998-09-03 | FI | M | Manhattan Team | 13.1983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 214 | 29.02%
M010-1294 | C.P. - GREAT LAWN (INCLUDING IRRIGATION, ETC.) | 1995-07-31 | 1995-08-31 | 1994-05-05 | 4256895 | 22432000 | 1995-10-19 | 1998-04-18 | 1998-04-09 | FI | M | Manhattan Team | 15.2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -9 | 427%
M010-1296 | C.P.- HANDICAP ACCESS TO BELVEDERE CASTLE,E. 100 ST C.S.,DELACORTE C.S. | 1997-10-29 | 1997-10-29 | 1996-04-03 | 339000 | 369000 | 1998-01-06 | 1999-04-05 | 1999-06-05 | GI | CPC | Other | 12.7338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 8.85%
M010-197 | C.P. - SWEDISH COTTAGE | 1997-06-30 | 1997-03-31 | 1996-08-01 | 683000 | 700000 | 1997-04-14 | 1999-04-03 | 1998-03-20 | GI | CPF;M | Other | 13.4343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -379 | 2.489%
M010-200M | CENTRAL PARK - STORM & SANITARY INFRASTRUCTURE (EMERGENCY) | 2000-03-31 | 2000-03-31 | 2000-04-19 | 456506 | 924000 | 2000-07-20 | 2000-10-17 | 2000-10-16 | FI | M;CPC | Other | 13.0314 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 102.4%
M010-300M | CHILDREN'S ZOO MESH REPLACEMENT - CENTRAL PARK (EMERGENCY) | 2000-03-31 | 2000-03-31 | 2000-05-25 | 293527 | 360000 | 2000-09-20 | 2001-03-18 | 2001-08-09 | FI | SS | Other | 12.5897 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 22.65%
M010-303M | CENTRAL PARK RESERVOIR - PERIMETER FENCE |  |  |  | 1645000 | 2045000 | 2003-07-29 | 2004-07-27 | 2004-10-22 | FI | M;CPC | Other | 14.3133 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 24.32%
M010-407M | LASKER MEMORIAL POOL & RINK - EMERGENCY RECONSTR OF MECH EQUIPMENT |  | 2007-05-23 | 2007-05-02 | 1958509 | 2059000 | 2007-05-10 | 2007-11-05 | 2007-11-02 | FI | M;E;CR | Other | 14.4877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 5.131%
M010-507M | THE ARSENAL - ROOF & PARAPET WALLS (EMERGENCY RECONSTR) |  | 2007-06-21 | 2007-06-05 | 4793940 | 5450000 | 2007-06-16 | 2007-12-12 | 2007-12-13 | FI | M;CR | Other | 15.3829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13.69%
M010-894/1194 | C.P. - 79TH ST. BLDGS, YARD, ADJACENT LANDSCAPE | 1997-04-30 | 1997-09-27 | 1994-02-23 | 1750000 | 2252000 | 1998-05-04 | 1999-08-01 | 1999-07-29 | GI | M | Manhattan Team | 14.3751 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -3 | 28.69%
M011-196 | CHELSEA PARK - BALLFIELDS & PLAZA | 1997-03-31 | 1997-03-26 | 1995-09-06 | 976148 | 1290000 | 1997-09-09 | 1998-03-07 | 1998-06-02 | GI | M | Manhattan Team | 13.7914 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 87 | 32.15%
M013-197A | 6 FLAGPOLES IN CITY HALL PARK | 1996-10-31 | 1996-12-06 | 1996-07-08 | 68900 | 122000 | 1997-11-05 | 1998-02-02 | 1998-02-10 | FI | M | Manhattan Team | 11.1404 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 77.07%
M014-100MA/300M | JACKIE ROBINSON REC CTR - EXTERIOR & INTERIOR REPAIR | 2000-02-28 | 2000-04-04 | 1999-08-24 | 302791 | 693000 | 2001-02-05 | 2001-12-01 | 2002-04-26 | GI | M | Manhattan Team | 12.6208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 146 | 128.9%
M014-102M/103M | JACKIE ROBINSON RECREATION CTR. - PHASE II | 2002-10-31 | 2002-11-18 | 2001-07-27 | 495625 | 753000 | 2003-09-08 | 2004-09-01 | 2005-03-21 | GI | M | Manhattan Team | 13.1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 201 | 51.93%
M014-103M | (ELECTRICAL) JACKIE ROBINSON RECREATION CTR. - PHASE II | 2002-10-31 | 2002-11-18 | 2001-07-27 | 34236 | 34236 | 2003-09-08 | 2004-09-01 | 2005-01-12 | GI | M | Manhattan Team | 10.441 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 133 | 0%
M014-104MA | JACKIE ROBINSON PARK - PERIMETER SIDEWALKS, FENCING, CURBS & LANDSCAPING | 2005-08-15 | 2005-08-15 | 2004-06-22 | 332645.2 | 472000 | 2006-06-05 | 2006-09-02 | 2006-11-17 | GI | M | Manhattan Team | 12.7148 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 76 | 41.89%
M014-197 | JACKIE ROBINSON PARK PLGD | 1997-09-03 | 1998-03-27 | 1996-09-30 | 582067 | 883000 | 1998-09-23 | 1999-04-20 | 1999-09-30 | GI | CPM | Construction Project Manager | 13.2743 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 51.7%
M014-199 | JACKIE ROBINSON SIDEWALKS | 1999-02-26 | 1999-04-08 | 1998-11-05 | 344157 | 453000 | 1999-08-16 | 1999-11-13 | 1999-12-14 | GI | CPM | Construction Project Manager | 12.7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31.63%
M014-200M | (ELECTRICAL) JACKIE ROBINSON REC CTR | 2000-02-28 | 2000-03-21 | 1999-08-24 | 74780 | 75000 | 2001-02-05 | 2001-12-01 | 2002-04-26 | GI | M | Manhattan Team | 11.2223 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 146 | 0.2942%
M014-300M | (HVAC) JACKIE ROBINSON REC CTR | 2000-02-28 | 2000-03-21 | 1999-08-24 | 88000 | 88000 | 2001-02-05 | 2001-12-01 | 2002-04-26 | GI | M | Manhattan Team | 11.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 146 | 0%
M015-103M | COLUMBUS PARK - LANDSCAPE IN NORTHERN PORTION | 2003-09-15 | 2004-03-23 | 2003-05-13 | 1647523 | 2242000 | 2004-09-07 | 2005-04-10 | 2005-10-05 | GI | M | Manhattan Team | 14.3148 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 178 | 36.08%
M015-104M | COLUMBUS PARK - CONSTR OF SYNTH TURF ATHLETIC FIELD | 2004-03-15 | 2004-03-15 | 2004-01-29 | 731315 | 180000 | 2004-09-07 | 2005-03-05 | 2005-06-30 | FI | M | Manhattan Team | 13.5026 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 117 | -75.39%
M015-203MA/503M | COLUMBUS PARK - PAVILION & ADJACENT LANDSCAPE | 2003-10-31 | 2004-01-15 | 2003-11-05 | 2239810 | 3457000 | 2005-06-01 | 2006-06-30 | 2007-06-07 | FI | M | Manhattan Team | 14.6219 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 342 | 54.34%
M015-303MA | (ELECTRICAL) COLUMBUS PARK - PAVILION & ADJACENT LANDSCAPE | 2003-10-31 | 2004-01-15 | 2003-11-05 | 189000 | 189000 | 2005-06-01 | 2006-06-30 | 2007-08-20 | FI | M | Manhattan Team | 12.1495 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 416 | 0%
M015-403MA1 | (PLUMBING) COLUMBUS PARK - PAVILION & ADJACENT LANDSCAPE | 2003-10-31 | 2004-01-15 | 2003-11-05 | 135806 | 136000 | 2005-06-01 | 2006-06-30 | 2007-12-13 | FI | M | Manhattan Team | 11.819 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 531 | 0.1429%
M015-503MA | (H&V) COLUMBUS PARK - PAVILION & ADJACENT LANDSCAPE | 2003-10-31 | 2004-01-15 | 2003-11-05 | 64380 | 64380 | 2005-06-01 | 2006-06-30 | 2007-12-13 | FI | M | Manhattan Team | 11.0726 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 531 | 0%
M025-196 | DUANE PARK (HUDSON TRIANGLE) | 1997-10-31 | 1998-05-14 | 1995-10-02 | 165859 | 242000 | 1999-03-01 | 1999-08-27 | 1999-08-27 | GI | M | Manhattan Team | 12.0189 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 45.91%
M026-301M | (ELECTRICAL) DYCKMAN FARMHOUSE - FIRE DETECTION SYSTEM | 2001-04-30 | 2001-10-31 | 2000-11-08 | 137420 | 138000 | 2002-11-04 | 2003-05-02 | 2005-02-17 | GI | M | Manhattan Team | 11.8308 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 657 | 0.4221%
M026-401M | (PLUMBING) DYCKMAN FARMHOUSE - FIRE DETECTION SYSTEM | 2001-04-30 | 2001-10-31 | 2000-11-08 | 27785 | 28000 | 2002-11-04 | 2003-05-02 | 2005-02-17 | GI | M | Manhattan Team | 10.2323 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 657 | 0.7738%
M028-190 | FT. WASHINGTON LINK TO RIVERSIDE PARK | 1997-10-30 | 1997-08-26 | 1990-01-16 | 1861754 | 2041000 | 1998-03-02 | 1998-12-26 | 1999-07-16 | GI | M | Manhattan Team | 14.437 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 202 | 9.628%
M028-199A1 | FT. WASHINGTON PK. - LITTLE RED LIGHT HOUSE LANDSCAPE & LIGHTING SYSTEM | 1999-03-31 | 1999-10-13 | 1998-10-05 | 376000 | 454000 | 2001-03-05 | 2001-08-31 | 2001-11-13 | GI | M | Manhattan Team | 12.8373 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 74 | 20.74%
M028-200M | FT. WASHINGTON PARK - EMERGENCY STABILIZATION OF ROCK WALL FACE | 2000-08-31 | 2000-08-29 | 2000-06-09 | 1279850 | 957000 | 2000-12-04 | 2001-04-02 | 2001-11-01 | GI | CPM | Construction Project Manager | 14.0623 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | -25.23%
M028-299 | FT. WASHINGTON PARK - PLGD @ 162 & 163RD STS. | 2001-03-15 | 2001-04-03 | 1999-01-26 | 1226690 | 1537000 | 2001-09-10 | 2002-06-06 | 2002-07-09 | FI | CPM | Construction Project Manager | 14.0198 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 25.3%
M029-100M | FORT TRYON PARK - PERIMETER SIDEWALKS | 1999-11-30 | 1999-11-24 | 1999-08-17 | 208682 | 399000 | 2000-05-08 | 2000-09-04 | 2000-11-09 | GI | M | Manhattan Team | 12.2486 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 66 | 91.2%
M029-199/499 | FT. TRYON PARK - ANNE LOFTUS PLGD. FIELDHOUSE | 1999-01-31 | 1999-03-08 | 1998-07-16 | 377370 | 864000 | 1999-09-13 | 2000-09-11 | 2001-06-18 | GI | M | Manhattan Team | 12.841 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 280 | 129%
M029-299 | (ELECTRICAL) FT. TRYON PARK - ANNE LOFTUS PLGD FIELDHOUSE | 1999-01-31 | 1999-03-08 | 1998-07-16 | 24856 | 41000 | 1999-09-13 | 2000-09-11 | 2001-06-18 | GI | M | Manhattan Team | 10.1209 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 280 | 64.95%
M029-395 | ANNE LOFTUS PLGD. IN FT. TRYON PARK | 1996-11-30 | 1997-02-04 | 1995-05-01 | 1037797 | 1454000 | 1997-08-05 | 1998-05-31 | 1998-05-29 | GI | M | Manhattan Team | 13.8526 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -2 | 40.1%
M029-399 | (PLUMBING) FT. TRYON PARK - ANNE LOFTUS PLGD FIELDHOUSE | 1999-01-31 | 1999-03-08 | 1998-07-16 | 131691 | 132000 | 1999-09-13 | 2000-09-11 | 2002-02-26 | GI | M | Manhattan Team | 11.7882 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 533 | 0.2346%
M029-499 | (H&V) FT. TRYON PARK - ANNE LOFTUS PLGD FIELDHOUSE | 1999-01-31 | 1999-03-08 | 1998-07-16 | 39000 | 42000 | 1999-09-13 | 2000-09-11 | 2002-02-26 | GI | M | Manhattan Team | 10.5713 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 533 | 7.692%
M029-599A | FT. TRYON PARK - ROCK WALL STABILIZATION (EMERGENCY) | 1998-10-05 | 1999-01-14 | 1998-08-27 | 769620 | 1764000 | 1999-02-08 | 1999-05-08 | 1999-06-25 | GI | M | Manhattan Team | 13.5537 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 129.2%
M030-193 | FOLEY SQUARE | 1996-01-31 | 1997-02-13 | 1992-10-28 | 13785960 | 23117000 | 1997-08-11 | 1999-08-10 | 2000-05-19 | GI | M | Manhattan Team | 16.4392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 283 | 67.69%
M031-199 | GORMAN MEMORIAL PARK - STEPS, MONUMENT, SITEWORK | 2000-11-14 | 2001-01-19 | 1999-05-19 | 739215 | 980000 | 2001-07-09 | 2002-04-04 | 2002-08-12 | GI | M | Manhattan Team | 13.5133 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 130 | 32.57%
M033-198 | HAMILTON FISH REC. CTR. - EMERGENCY MARBLE TILE RECONSTR. | 1998-06-12 | 1998-06-12 | 1998-06-04 | 585000 | 670000 | 1998-06-20 | 1998-07-04 | 1998-07-10 | GI | M | Manhattan Team | 13.2794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 14.53%
M037-100M | HIGHBRIDGE PARK - COURT & LANDSCAPE AREAS ADJ TO W.175-177 STS. | 2000-02-28 | 2000-02-09 | 1999-09-01 | 638118 | 817000 | 2000-07-31 | 2001-01-26 | 2001-01-25 | GI | CPM | Construction Project Manager | 13.3663 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 28.03%
M037-101M | HIGHBRIDGE PARK - PATHS - DYCKMAN ST. TO W.186 ST | 2001-12-28 | 2002-03-15 | 2000-09-14 | 415783 | 708000 | 2002-11-04 | 2003-05-02 | 2003-12-02 | GI | CPM | Construction Project Manager | 12.9379 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 70.28%
M037-102M;104M | HIGHBRIDGE BATHHOUSE - GYM FLOOR & MISC WORK | 2003-03-31 | 2003-12-17 | 2001-10-22 | 269080 | 510000 | 2004-09-13 | 2005-01-10 | 2005-03-18 | GI | M | Manhattan Team | 12.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 67 | 89.53%
M037-104M | (PLUMBING) HIGHBRIDGE BATHHOUSE - GYM FLOOR & MISC WORK | 2003-03-31 | 2004-04-12 | 2003-11-11 | 120474 | 121000 | 2004-09-13 | 2005-01-10 | 2004-12-10 | GI | M | Manhattan Team | 11.6992 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -31 | 0.4366%
M037-106M | HIGHBRIDGE PARK - EMERGENCY STABILIZATION OF 800 LF OF ROCKWALL FACE |  | 2005-11-03 | 2005-11-03 | 817350 | 900000 | 2005-11-28 | 2006-03-07 | 2006-06-13 | FI | M;CR | Other | 13.6138 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 10.11%
M037-196 | HIGHBRIDGE PARK - WALLENBERG PLGD. | 1997-09-20 | 1998-04-02 | 1995-10-03 | 1582840 | 2085000 | 1998-07-20 | 1999-07-14 | 1999-05-25 | GI | CPM | Construction Project Manager | 14.2747 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50 | 31.73%
M037-199 | HIGHBRIDGE PARK - WATERPROOFING POOL & DECK AREAS | 1999-10-29 | 1999-10-21 | 1999-05-12 | 180700 | 237000 | 2000-03-17 | 2000-07-14 | 2000-08-17 | GI | TS | Technical Services (Randalls Isl.) | 12.1046 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 34 | 31.16%
M037-200M/400M | HIGHBRIDGE PARK BATHHOUSE - PORTIONS OF | 2000-02-10 | 2000-02-27 | 1999-10-25 | 129601 | 701000 | 2000-09-18 | 2001-03-16 | 2001-06-22 | FI | M | Manhattan Team | 11.7722 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 98 | 440.9%
M037-206M | HIGHBRIDGE PARK - BUCZEK BALLFIELD & ADJACENT BASKETBALL COURT | 2006-09-10 | 2007-01-08 | 2006-06-15 | 719165.7 | 1042000 | 2007-09-05 | 2008-02-01 | 2007-11-19 | FI | M | Manhattan Team | 13.4858 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -74 | 44.89%
M037-297 | HIGHBRIDGE PARK BATHHOUSE & POOL - H & V SYSTEMS | 1997-12-31 | 1998-01-13 | 1997-07-11 | 330720 | 464000 | 1998-06-22 | 1998-12-18 | 1999-05-06 | GI | CPM | Construction Project Manager | 12.709 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 40.3%
M037-299 | HIGHBRIDGE PARK - POOL MECHANICAL SYSTEMS | 1999-11-30 | 1999-10-26 | 1999-05-12 | 132400 | 176000 | 2000-03-16 | 2000-07-13 | 2000-08-17 | GI | TS | Technical Services (Randalls Isl.) | 11.7936 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 35 | 32.93%
M037-300M | (ELECTRICAL) HIGHBRIDGE PARK BATHHOUSE | 2000-02-10 | 2000-03-27 | 1999-10-25 | 13900 | 14000 | 2000-09-25 | 2001-03-23 | 2001-06-22 | GI | M | Manhattan Team | 9.5396 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 91 | 0.7194%
M037-400M | (PLUMBING) HIGHBRIDGE PARK BATHHOUSE | 2000-02-10 | 2000-03-27 | 1999-10-25 | 61900 | 93000 | 2000-09-18 | 2001-03-16 | 2001-06-22 | GI | M | Manhattan Team | 11.0333 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 98 | 50.24%
M038-100M | J.J. WALKER PARK - BALLFIELD | 1999-12-22 | 1999-12-10 | 1999-07-08 | 287772 | 456000 | 2000-05-23 | 2000-09-19 | 2000-10-17 | GI | M | Manhattan Team | 12.5699 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 58.46%
M041-103M | HAMILTON PLACE PLGD (EMERGENCY) |  |  | 2003-05-28 | 259800 | 323000 | 2003-05-28 | 2003-07-10 | 2003-07-03 | GI | M | Manhattan Team | 12.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -7 | 24.33%
M042-104M | INWOOD HILL PARK - ENTRANCES & PATHS | 2003-01-05 | 2004-03-16 | 2003-11-20 | 563974 | 731000 | 2004-08-09 | 2005-02-04 | 2005-06-07 | FI | M | Manhattan Team | 13.2428 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 123 | 29.62%
M042-105M | INWOOD HILL PARK - NATURE CENTER LOBBY & CONSTR OF A BOATHOUSE | 2005-03-01 | 2005-03-15 | 2004-12-14 | 249940 | 498000 | 2005-12-21 | 2006-06-18 | 2006-06-09 | GI | M | Manhattan Team | 12.429 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -9 | 99.25%
M042-106M | INWOOD HILL PARK - DRAINAGE & RIPARIAN FOREST SLOPES | 2006-03-05 | 2006-03-15 | 2005-09-27 | 292955 | 496000 | 2007-03-12 | 2007-09-07 | 2007-09-07 | FI | M | Manhattan Team | 12.5878 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 69.31%
M043-102M | ISHAM PARK - RETAINING WALL ON PARK TERRACE WEST | 2002-03-15 | 2002-05-20 | 2001-10-11 | 80703 | 165000 | 2003-03-17 | 2003-06-14 | 2003-05-29 | GI | M | Manhattan Team | 11.2985 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -16 | 104.5%
M045-104M | JOHN JAY PARK TOT LOT | 2005-03-15 | 2005-03-08 | 2003-09-11 | 656780.68 | 866000 | 2005-08-15 | 2006-02-10 | 2006-06-21 | GI | M | Manhattan Team | 13.3951 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 131 | 31.86%
M046-101M | VIETNAM VETERANS MEMORIAL PLAZA | 2000-10-30 | 2000-10-26 | 2000-07-24 | 2450000 | 2450000 | 2001-03-19 | 2002-03-18 | 2001-10-24 | GI | SS | Other | 14.7116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -145 | 0%
M047-102M | THOMAS JEFFERSON PARK - ARTIFICIAL TURF F/SOCCER FIELD | 2002-03-29 | 2002-03-15 | 2002-01-30 | 906921 | 1522000 | 2002-11-12 | 2003-06-09 | 2003-12-01 | GI | CPM | Construction Project Manager | 13.7178 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 67.82%
M052-100M | MADISON SQUARE PARK PLAYGROUND (NORTHEAST CORNER) | 2000-09-29 | 2000-10-21 | 2000-05-04 | 626000 | 768000 | 2001-04-16 | 2001-10-12 | 2002-02-26 | GI | M | Manhattan Team | 13.3471 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 137 | 22.68%
M052-102M | MADISON SQUARE PARK - SECURITY LIGHTING | 2002-02-25 | 2003-01-27 | 2001-10-10 | 197600 | 273000 | 2003-09-30 | 2003-11-28 | 2004-01-09 | GI | M | Manhattan Team | 12.194 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 42 | 38.16%
M052-197 | MADISON SQUARE PK. SO.END - PERIMETER FENCE & SPRAY FOUNTAIN | 1997-10-08 | 1998-04-09 | 1996-10-18 | 661666 | 839000 | 1998-09-08 | 1999-03-06 | 1999-07-01 | GI | M | Manhattan Team | 13.4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 117 | 26.8%
M052-199 | MADISON SQUARE PARK | 1999-02-26 | 1999-02-10 | 1998-09-11 | 2500000 | 5200000 | 1999-02-12 | 2001-08-09 | 2001-10-03 | FI | CPF | Other | 14.7318 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 108%
M053-107M | T.ROOSEVELT PARK - PORTION OF PERIMETER SIDEWALKS (M053) |  | 2007-01-30 | 2006-08-18 | 772677.25 | 1000000 | 2007-08-13 | 2008-02-08 | 2007-12-19 | FI | M | Manhattan Team | 13.5576 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -51 | 29.42%
M053-195 | THEODORE ROOSEVELT PARK (NO.WEST CORNER) | 1999-02-26 | 1999-06-18 | 1994-07-19 | 1203000 | 1309000 | 1999-07-01 | 2000-06-29 | 2000-07-13 | FI | M | Manhattan Team | 14.0003 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 8.811%
M054-198 | MITCHEL SQUARE PARK | 1997-11-15 | 1997-11-25 | 1997-09-09 | 788655 | 945000 | 1998-03-09 | 1998-10-14 | 1998-10-14 | GI | M | Manhattan Team | 13.5781 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 19.82%
M056-104M | MORNINGSIDE PARK - STAIRWAYS & PATHS @ W 120TH ST. | 2004-01-05 | 2004-03-04 | 2003-10-10 | 524000 | 685000 | 2004-09-07 | 2005-06-03 | 2005-11-15 | GI | M | Manhattan Team | 13.1692 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 165 | 30.73%
M058-103M | MARCUS GARVEY PARK - LANDSCAPE - EAST SIDE | 2003-03-28 | 2004-05-03 | 2004-02-12 | 931279 | 1164000 | 2005-03-21 | 2005-11-15 | 2005-09-23 | GI | M | Manhattan Team | 13.7443 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -53 | 24.99%
M058-105M | MARCUS GARVEY PARK - STAIRWAYS & PATHS | 2005-03-15 | 2005-03-11 | 2004-09-16 | 467820 | 571000 | 2005-08-22 | 2005-12-19 | 2006-06-02 | GI | M | Manhattan Team | 13.0558 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 165 | 22.06%
M058-197 | PELHAM FRITZ RECREATION CTR. ROOF | 1997-01-15 | 1997-03-31 | 1996-08-18 | 206750 | 350000 | 1997-08-11 | 1997-12-08 | 1998-04-22 | FI | M | Manhattan Team | 12.2393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 135 | 69.29%
M058-297 | MARCUS GARVEY PARK BASEBALL DIAMOND @ W.121 ST. | 1997-03-26 | 1997-03-26 | 1997-01-03 | 299789 | 390000 | 1998-05-12 | 1998-09-08 | 1998-12-23 | GI | M | Manhattan Team | 12.6108 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 106 | 30.09%
M060-103M | PARK AVENUE CENTER PLOT-BET. 96TH & 97TH STREETS | 2003-03-31 | 2004-03-10 | 2002-12-02 | 684805 | 953000 | 2005-03-14 | 2005-12-08 | 2006-10-27 | GI | M | Manhattan Team | 13.4369 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 323 | 39.16%
M060-198 | PARK AVENUE SOUTH 34TH -39TH STS. | 1998-03-15 | 1998-04-14 | 1998-01-26 | 330100 | 433000 | 1998-07-13 | 1999-02-07 | 1999-11-17 | GI | M | Manhattan Team | 12.7072 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 283 | 31.17%
M060-199 | PARK AVENUE MALLS - 49TH - 50TH STS. | 1999-10-30 | 1999-12-10 | 1999-07-07 | 127313 | 174000 | 2000-06-26 | 2000-10-03 | 2000-11-08 | GI | M | Manhattan Team | 11.7544 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 36.67%
M060-298 | PARK AVENUE MALLS - 91ST - 96TH STS. | 1998-03-15 | 1998-04-14 | 1998-01-26 | 110964 | 171000 | 1998-07-13 | 1998-11-09 | 1999-06-14 | GI | M | Manhattan Team | 11.617 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 217 | 54.1%
M064-103M | LILLIAN D. WALD PLGD | 2003-03-28 | 2003-03-20 | 2002-09-30 | 808439 | 1071000 | 2003-09-15 | 2004-06-10 | 2004-12-22 | GI | M | Manhattan Team | 13.6029 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 195 | 32.48%
M066-197 | GERTRUDE B. KELLY PLGD. | 1997-12-31 | 1998-02-02 | 1996-10-23 | 431000 | 561000 | 1998-09-23 | 1999-03-21 | 1999-05-13 | GI | M | Manhattan Team | 12.9739 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 53 | 30.16%
M069-102MA | VESUVIO/THOMPSON PLAYGROUND | 2004-09-30 | 2003-04-14 | 2001-08-20 | 2127000 | 2916000 | 2006-04-03 | 2006-12-28 | 2007-07-17 | FI | M | Manhattan Team | 14.5702 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 201 | 37.09%
M071-101M | RIVERSIDE PARK @ 115TH STREET ENTRANCE | 2005-12-15 | 2004-02-20 | 2003-06-24 | 997846 | 1421000 | 2005-05-23 | 2006-02-26 | 2006-01-04 | GI | M | Manhattan Team | 13.8134 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -53 | 42.41%
M071-102M | RIVERSIDE PARK - PEDESTRIAN AREAS (79TH TO 87TH STS) | 2002-08-28 | 2002-12-17 | 2001-10-10 | 914245 | 1175000 | 2003-09-22 | 2004-06-17 | 2004-06-29 | GI | M | Manhattan Team | 13.7259 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 28.52%
M071-105MA | RIVERSIDE PK - PLAY EQUIPMT @ 91ST ST PLGD; WADING POOL & WATER FEATURE @ 97TH ST PLGD | 2005-03-15 | 2005-03-17 | 2004-11-30 | 168430 | 256000 | 2006-04-17 | 2006-10-13 | 2006-09-15 | FI | M | Manhattan Team | 12.0343 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -28 | 51.99%
M071-106M | RIVERSIDE PARK PROMENADE FROM W. 83RD - W. 91ST STREETS | 2006-03-01 | 2006-03-13 | 2005-09-12 | 1351755.99 | 1678000 | 2006-10-23 | 2007-07-19 | 2007-10-18 | FI | M | Manhattan Team | 14.1169 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 91 | 24.13%
M071-196 | RIVERSIDE PARK - CLAREMONT PLGD | 1996-10-31 | 1996-11-06 | 1995-10-02 | 444503 | 576000 | 1997-04-14 | 1997-10-10 | 1998-04-03 | GI | M | Manhattan Team | 13.0047 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 175 | 29.58%
M071-197 | RIVERSIDE PARK - 83RD ST. PLGD. | 1997-09-30 | 1998-01-26 | 1996-10-17 | 551061 | 782000 | 1998-05-04 | 1999-01-28 | 1999-04-30 | GI | M | Manhattan Team | 13.2196 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 92 | 41.91%
M071-198 | RIVERSIDE PARK - 119TH ST. (ULYSSES) TENNIS CTS. | 1998-02-28 | 1998-04-15 | 1997-09-12 | 1098287 | 1318000 | 1998-09-02 | 1999-06-28 | 1999-09-08 | GI | CPM | Construction Project Manager | 13.9093 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 20.01%
M071-199 | RIVERSIDE PARK - 79TH ST. ENTRANCE & PATHS | 1999-03-30 | 1999-03-26 | 1998-10-08 | 535328 | 774000 | 1999-07-19 | 2000-01-14 | 2000-05-15 | GI | M | Manhattan Team | 13.1906 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 122 | 44.58%
M071-296 | RIVERSIDE PARK - 101 ST. SOCCER FIELD | 1996-11-04 | 1997-02-06 | 1995-10-02 | 785671 | 1047000 | 1997-08-18 | 1998-03-15 | 1998-04-16 | GI | CPM | Construction Project Manager | 13.5743 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 33.26%
M071-298A | RIVERSIDE DRIVE MALLS - W. 110TH-114TH STS. | 1998-12-31 | 1999-06-18 | 1997-10-21 | 303346 | 366000 | 1999-10-18 | 2000-04-14 | 2000-07-05 | GI | M | Manhattan Team | 12.6226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 82 | 20.65%
M071-303M | RIVERSIDE PARK - OVERLOOK & VEH RAMPS ON ROUTE 9A | 2004-03-31 | 2004-02-24 | 2003-06-12 | 197786 | 329000 | 2004-09-20 | 2005-03-18 | 2005-04-21 | GI | M | Manhattan Team | 12.1949 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 34 | 66.34%
M071-395 | RIVERSIDE PARK - BASKETBALL CTS @ W.111TH ST. | 1996-05-13 | 1996-06-19 | 1995-10-31 | 290569 | 354000 | 1997-03-03 | 1997-07-20 | 1998-01-07 | FI | CPM | Construction Project Manager | 12.5796 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 21.83%
M071-397 | RIVERSIDE PARK - 105TH ST. PLAY AREA | 1997-03-31 | 1997-04-09 | 1996-12-05 | 181112 | 281000 | 1997-07-21 | 1997-11-17 | 1998-03-26 | FI | M | Manhattan Team | 12.1069 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 129 | 55.15%
M071-403M | RIVERSIDE PK - TWO BALLFIELDS FROM WEST 103RD TO 104TH & W 107TH TO W 108TH STS | 2006-03-20 | 2006-03-20 | 2003-03-29 | 2293579 | 3732000 | 2005-03-21 | 2006-03-20 | 2006-03-31 | FI | SS;M | Other | 14.6456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 62.72%
M071-496 | RIVERSIDE PARK - PATH (CHERRY WALK) FROM 100TH TO 125TH STS. | 1998-01-31 | 1998-03-24 | 1996-01-16 | 1829240 | 2142000 | 1999-03-15 | 1999-12-09 | 2000-06-13 | GI | M | Manhattan Team | 14.4194 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 187 | 17.1%
M072-100MA | RIVERSIDE PARK DRIVE PEDESTRIAN AREA - 135TH - 138TH STS. | 2000-04-04 | 2001-01-26 | 1999-11-17 | 607143 | 917000 | 2001-08-01 | 2001-12-28 | 2002-08-29 | GI | CPM | Construction Project Manager | 13.3165 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 51.04%
M072-101M | RIVERSIDE PARK - 143 TO 148TH ST. PATH RESTORATION | 2002-09-30 | 2003-03-19 | 2001-09-26 | 818125 | 1183000 | 2003-09-22 | 2004-03-19 | 2004-12-23 | GI | M | Manhattan Team | 13.6148 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 279 | 44.6%
M072-103M | NORTH RIVER WEST 135TH-145TH STREETS | 1999-09-08 | 2003-03-31 | 2003-03-03 | 2393333 | 3884000 | 2004-08-09 | 2005-02-04 | 2007-08-28 | FI | M | Manhattan Team | 14.6882 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 935 | 62.28%
M072-193 | RIVERSIDE PARK - PLAYGROUND @ 148TH ST. | 1996-10-31 | 1996-12-17 | 1992-10-06 | 265125 | 393000 | 1997-04-07 | 1997-10-03 | 1998-01-29 | GI | M | Manhattan Team | 12.488 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 118 | 48.23%
M072-199 | RIVERSIDE PARK ISLANDS (RALPH ELLISON ISLAND 149-153 STREETS) | 2001-08-31 | 2001-08-16 | 1998-09-21 | 489785 | 818000 | 2002-06-10 | 2002-12-06 | 2002-12-06 | GI | M | Manhattan Team | 13.1017 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 67.01%
M073-105M | ROGER MORRIS PARK-SO. STONE RETAINING WALL & DRAINAGE SYS (EMERGENCY) |  | 2004-12-09 | 2004-11-30 | 247140 | 330000 | 2004-12-27 | 2005-01-25 | 2005-02-18 | GI | M | Manhattan Team | 12.4177 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 33.53%
M073-194/199/299 | MORRIS JUMEL MANSION FIRE DETECTION & SUPPRESSION SYSTEM | 1999-03-30 | 1999-03-18 | 1994-04-27 | 142456 | 545000 | 1999-08-23 | 2000-01-19 | 2000-09-22 | GI | M | Manhattan Team | 11.8668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 247 | 282.6%
M073-199 | (ELECTRICAL) MORRIS JUMEL MANSION FIRE DETECTION & SUPPRESSION SYSTEM | 1999-03-18 | 1999-03-18 | 1999-12-22 | 39800 | 40000 | 1999-08-23 | 2000-01-19 | 2000-09-22 | GI | M | Manhattan Team | 10.5916 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 247 | 0.5025%
M073-201M/301M | MORRIS-JUMEL MANSION - ROOF & MISC. WORK | 2000-02-15 | 2001-01-30 | 2000-10-02 | 144125 | 353000 | 2001-06-25 | 2001-10-22 | 2002-02-12 | GI | M | Manhattan Team | 11.8784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 113 | 144.9%
M073-299 | (MISC RESTORATION) MORRIS JUMEL MANSION FIRE DETECTION & SUPPRESSION SYSTEM | 1999-03-18 | 1999-03-18 | 1999-12-22 | 163330 | 164000 | 1999-08-23 | 2000-01-19 | 2000-09-22 | GI | M | Manhattan Team | 12.0035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 247 | 0.4102%
M073-301M | (MECHANICAL/BOILER WORK) MORRIS JUMEL MANSION | 2000-12-15 | 2001-02-02 | 2000-10-12 | 62920 | 65000 | 2001-06-25 | 2001-10-22 | 2002-02-12 | GI | M | Manhattan Team | 11.0496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 113 | 3.306%
M076-100M | ST. VARTAN PLAYGROUND RECONSTRUCTION | 2000-11-30 | 2000-11-15 | 2000-07-17 | 440288 | 592000 | 2001-04-09 | 2001-10-05 | 2002-01-31 | GI | M | Manhattan Team | 12.9952 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 118 | 34.46%
M077-105M | SAINT NICHOLAS PARK - STEPS | 2005-12-15 | 2005-03-15 | 2004-09-16 | 929780 | 1210000 | 2005-10-17 | 2006-04-14 | 2006-06-30 | GI | M | Manhattan Team | 13.7427 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 77 | 30.14%
M079-104M | ST. CATHERINES PARK - COURT GAME AREA | 2004-03-01 | 2004-03-10 | 2003-09-15 | 485903 | 665000 | 2004-09-13 | 2005-01-10 | 2005-02-10 | GI | M | Manhattan Team | 13.0938 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 31 | 36.86%
M079-196 | ST. CATHERINE'S PARK | 1998-01-31 | 1998-04-08 | 1995-10-02 | 832792 | 1084000 | 1998-07-07 | 1999-04-02 | 1999-07-13 | GI | M | Manhattan Team | 13.6325 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 102 | 30.16%
M081-100M | CARL SCHURZ PK - EMERGENCY DEMO OF DAMAGED STRUCTURES & DECKS @ 90TH ST PIER | 1999-09-30 | 1999-09-07 | 1999-08-27 | 43045 | 56000 | 1999-07-10 | 1999-07-24 | 1999-07-16 | FI | B | Brooklyn Team | 10.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 30.1%
M081-104M | CARL SCHURZ PARK - LANDSCAPE & PATHS RECON |  | 2004-03-09 | 2003-12-12 | 313695 | 457000 | 2004-10-12 | 2005-02-08 | 2005-02-24 | GI | M | Manhattan Team | 12.6562 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 45.68%
M081-203M/503M | GRACIE MANSION/CARL SCHURZ PARK - MISC RECONSTR. |  | 2003-06-03 | 2003-02-04 | 177235 | 4635000 | 2004-02-17 | 2004-08-23 | 2005-01-31 | GI | M | Manhattan Team | 12.0852 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 161 | 2515%
M081-204MA | CARL SCHURZ PARK - SIDEWALKS, PVMTS, HYDRANTS, FENCING, ETC |  | 2004-04-20 | 2004-03-30 | 269000 | 350000 | 2005-02-01 | 2005-07-30 | 2005-08-11 | GI | RCU | Requirements Contract Unit | 12.5025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 30.11%
M081-205M | CARL SCHURZ PARK - PERIMETER SIDEWALK & LANDSCAPE | 2005-03-15 | 2005-01-06 | 2004-08-23 | 507157 | 750000 | 2005-07-20 | 2006-01-15 | 2005-12-08 | GI | M | Manhattan Team | 13.1366 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -38 | 47.88%
M081-299 | CARL SCHURZ PK - PARTIAL RECONSTR. OF CHILDREN'S PLGD. | 1999-10-22 | 1999-10-26 | 1999-05-17 | 413051 | 540000 | 2000-04-24 | 2000-10-20 | 2000-11-20 | GI | M | Manhattan Team | 12.9313 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 31 | 30.73%
M081-303M | (ELECTRICAL) GRACIE MANSION/CARL SCHURZ PARK - MISC RECONSTR. |  | 2003-06-03 | 2003-02-04 | 86996 | 60500 | 2004-02-17 | 2004-08-23 | 2005-01-31 | GI | M | Manhattan Team | 11.3736 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 161 | -30.46%
M081-403M | (PLUMBING) GRACIE MANSION/CARL SCHURZ PARK - MISC RECONSTR. |  | 2003-06-03 | 2003-02-04 | 41236 | 41236 | 2004-02-17 | 2004-08-23 | 2005-01-31 | GI | M | Manhattan Team | 10.6271 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 161 | 0%
M081-503M | (H&V) GRACIE MANSION/CARL SCHURZ PARK - MISC RECONSTR. |  | 2003-06-03 | 2003-02-04 | 1406200 | 1406200 | 2004-02-17 | 2004-08-23 | 2005-01-31 | GI | M | Manhattan Team | 14.1564 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 161 | 0%
M082-199 | SEWARD PARK - 2 PLAYGROUNDS | 1999-08-31 | 1999-10-06 | 1998-10-08 | 1898834 | 2353000 | 2000-04-17 | 2001-01-11 | 2001-06-18 | GI | M | Manhattan Team | 14.4568 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 158 | 23.92%
M086-198 | STUYVESANT PARK SIDEWALK | 1998-02-01 | 1998-02-17 | 1997-10-01 | 184475 | 310000 | 1998-08-17 | 1998-11-14 | 1999-04-20 | GI | M | Manhattan Team | 12.1253 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 157 | 68.04%
M089-198 | UNION SQUARE - SOUTH EXPANSION | 2000-02-09 | 2000-03-30 | 1998-04-08 | 4899569 | 8151000 | 2000-10-04 | 2002-03-27 | 2002-10-09 | GI | CPM | Construction Project Manager | 15.4047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 66.36%
M094-198 | BROADWAY MALLS - BETWEEN 60TH & 122ND STS. | 1998-03-30 | 1998-03-27 | 1997-09-29 | 512480 | 694000 | 1998-09-17 | 1999-06-13 | 1999-07-08 | GI | M | Manhattan Team | 13.147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 25 | 35.42%
M095-103MA | BROADWAY MALLS - W. 140TH TO W. 145TH STS. |  | 2004-03-15 | 2003-10-07 | 226373.5 | 392000 | 2006-05-15 | 2006-09-11 | 2006-12-15 | GI | M | Manhattan Team | 12.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 95 | 73.17%
M096-106M | SEVENTH AVE CENTER PLOTS (POWELL MALLS) | 2006-02-01 | 2006-02-14 | 2005-10-19 | 311000 | 399000 | 2006-07-17 | 2007-01-12 | 2006-11-22 | GI | M | Manhattan Team | 12.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -51 | 28.3%
M098-102M/202M | WASHINGTON SQUARE PARK ARCH RESTORATION | 2002-02-15 | 2002-05-01 | 2001-07-20 | 1487600 | 2731000 | 2003-01-06 | 2004-04-04 | 2004-04-28 | GI | M | Manhattan Team | 14.2127 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 83.58%
M098-202M | (ELECTRICAL) WASHINGTON SQUARE PARK ARCH RESTORATION | 2002-02-15 | 2002-05-06 | 2001-07-20 | 412224 | 412224 | 2003-01-06 | 2004-04-04 | 2004-04-28 | GI | M | Manhattan Team | 12.9293 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0%
M098-295 | WASHINGTON SQUARE ARCH | 1996-10-31 | 1997-02-13 | 1995-05-08 | 193150 | 276000 | 1997-07-23 | 1998-02-17 | 1998-11-18 | GI | M | Manhattan Team | 12.1712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 274 | 42.89%
M099-195 | J.HOOD WRIGHT PARK - PLGD/BALLFIELD/COURT AREA | 1996-11-30 | 1997-02-25 | 1995-09-25 | 1485780 | 2255000 | 1997-06-16 | 1998-11-12 | 1999-02-10 | GI | CPM | Construction Project Manager | 14.2115 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 51.77%
M099-295/395/495 | J.HOOD WRIGHT GOLDEN AGE CTR. & C.S. | 1996-04-01 | 1997-02-04 | 1994-11-16 | 744412 | 1291000 | 1997-06-16 | 1998-11-12 | 1999-02-10 | GI | CPM | Construction Project Manager | 13.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 73.43%
M099-395 | (ELECTRICAL) J.HOOD WRIGHT GOLDEN AGE CTR & C.S. | 1996-04-01 | 1997-02-03 | 1997-01-06 | 88411 | 230000 | 1997-06-16 | 1998-11-12 | 1999-02-10 | GI | CPM | Construction Project Manager | 11.3898 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 160.1%
M099-495 | (MECHANICAL) J.HOOD WRIGHT GOLDEN AGE CTR & C.S. | 1996-04-01 | 1997-02-03 | 1997-01-06 | 248858 | 488000 | 1997-06-16 | 1998-11-12 | 1999-02-10 | GI | CPM | Construction Project Manager | 12.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 96.1%
M103-196A | PORTIONS OF CARMINE ST. REC. CTR. | 1995-12-15 | 1996-04-01 | 1995-08-21 | 271654 | 567000 | 1996-09-03 | 1997-03-01 | 1998-04-15 | FI | M | Manhattan Team | 12.5123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 410 | 108.7%
M104-198 | RANDALL'S ISLAND DOWNING STADIUM RUNNING TRACK | 1998-03-31 | 1998-03-17 | 1998-02-06 | 103457 | 169000 | 1998-08-03 | 1998-08-23 | 1998-10-30 | GI | M | Manhattan Team | 11.5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 68 | 63.35%
M104-200MA | RANDALLS IS. (LITTLE HELL GATE INLET) - ELEVATED BOARDWALK/BRIDGE | 2001-03-30 | 2001-06-29 | 2000-03-23 | 1487822 | 1650000 | 2002-08-05 | 2003-05-01 | 2004-12-17 | GI | M | Manhattan Team | 14.2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 596 | 10.9%
M104-299 | RANDALLS ISLAND - LITTLE HELL GATE ROADWAY | 1999-11-12 | 2000-03-18 | 1998-08-18 | 2062024 | 2661000 | 2001-06-04 | 2001-11-30 | 2003-12-19 | GI | CPM | Construction Project Manager | 14.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749 | 29.05%
M105-100M | SARA D. ROOSEVELT PARK - ATHLETIC FIELD | 2000-10-30 | 2000-10-31 | 2000-07-20 | 814749 | 1170000 | 2001-06-04 | 2001-11-30 | 2002-04-10 | GI | M | Manhattan Team | 13.6106 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 131 | 43.6%
M105-101M | SARA ROOSEVELT PARK - EMERGENCY STABILIZATION OF SOIL | 2001-06-15 | 2001-06-18 | 2001-03-16 | 1582484 | 2743000 | 2001-09-10 | 2002-03-08 | 2002-10-18 | GI | CPM | Construction Project Manager | 14.2745 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 73.34%
M105-105M | SARA D ROOSEVELT PARK - PROMENADE | 2003-02-28 | 2003-02-28 | 2004-10-04 | 170635 | 273000 | 2006-09-18 | 2006-11-16 | 2006-11-16 | GI | M | Manhattan Team | 12.0473 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 59.99%
M108-199 | SUTTON PLACE PARKS - EAST 33/54 STS. & EAST 55/57 STS. | 1999-08-15 | 1999-09-09 | 1998-10-09 | 297185 | 429000 | 2000-02-28 | 2000-08-25 | 2000-08-18 | GI | M | Manhattan Team | 12.6021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -7 | 44.35%
M125-199 | RECREATION AREA @ AVE.OF AMERICAS & 3RD & 4TH ST - GARDEN | 1999-03-31 | 1999-01-26 | 1998-12-03 | 92403 | 109000 | 1999-08-30 | 2000-02-25 | 2000-10-27 | GI | M | Manhattan Team | 11.4339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 245 | 17.96%
M130-199A1/499A1 | EAST 54TH ST. RECREATION CTR | 2000-12-31 | 2001-02-20 | 1998-10-30 | 1792650 | 7704000 | 2001-09-04 | 2002-09-03 | 2004-12-03 | GI | M | Manhattan Team | 14.3992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 822 | 329.8%
M130-399A1 | (PLUMBING) EAST 54TH ST. RECREATION CTR | 2000-12-31 | 2001-02-20 | 1998-10-30 | 103000 | 103000 | 2001-09-04 | 2002-09-03 | 2004-10-01 | GI | M | Manhattan Team | 11.5425 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 759 | 0%
M130-499A1 | (HVAC) EAST 54TH ST. RECREATION CTR | 2000-12-31 | 2001-02-20 | 1998-10-30 | 1115237 | 1115000 | 2001-09-04 | 2002-09-03 | 2005-11-04 | GI | M | Manhattan Team | 13.9246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1158 | -0.02125%
M131-101M | HANSBOROUGH REC. CTR. - DEHUMIDIFICATION SYSTEM | 2001-03-05 | 2001-04-13 | 2000-08-28 | 516485 | 675000 | 2001-09-10 | 2002-06-06 | 2003-08-26 | GI | TS | Technical Services (Randalls Isl.) | 13.1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 446 | 30.69%
M131-104M/304M | HANSBOROUGH REC CENTER - CONSTR OF COMPUTER RESOURCE CTR | 2004-09-15 | 2004-09-15 | 2004-04-01 | 120100 | 720000 | 2005-10-24 | 2006-02-20 | 2006-10-02 | GI | M | Manhattan Team | 11.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 224 | 499.5%
M131-196A/396 | HANSBOROUGH REC. CTR. | 1996-04-19 | 1996-07-08 | 1996-03-27 | 763000 | 1414000 | 1997-01-20 | 1998-01-14 | 1998-06-10 | GI | CPM | Construction Project Manager | 13.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 85.32%
M131-204M | (ELECTRICAL) HANSBOROUGH REC CENTER - CONSTR OF COMPUTER RESOURCE CTR | 2004-09-15 | 2004-03-01 | 2004-04-01 | 45500 | 45500 | 2005-10-24 | 2006-02-20 | 2006-10-02 | GI | M | Manhattan Team | 10.7255 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 224 | 0%
M131-296 | (ELECTRICAL) HANSBOROUGH REC CTR | 1996-04-19 | 1996-07-08 | 1996-03-27 | 140592 | 140592 | 1997-01-20 | 1998-01-14 | 1998-06-10 | GI | CPM | Construction Project Manager | 11.8536 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 0%
M131-304M | (MECHANICAL) HANSBOROUGH REC CENTER - CONSTR OF COMPUTER RESOURCE CTR | 2004-09-15 | 2004-03-01 | 2004-04-01 | 44928 | 44928 | 2005-10-24 | 2006-02-20 | 2006-10-27 | GI | M | Manhattan Team | 10.7128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 249 | 0%
M132-195 | LITTLE FLOWER (LAGUARDIA PLGD) PARK | 1998-12-31 | 1999-01-19 | 1994-07-28 | 948228 | 1248000 | 1999-05-24 | 2000-03-18 | 2000-02-18 | GI | M | Manhattan Team | 13.7624 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -29 | 31.61%
M144-100M | EAST RIVER PARK (JACKSON TO DELANCEY BET. FDR DRIVE & EAST RIVER) | 2001-03-22 | 2001-04-02 | 2000-03-31 | 4847460 | 6899000 | 2001-08-07 | 2002-08-06 | 2002-10-18 | GI | CPM | Construction Project Manager | 15.394 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 42.32%
M144-103M | AMPHITHEATER/EAST RIVER PARK - CONSTR. OF HANDICAPPED ACCESSIBILITY MODIFICATIONS | 2004-10-15 | 2003-04-22 | 2003-02-24 | 587884 | 750000 | 2004-01-20 | 2004-04-18 | 2005-05-24 | GI | M | Manhattan Team | 13.2843 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 401 | 27.58%
M144-199 | EAST RIVER PARK - BALLFIELD LIGHTING | 1999-01-15 | 1999-01-14 | 1998-07-28 | 197030 | 460000 | 1999-09-07 | 2000-03-04 | 2000-04-14 | GI | M | Manhattan Team | 12.1911 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 41 | 133.5%
M144-604MA | EAST RIVER PARK - AMPHITHEATER STRUCTURAL RECONSTR. | 2005-01-17 | 2005-03-11 | 2004-05-14 | 316264 | 405000 | 2006-03-27 | 2006-06-24 | 2006-08-23 | FI | M | Manhattan Team | 12.6643 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 28.06%
M155-100M | COURTNEY CALLENDER PLAYGROUND | 2000-03-08 | 2000-03-27 | 1999-07-17 | 755304 | 872000 | 2000-09-05 | 2001-05-02 | 2001-11-01 | GI | M | Manhattan Team | 13.5349 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 183 | 15.45%
M158-196 | ROBERT MOSES PLGD. | 1996-11-30 | 1997-01-02 | 1995-10-02 | 484200 | 650000 | 1997-05-12 | 1997-11-07 | 1998-05-22 | FI | M | Manhattan Team | 13.0903 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 196 | 34.24%
M159-101MA2 | FRED JOHNSON PARK - TENNIS COURTS | 2001-03-15 | 2003-04-10 | 2000-07-28 | 428762 | 583000 | 2003-08-04 | 2003-12-01 | 2004-08-26 | GI | M | Manhattan Team | 12.9687 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 269 | 35.97%
M160-105M | FRED SAMUEL PLAYGROUND | 2005-03-15 | 2005-03-25 | 2004-09-16 | 1076459 | 1493000 | 2006-03-13 | 2006-12-07 | 2007-05-02 | FI | M | Manhattan Team | 13.8892 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 146 | 38.7%
M161-100MA | MCCAFFREY PLAYGROUND | 2000-03-22 | 2000-05-26 | 1999-08-09 | 821998 | 1119000 | 2001-04-23 | 2001-10-19 | 2002-03-19 | GI | M | Manhattan Team | 13.6195 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 151 | 36.13%
M164-100M | ASSER LEVY RECREATION CTR. - HVAC UNITS | 2000-02-15 | 2000-03-13 | 1999-10-08 | 241280 | 312000 | 2000-08-14 | 2001-02-09 | 2001-06-26 | FI | TS | Technical Services (Randalls Isl.) | 12.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 137 | 29.31%
M164-104M | ASSER LEVY POOL - OUTDOOR POOLS, PAVEMENTS & SITE WORK | 2004-10-15 | 2004-10-13 | 2003-09-11 | 577000 | 834000 | 2005-04-22 | 2005-08-19 | 2005-06-24 | GI | M | Manhattan Team | 13.2656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -56 | 44.54%
M165A-104M | BARUCH PLGD - CONSTR OF SYNTH TURF FIELD |  | 2004-03-08 | 2003-10-21 | 834515 | 1055000 | 2005-03-14 | 2005-09-09 | 2005-10-24 | GI | M | Manhattan Team | 13.6346 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 26.42%
M180-197 | LT. WILLIAM TIGHE TRIANGLE - R.I.N.G. GARDEN | 1998-11-30 | 1999-02-22 | 1997-02-10 | 186403 | 235000 | 1999-06-21 | 1999-12-17 | 2000-02-09 | GI | M | Manhattan Team | 12.1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 54 | 26.07%
M191-104MA | FATHER DEMO SQUARE REHAB | 2004-09-15 | 2004-04-12 | 2003-09-11 | 977000 | 1455000 | 2005-11-14 | 2006-08-20 | 2007-05-29 | FI | M | Manhattan Team | 13.7922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 282 | 48.93%
M194-298/498 | ALFRED SMITH REC. CTR. - ELEC & MECH SYSTEMS | 1998-03-10 | 1998-03-12 | 1997-09-05 | 74628 | 543000 | 1998-07-14 | 1999-04-09 | 1999-04-08 | GI | M | Manhattan Team | 11.2203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -1 | 627.6%
M194-398 | AL SMITH REC CTR - PLUMBING SYSTEM | 1998-03-10 | 1998-03-12 | 1998-01-12 | 48000 | 48000 | 1998-07-14 | 1999-04-09 | 1999-04-08 | GI | M | Manhattan Team | 10.779 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -1 | 0%
M194-498 | AL SMITH REC CTR - H&V SYSTEM | 1998-03-10 | 1998-03-12 | 1998-01-12 | 221112 | 260000 | 1998-07-14 | 1999-04-09 | 1999-04-08 | GI | M | Manhattan Team | 12.3064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -1 | 17.59%
M200-105M | BOOKER T. WASHINGTON PARK - INSTALLATION OF SYNTH TURF & BASKETBALL CT? | 2005-02-15 | 2005-03-02 | 2004-07-07 | 591034 | 923000 | 2006-04-10 | 2006-09-06 | 2006-08-25 | GI | M | Manhattan Team | 13.2896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -12 | 56.17%
M204-197 | P.S. 133 RECREATION AREA (MOORE PLGD.) | 1997-09-17 | 1998-03-13 | 1996-10-18 | 665000 | 846000 | 1998-09-09 | 1999-04-06 | 1999-08-06 | GI | CPM | Construction Project Manager | 13.4075 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 27.22%
M206-195 | PORTION OF TANAHEY PLGD. | 1997-01-15 | 1997-04-01 | 1995-05-01 | 345405 | 433000 | 1997-07-24 | 1997-12-20 | 1998-03-13 | FI | M | Manhattan Team | 12.7525 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 83 | 25.36%
M208-106M | HARLEM RIVER PARK - BASKETBALL & HANDBALL COURTS | 2006-02-15 | 2006-03-02 | 2005-06-29 | 912322 | 1718000 | 2006-09-11 | 2007-06-12 | 2007-09-13 | FI | M | Manhattan Team | 13.7237 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 93 | 88.31%
M208-197 | HARLEM RIVER PARK/BIKEWAY BET. 135 & 139 STS. | 1999-09-30 | 1999-10-26 | 1997-07-21 | 2515510 | 3155000 | 2001-06-04 | 2002-06-03 | 2002-09-12 | GI | M | Manhattan Team | 14.738 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 101 | 25.42%
M208-206M | HARLEM RIVER PARK - CONSTR OF SYNTH TURF & RELATED SITEWORK | 2006-03-01 | 2006-02-15 | 2005-07-20 | 2997800.5 | 4099000 | 2006-09-11 | 2007-06-12 | 2007-06-28 | FI | M | Manhattan Team | 14.9134 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 36.73%
M219-197 | P.S. 87 (TECUMSEH) PLGD. | 1998-01-31 | 1998-02-09 | 1996-10-15 | 588229 | 746000 | 1998-06-22 | 1999-02-01 | 1999-02-01 | FI | M | Manhattan Team | 13.2849 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26.82%
M220-102M | FREDERICK DOUGLASS PLGD - SYNTHETIC TURF |  | 2003-03-18 | 2003-03-04 | 598830 | 875000 | 2003-07-21 | 2004-01-16 | 2003-10-30 | GI | M | Manhattan Team | 13.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -78 | 46.12%
M220-206M | (ELECTRICAL) FREDERICK DOUGLASS PLGD - CONSTR OF IN-GROUND MINI POOL |  | 2006-02-28 | 2005-09-19 | 36840 | 37000 | 2007-07-09 | 2008-04-03 | 2008-03-28 | FI | M | Manhattan Team | 10.5143 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -6 | 0.4343%
M221-198 | NEW YORK SCHOOL OF PRINTING (GUTENBERG PLGD) | 1999-09-15 | 1999-10-29 | 1998-05-26 | 464191 | 667000 | 2000-04-03 | 2000-07-31 | 2000-09-26 | GI | M | Manhattan Team | 13.0481 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 57 | 43.69%
M223-103M | JACOB SCHIFF PLAYGROUND (M223) - SYNTHETIC TURF | 2002-03-15 | 2003-03-12 | 2002-12-13 | 660709 | 928000 | 2003-06-30 | 2003-12-26 | 2004-04-26 | GI | M | Manhattan Team | 13.4011 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 122 | 40.46%
M225-104M | WAGNER PLGD - CONSTR OF MULTI-USE SYNTH TURF & RECONSTR OF HANDBALL CTS |  | 2004-03-16 | 2003-11-25 | 1148369 | 1513000 | 2004-08-23 | 2005-02-18 | 2005-03-18 | GI | M | Manhattan Team | 13.9539 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 31.75%
M227-198 | PETER'S FIELD - JHS 104 | 1998-02-28 | 1998-02-02 | 1997-09-22 | 387045 | 512000 | 1998-05-12 | 1998-10-08 | 1998-10-08 | GI | M | Manhattan Team | 12.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 32.28%
M229-199 | HAPPY WARRIOR (P.S. 163) PLAYGROUND | 1999-11-22 | 1999-12-03 | 1999-05-11 | 915670 | 1106000 | 2000-08-14 | 2001-04-10 | 2001-07-06 | GI | M | Manhattan Team | 13.7274 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 87 | 20.79%
M233-101M | PS 199 (SEVENTIETH) PLGD FOR ALL CHILDREN & C.S. | 2001-12-30 | 2002-02-06 | 2001-05-22 | 758728 | 1167000 | 2002-07-29 | 2003-04-24 | 2003-06-05 | GI | M | Manhattan Team | 13.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 42 | 53.81%
M236-103MA | SAMUEL SEABURY PLAYGROUND | 2004-03-02 | 2004-06-02 | 2003-04-09 | 1164733.5 | 1433000 | 2005-01-24 | 2005-11-19 | 2006-03-09 | GI | M | Manhattan Team | 13.968 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 110 | 23.03%
M245-199 | P.S. 194 PLAYGROUND - BASKETBALL CT. | 1999-04-18 | 1999-04-19 | 1998-11-04 | 268058 | 395000 | 1999-08-16 | 2000-02-11 | 2000-03-08 | GI | CPM | Construction Project Manager | 12.499 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 47.36%
M259-196 | MCKINLEY PLGD. @ P.S.63 | 1997-02-03 | 1997-03-28 | 1996-04-22 | 278686 | 321000 | 1997-07-24 | 1997-12-20 | 1998-04-22 | GI | M | Manhattan Team | 12.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 123 | 15.18%
M264-193T | P.S. 166 PLGD. | 1998-04-30 | 1998-12-15 | 1998-12-14 | 831570 | 1102000 | 1999-06-01 | 2000-05-30 | 2000-09-29 | GI | M | Manhattan Team | 13.6311 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 122 | 32.52%
M277-103M | HELL'S KITCHEN PARK RECONSTRUCTION | 2003-03-31 | 2004-04-19 | 2002-10-16 | 954944 | 1266000 | 2004-09-07 | 2005-06-03 | 2005-11-03 | GI | M | Manhattan Team | 13.7694 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 153 | 32.57%
M280-102MA1 | TRAMWAY PLAZA | 2005-10-15 | 2005-08-09 | 2002-01-03 | 621735 | 779000 | 2006-05-30 | 2007-01-24 | 2007-02-23 | GI | M | Manhattan Team | 13.3403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 25.29%
M285-104M | MCNAIR PARK - CONSTRUCTION OF | 2005-03-15 | 2005-03-15 | 2004-06-30 | 1369085 | 1868000 | 2005-10-04 | 2006-07-04 | 2006-10-18 | FI | M | Manhattan Team | 14.1297 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 106 | 36.44%
M286-100M | ASPHALT GREEN - MURPHY CENTER ADDITIONS | 2000-11-30 | 2000-10-20 | 2000-02-15 | 4535000 | 5650000 | 2001-03-08 | 2004-03-06 | 2002-02-04 | GI | SS | Other | 15.3273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -761 | 24.59%
M294-100M | RUPPERT PARK - SECURITY LIGHTING SYSTEM | 1999-10-29 | 1999-12-08 | 1999-08-31 | 77940 | 95000 | 2000-05-15 | 2000-11-10 | 2000-08-31 | GI | M | Manhattan Team | 11.2637 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -71 | 21.89%
M294-101MA | RUPPERT PARK - IRRIGATION & FENCING - CONSTR OF |  | 2004-01-30 | 2000-09-07 | 480665 | 690000 | 2004-11-29 | 2005-05-27 | 2005-09-13 | GI | M | Manhattan Team | 13.0829 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 109 | 43.55%
M296-101M | W. 132 ST. BLOCK ASSOC. COMMUNITY GARDEN - WATER SYSTEM | 2000-10-15 | 2000-11-16 | 2000-08-17 | 48700 | 77000 | 2001-05-14 | 2001-09-10 | 2001-07-18 | GI | M | Manhattan Team | 10.7934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -54 | 58.11%
M308-103M | WASHINGTON MARKET PARK @ GREENWICH & CHAMBERS - PLAY EQUIPMET | 2002-07-26 | 2002-07-26 | 2002-07-19 | 522230 | 557000 | 2003-08-11 | 2003-11-08 | 2003-11-21 | GI | M | Manhattan Team | 13.1659 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 6.658%
M313-101M | 6BC BOTANICAL GARDEN - WATER SERVICE | 2001-08-15 | 2001-05-22 | 2001-02-21 | 60981 | 132000 | 2001-11-05 | 2002-03-04 | 2002-05-23 | GI | M | Manhattan Team | 11.0183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 80 | 116.5%
M318-101M | MERCHANTS HOUSE MUSEUM - EAST WALL | 2000-12-31 | 2000-12-14 | 2000-07-27 | 82000 | 90000 | 2001-11-28 | 2002-08-24 | 2002-08-28 | FI | SS | Other | 11.3145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9.756%
MG-1000MA | BOILERS & HEATING SYSTEMS AT MANHATTAN FACILITIES | 2001-01-15 | 2001-04-11 | 2000-07-03 | 462800 | 622000 | 2001-10-09 | 2002-07-05 | 2002-07-03 | GI | M | Manhattan Team | 13.0451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -2 | 34.4%
MG-1001M | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2001-07-31 | 2001-07-17 | 2001-04-25 | 500000 | 862000 | 2002-01-15 | 2002-10-11 | 2003-01-09 | FI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 90 | 72.4%
MG-1001MR | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2002-09-30 | 2002-09-30 | 2001-04-25 | 500000 | 662000 | 2003-03-17 | 2003-12-11 | 2004-05-25 | GI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 166 | 32.4%
MG-100MA | BOILERS & HEATING SYSTEMS - BORO-WIDE | 1999-11-30 | 1999-12-27 | 1999-06-22 | 489258 | 591000 | 2001-05-15 | 2001-11-10 | 2002-06-17 | GI | M | Manhattan Team | 13.1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 219 | 20.8%
MG-101M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-07-17 | 252192 | 291000 | 2001-03-12 | 2001-09-07 | 2001-08-16 | GI | T | Tree Unit | 12.4379 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -22 | 15.39%
MG-101MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-07-17 | 252192 | 331000 | 2002-03-25 | 2002-09-20 | 2002-07-15 | GI | T | Tree Unit | 12.4379 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -67 | 31.25%
MG-102M | C.B. 7 - TREE PIT GUARDS (80) & EXPANSION OF SIDEWALK TREE PITS | 2001-08-01 | 2001-08-10 | 2001-07-05 | 74318 | 113000 | 2002-06-03 | 2003-02-27 | 2002-08-19 | GI | T | Tree Unit | 11.2161 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -192 | 52.05%
MG-103M | STREET TREE PLANTING - C.B. 1 - 12 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 398450 | 489000 | 2003-03-31 | 2003-09-26 | 2003-08-14 | GI | T | Tree Unit | 12.8953 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -43 | 22.73%
MG-104MA | TREE PLANTINGS - CB 1-12 MANHATTAN |  | 2004-01-05 | 2003-08-29 | 428000 | 543000 | 2004-10-25 | 2005-07-21 | 2005-06-20 | GI | T | Tree Unit | 12.9669 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -31 | 26.87%
MG-104MAR | TREE PLANTINGS - MANHATTAN |  | 2005-07-18 | 2003-08-29 | 543000 | 597000 | 2005-10-17 | 2006-07-13 | 2006-02-07 | FI | T | Tree Unit | 13.2049 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -156 | 9.945%
MG-105M | P.E., S.S., HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 1141000 | 1800000 | 2005-08-22 | 2006-08-21 | 2006-09-14 | FI | RCU | Requirements Contract Unit | 13.9474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 24 | 57.76%
MG-105MR | P.E., S.S., HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 1141000 | 1369000 | 2006-07-10 | 2007-07-09 | 2007-09-25 | FI | RCU | Requirements Contract Unit | 13.9474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 78 | 19.98%
MG-1099 | M&O REQ. CONTRACT F/PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 1999-06-15 | 1999-06-07 | 1999-04-09 | 488700 | 605000 | 2000-01-03 | 2001-01-01 | 2001-05-02 | GI | RCU | Requirements Contract Unit | 13.0995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 121 | 23.8%
MG-1198 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-26 | 1997-09-15 | 707591 | 924000 | 1998-05-07 | 1999-05-06 | 2000-06-30 | GI | RCU | Requirements Contract Unit | 13.4696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 421 | 30.58%
MG-1199 | SIDEWALKS, PAVEMENTS, LAWNS, GREENSTREETS & SITE WORK IN VARIOUS PARKS & PLGDS. | 1999-06-30 | 1999-06-23 | 1999-04-09 | 524500 | 604000 | 1999-12-06 | 2000-12-04 | 2001-11-21 | GI | RCU | Requirements Contract Unit | 13.1702 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 352 | 15.16%
MG-1199R | SIDEWALKS, PAVEMENTS, LAWNS, GREENSTREETS & SITE WORK IN BROOKLYN | 2001-07-21 | 2001-07-21 | 2001-07-12 | 524500 | 780000 | 2001-10-05 | 2002-10-04 | 2002-04-11 | GI | RCU | Requirements Contract Unit | 13.1702 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -176 | 48.71%
MG-1299 | SIDEWALKS, PAVEMENTS, LAWNS GREENSTREETS & SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 526473 | 615000 | 2000-01-03 | 2001-01-01 | 2001-12-05 | FI | RCU | Requirements Contract Unit | 13.174 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 338 | 16.82%
MG-1299R | SIDEWALKS, PAVEMENTS, LAWNS GREENSTREETS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 526473 | 776000 | 2001-03-01 | 2002-02-28 | 2002-07-30 | FI | RCU | Requirements Contract Unit | 13.174 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 152 | 47.4%
MG-1398 | STREET TREE PLANTING F.Y. 1998 - C.B. 1-12 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 244481 | 284000 | 1998-05-11 | 1999-05-10 | 1999-04-28 | GI | T | Tree Unit | 12.4069 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -12 | 16.16%
MG-1597 | CENTRAL PARK - THE ARSENAL'S NEW PBX TELEPHONE SYSTEM | 1997-06-23 | 1997-06-23 | 1997-06-05 | 224642 | 256000 | 1997-12-13 | 1998-02-10 | 1998-03-31 | FI | TC | Other | 12.3223 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 13.96%
MG-198 | STREET TREE PLANTING F/FY 1998 | 1997-08-27 | 1997-08-27 | 1997-07-03 | 462060 | 462000 | 1997-12-01 | 1998-11-30 | 1998-11-10 | GI | T | Tree Unit | 13.0435 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -20 | -0.01299%
MG-199 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-23 | 1998-07-09 | 255887 | 279000 | 1999-03-01 | 2000-02-28 | 1999-07-29 | GI | T | Tree Unit | 12.4525 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -214 | 9.033%
MG-199R | STREET TREE PLANTING - F.Y. 2000 | 1999-08-23 | 1999-08-17 | 1998-07-09 | 255887 | 274000 | 1999-09-13 | 2000-09-11 | 2000-06-05 | GI | T | Tree Unit | 12.4525 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -98 | 7.079%
MG-200M | ARTIFICIAL TURF @ 2 SITE BALLFIELDS (M187 & M243) | 2000-03-31 | 2000-04-03 | 1999-10-05 | 1218812 | 1887000 | 2000-10-09 | 2001-10-03 | 2001-06-06 | GI | CPM | Construction Project Manager | 14.0134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -119 | 54.82%
MG-201MA | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2000-11-30 | 2000-10-16 | 2000-08-15 | 463151 | 717000 | 2001-06-20 | 2002-06-19 | 2002-10-24 | GI | RCU | Requirements Contract Unit | 13.0458 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 127 | 54.81%
MG-203M | PLAY EQUIP, S.S., HANDBALL CTS, PAVEMENTS, SIDEWALKS & SITE WORK | 2002-10-31 | 2002-09-17 | 2002-07-17 | 1350000 | 1812000 | 2003-04-21 | 2004-04-19 | 2003-12-17 | GI | RCU | Requirements Contract Unit | 14.1156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -124 | 34.22%
MG-203MR | PLAY EQUIP, S.S., HANDBALL CTS, PAVEMENTS, SIDEWALKS & SITE WORK | 2002-10-31 | 2002-09-17 | 2002-07-17 | 1112200 | 1334000 | 2004-07-12 | 2005-07-11 | 2005-08-15 | GI | RCU | Requirements Contract Unit | 13.9219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 35 | 19.94%
MG-204MA | TREE GUARD & TREE PIT UPGRADES IN CD 8 | 2003-10-31 | 2003-12-12 | 2003-08-29 | 250000 | 300000 | 2004-11-01 | 2005-07-28 | 2005-07-20 | GI | T | Tree Unit | 12.4292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -8 | 20%
MG-205M | PAVEMENTS, SIDEWALKS, WALLS & STEPS & GENERAL SITEWORK |  | 2005-03-31 | 2004-06-21 | 710000 | 840000 | 2005-08-15 | 2006-08-14 | 2006-09-14 | FI | RCU | Requirements Contract Unit | 13.473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 31 | 18.31%
MG-205MR | PAVEMENTS, SIDEWALKS, WALLS & STEPS & GENERAL SITEWORK |  | 2005-03-31 | 2004-06-21 | 710000 | 862000 | 2006-07-19 | 2007-07-18 | 2007-01-26 | FI | RCU | Requirements Contract Unit | 13.473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -173 | 21.41%
MG-207M | STREET TREES - CB 1-12 MANHATTAN |  | 2007-01-05 | 2006-09-14 | 732000 | 805000 | 2007-04-09 | 2007-10-05 | 2007-10-05 | FI | T | Tree Unit | 13.5035 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 9.973%
MG-297 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & SITEWORK | 1996-10-15 | 1996-11-07 | 1996-09-20 | 559220 | 625000 | 1997-03-03 | 1998-03-02 | 1998-12-04 | GI | RCU | Requirements Contract Unit | 13.2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 277 | 11.76%
MG-299 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 282691 | 303000 | 1999-07-06 | 2000-07-04 | 2000-03-08 | GI | T | Tree Unit | 12.5521 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -118 | 7.184%
MG-299R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 244113 | 300000 | 2000-03-13 | 2001-03-12 | 2000-07-14 | GI | T | Tree Unit | 12.4054 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -241 | 22.89%
MG-300M | FT. TRYON/INWOOD HILL/ISHAM PARKS - STEPS, PATHS, PLAZAS | 2000-01-31 | 2000-03-17 | 1999-10-06 | 556983 | 865000 | 2000-08-21 | 2001-05-17 | 2001-10-05 | FI | CPM | Construction Project Manager | 13.2303 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 55.3%
MG-301M | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2000-11-30 | 2000-11-20 | 2000-08-15 | 463151 | 614000 | 2001-05-01 | 2002-04-30 | 2003-09-02 | FI | RCU | Requirements Contract Unit | 13.0458 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 490 | 32.57%
MG-301MR | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2001-07-12 | 2001-07-12 | 2001-07-12 | 463151 | 663000 | 2002-02-15 | 2003-02-14 | 2002-09-18 | GI | RCU | Requirements Contract Unit | 13.0458 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -149 | 43.15%
MG-302M | INWOOD HILL & FT. TRYON PARKS - PATHS | 2002-01-30 | 2003-02-11 | 2001-08-14 | 494418 | 697000 | 2003-08-18 | 2003-12-15 | 2004-08-25 | GI | M | Manhattan Team | 13.1111 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 254 | 40.97%
MG-305M | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 250000 | 288000 | 2005-08-09 | 2006-08-08 | 2006-01-30 | GI | RCU | Requirements Contract Unit | 12.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -190 | 15.2%
MG-305MR | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 250000 | 300000 | 2006-07-10 | 2007-07-09 | 2007-06-20 | FI | RCU | Requirements Contract Unit | 12.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -19 | 20%
MG-306M | CB 1-12 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 426000 | 426000 | 2006-10-16 | 2007-07-12 | 2007-01-19 | FI | T | Tree Unit | 12.9622 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -174 | 0%
MG-397 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & SITEWORK | 1996-10-15 | 1996-11-07 | 1996-09-20 | 614143 | 675000 | 1997-03-10 | 1998-03-09 | 1998-03-09 | GI | RCU | Requirements Contract Unit | 13.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9.909%
MG-399 | BOILERS & HEATINGS SYSTEMS IN MANHATTAN | 1998-12-15 | 1998-12-30 | 1998-11-23 | 316035 | 364000 | 1999-07-19 | 2000-04-13 | 2000-07-05 | GI | M | Manhattan Team | 12.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 83 | 15.18%
MG-400M | PLAY EQUIP, S.S., PAVING, FENCING, LAWNS & SITE WORK | 1999-11-30 | 2000-02-08 | 1999-10-12 | 230000 | 301000 | 2000-09-05 | 2001-06-01 | 2001-06-05 | GI | RCU | Requirements Contract Unit | 12.3458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 30.87%
MG-401M | PLAY EQUIPMENT, SAFETY SURFACING, HANDBALL CTS., & SITE WORK | 2000-11-30 | 2000-11-03 | 2000-08-15 | 650000 | 1005000 | 2001-05-14 | 2002-05-13 | 2002-07-25 | GI | RCU | Requirements Contract Unit | 13.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 73 | 54.62%
MG-401MR | PLAY EQUIPMENT, SAFETY SURFACING, HANDBALL CTS., & SITE WORK | 2002-09-11 | 2002-09-11 | 2000-08-15 | 650000 | 780000 | 2003-01-06 | 2004-01-05 | 2004-06-09 | GI | RCU | Requirements Contract Unit | 13.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 156 | 20%
MG-40250-199 | LOWER EAST SIDE PARK (JHS 60) - PERIMETER FENCE & SIDEWALKS | 1999-08-30 | 1999-08-05 | 1999-05-14 | 134890 | 221000 | 2000-04-24 | 2000-08-21 | 2000-08-21 | GI | M | Manhattan Team | 11.8122 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 63.84%
MG-402M | JACOB H SHIFF (P.S.192) PLGD. | 1999-03-31 | 1999-04-16 | 1998-10-06 | 585745 | 768000 | 1999-08-16 | 2000-02-11 | 2000-05-11 | GI | M | Manhattan Team | 13.2806 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 90 | 31.12%
MG-40300-102M | CANAL ST TRIANGLE (CANAL ST, RT 9A, & WASHINGTON ST) | 2002-01-30 | 2002-12-13 | 2001-12-03 | 1726163 | 3298000 | 2003-11-03 | 2005-04-25 | 2005-06-10 | GI | M | Manhattan Team | 14.3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 46 | 91.06%
MG-40400-103M | CONSTRUCTION OF A GREENWAY @ VARIOUS LOCATIONS IN MANHATTAN PHASE I & II |  | 2003-03-26 | 2002-12-16 | 1844330 | 3115000 | 2003-06-09 | 2003-12-31 | 2003-12-31 | GI | M | Manhattan Team | 14.4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 68.9%
MG-40400-104M | MANHATTAN WATERFRONT GREENWAY - CONSTR OF SIGNAGE | 2004-11-19 | 2005-03-09 | 2004-01-06 | 209495 | 353000 | 2006-03-27 | 2006-08-23 | 2007-12-17 | FI | M | Manhattan Team | 12.2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 481 | 68.5%
MG-405M | STREET TREES - CB 1-12 MANHATTAN |  | 2004-08-05 | 2004-07-06 | 319000 | 351000 | 2005-03-28 | 2005-09-23 | 2005-08-01 | GI | T | Tree Unit | 12.6729 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -53 | 10.03%
MG-405MR | STREET TREES - CB 1-12 MANHATTAN |  | 2004-08-05 | 2004-07-06 | 578000 | 578000 | 2006-03-20 | 2006-09-15 | 2006-09-15 | FI | T | Tree Unit | 13.2673 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0%
MG-40750-106M | 369TH REGIMENT MEMORIAL - RIGGING & PLACEMENT & RELATED SITEWORK | 2005-12-15 | 2005-12-15 | 2005-07-21 | 79975 | 106000 | 2006-05-15 | 2006-09-11 | 2006-09-22 | GI | M | Manhattan Team | 11.2895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 32.54%
MG-499 | SIDEWALKS, PAVEMENTS, LAWNS, & GENERAL SITE WORK | 1999-02-12 | 1999-03-12 | 1999-01-20 | 575301 | 734000 | 1999-08-02 | 2000-04-27 | 2000-05-12 | GI | RCU | Requirements Contract Unit | 13.2626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 15 | 27.59%
MG-499R | SIDEWALKS, PAVEMENTS, & GENERAL SITE WORK | 2000-03-31 | 2000-02-11 | 1999-01-20 | 450000 | 638000 | 2000-05-08 | 2001-02-01 | 2002-03-13 | FI | RCU | Requirements Contract Unit | 13.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 405 | 41.78%
MG-501M | FENCES, GUIDERAILS, & GENERAL SITE WORK | 2000-11-30 | 2000-10-11 | 2000-08-15 | 342226 | 490000 | 2001-03-19 | 2001-12-13 | 2002-04-25 | FI | RCU | Requirements Contract Unit | 12.7432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 133 | 43.18%
MG-502M | STREET TREE PLANTING - CB 1-12 | 2002-06-30 | 2002-06-25 | 2002-04-23 | 361565 | 441000 | 2002-10-31 | 2003-07-27 | 2003-07-25 | GI | T | Tree Unit | 12.7982 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 21.97%
MG-502MR | STREET TREE PLANTING - CB 1-12 | 2002-06-30 | 2002-06-25 | 2002-04-23 | 305500 | 366000 | 2003-10-20 | 2004-07-15 | 2004-05-19 | GI | T | Tree Unit | 12.6297 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -57 | 19.8%
MG-503M | CB 1-12: SIDEWALK TREE PITS EXPANSION & INSTALLATION OF TREE PIT GUARDS | 2002-10-01 | 2003-02-05 | 2003-01-08 | 59295 | 85000 | 2004-01-05 | 2004-07-02 | 2004-04-30 | GI | T | Tree Unit | 10.9903 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -63 | 43.35%
MG-504M | STREET TREES - CB 1-12 MANHATTAN |  | 2004-05-25 | 2004-03-24 | 369000 | 405000 | 2004-11-01 | 2005-07-28 | 2005-03-31 | GI | T | Tree Unit | 12.8186 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -119 | 9.756%
MG-505M | BOILERS & HEATING SYSTEMS - MANHATTAN |  | 2005-04-05 | 2004-08-31 | 282900 | 288000 | 2006-04-03 | 2006-09-29 | 2006-11-28 | FI | M | Manhattan Team | 12.5528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 1.803%
MG-597 | SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1996-11-30 | 1996-12-05 | 1996-10-30 | 433685 | 433000 | 1997-03-17 | 1998-03-16 | 1998-03-06 | GI | RCU | Requirements Contract Unit | 12.9801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -10 | -0.1579%
MG-597R | RECONSTR. OF SIDEWALKS & PAVEMENTS - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 433685 | 537000 | 1998-01-21 | 1999-01-20 | 1999-02-17 | FI | RCU | Requirements Contract Unit | 12.9801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 28 | 23.82%
MG-599 | FENCES, GUIDERAILS, & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-09 | 1999-01-20 | 310233 | 392000 | 1999-06-14 | 2000-03-09 | 2000-05-24 | GI | RCU | Requirements Contract Unit | 12.6451 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 76 | 26.36%
MG-599R | FENCES, GUIDERAILS, & GENERAL SITE WORK | 1999-11-01 | 2000-02-10 | 1999-01-20 | 310233 | 501000 | 2000-05-08 | 2001-02-01 | 2000-10-05 | GI | RCU | Requirements Contract Unit | 12.6451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -119 | 61.49%
MG-600MA | RAPARIAN FOREST SLOPES (RIVERSIDE & INWOOD PARK) | 2001-02-09 | 2001-06-18 | 2000-05-04 | 317445 | 427000 | 2002-04-22 | 2002-10-18 | 2002-08-20 | GI | CPM | Construction Project Manager | 12.6681 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59 | 34.51%
MG-697 | RECONSTR. OF FENCES, GUIDERAILS & GENERAL SITE WORK | 1996-10-15 | 1996-10-28 | 1996-09-20 | 354174 | 354000 | 1997-03-03 | 1997-11-27 | 1998-02-09 | FI | RCU | Requirements Contract Unit | 12.7775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 74 | -0.04913%
MG-697R | CHAIN LINK FENCES, GUIDERAILS, & STEEL FENCES - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 322174 | 434000 | 1998-02-09 | 1998-11-05 | 1998-11-24 | GI | RCU | Requirements Contract Unit | 12.6828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 19 | 34.71%
MG-699 | STEEL FENCES, BEAR CLAW EXTENSIONS & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-10 | 1999-01-20 | 364933 | 447000 | 1999-06-01 | 1999-09-28 | 2000-01-11 | GI | RCU | Requirements Contract Unit | 12.8075 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 105 | 22.49%
MG-699R | MANHATTAN M&O REQ. CONTRACT F/ STEEL FENCES, BEAR CLAW, ETC. | 1999-11-01 | 1999-12-01 | 1999-01-20 | 246000 | 560000 | 2000-03-02 | 2000-06-29 | 2001-10-02 | FI | RCU | Requirements Contract Unit | 12.4131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 460 | 127.6%
MG-700M | STREET TREE PLANTING - FY 2001 | 2000-07-15 | 2000-07-13 | 2000-05-11 | 252399 | 274000 | 2000-11-03 | 2001-07-30 | 2001-04-09 | GI | T | Tree Unit | 12.4388 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -112 | 8.558%
MG-700MR | STREET TREE PLANTING - FY 2002 | 2001-06-13 | 2001-06-13 | 2000-05-11 | 246215 | 293000 | 2001-09-25 | 2002-06-21 | 2002-02-08 | GI | T | Tree Unit | 12.414 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -133 | 19%
MG-701MA | PLAY EQUIP, S.S. HANDBALL CTS. & GENERAL SITE WORK | 2001-08-31 | 2003-03-26 | 2001-04-25 | 800000 | 987000 | 2003-07-18 | 2004-07-16 | 2004-11-17 | GI | RCU | Requirements Contract Unit | 13.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 124 | 23.38%
MG-703M | LOWER MANHATTAN - VARIOUS PARKS, PLGDS, GATEWAYS | 2003-07-01 | 2003-07-17 | 2003-06-02 | 10400000 | 15867000 | 2003-11-19 | 2004-11-17 | 2005-11-02 | FI | M | Manhattan Team | 16.1573 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 350 | 52.57%
MG-798 | DOWNING PLGD & MINETTA PARK | 1997-12-15 | 1998-02-19 | 1997-09-11 | 563991 | 733000 | 1998-10-07 | 1999-04-04 | 1999-11-30 | GI | M | Manhattan Team | 13.2428 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 240 | 29.97%
MG-799 | SIDEWALKS, PAVEMENTS, LAWNS, & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-12 | 1999-01-20 | 555300 | 697000 | 1999-06-07 | 2000-03-02 | 2000-05-18 | GI | RCU | Requirements Contract Unit | 13.2273 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 77 | 25.52%
MG-799R | M & O REQ. CONTRACT F/SIDEWALKS, PAVEMENTS, LAWNS & SITEWORK | 2000-03-31 | 2000-02-11 | 1999-01-20 | 400000 | 589000 | 2000-04-17 | 2001-01-11 | 2001-07-20 | GI | RCU | Requirements Contract Unit | 12.8992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 190 | 47.25%
MG-800M | MANHATTAN FLAGPOLES (EMERGENCY) | 2000-07-30 | 2000-07-21 | 2000-05-30 | 850788 | 928000 | 2000-08-28 | 2000-12-25 | 2000-12-24 | GI | CPM | Construction Project Manager | 13.6539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 9.075%
MG-805M | INWOOD HILL & FORT TRYON PARKS - PATHS | 2005-02-25 | 2005-03-11 | 2004-11-09 | 636516.75 | 754000 | 2005-08-22 | 2006-05-18 | 2006-05-16 | GI | M | Manhattan Team | 13.3638 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -2 | 18.46%
MG-897 | PLANTING FLOWERING TREES | 1997-02-15 | 1997-02-24 | 1996-09-03 | 256988 | 257000 | 1997-05-01 | 1997-08-28 | 1998-04-14 | GI | T | Tree Unit | 12.4568 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 229 | 0.004669%
MG-898 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-23 | 1997-09-15 | 802652 | 1003000 | 1998-05-18 | 1999-05-17 | 1999-10-26 | GI | RCU | Requirements Contract Unit | 13.5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 162 | 24.96%
MG-899 | PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-09 | 1999-01-20 | 436500 | 558000 | 1999-06-14 | 2000-06-12 | 2000-05-11 | GI | RCU | Requirements Contract Unit | 12.9865 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -32 | 27.84%
MG-997A | FT. TRYON & INWOOD HILL PARKS - ASPHALT PATHS | 1997-04-03 | 1997-05-13 | 1996-12-18 | 338990 | 498000 | 1997-08-11 | 1998-01-07 | 1998-04-29 | GI | M | Manhattan Team | 12.7337 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 112 | 46.91%
MG-998 | SIDEWALKS, PATHS, PAVEMENTS AND GENERAL SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1998-03-31 | 1998-02-20 | 1997-09-15 | 684058 | 821000 | 1998-05-18 | 1999-05-17 | 1999-04-20 | GI | RCU | Requirements Contract Unit | 13.4358 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -27 | 20.02%
MG-999 | M&O REQ. CONTRACT F/PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 1999-06-15 | 1999-06-07 | 1999-04-09 | 799219 | 1045000 | 1999-11-01 | 2000-10-30 | 2001-05-02 | GI | RCU | Requirements Contract Unit | 13.5914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 184 | 30.75%
Q001-100M | ALLEY POND PARK - PROTECTIVE BARRIERS (THREE KETTLE PONDS) | 2001-01-08 | 2001-02-12 | 2000-05-11 | 144612 | 275000 | 2001-07-02 | 2001-10-29 | 2002-01-18 | GI | CPM | Construction Project Manager | 11.8818 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 90.16%
Q001-197 | ALLEY POND PARK GREENWAY | 2000-07-02 | 2001-09-25 | 1997-06-28 | 354069 | 675000 | 2002-07-15 | 2003-01-10 | 2002-12-23 | FI | CPM | Construction Project Manager | 12.7772 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18 | 90.64%
Q002-101M/401M | GROVER CLEVELAND PARK - PLAYGROUND, BALLFIELDS & C.S. | 2001-08-15 | 2001-10-01 | 2001-09-12 | 1921362 | 2719000 | 2002-07-22 | 2003-07-21 | 2004-05-13 | GI | Q | Queens Team | 14.4685 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 297 | 41.51%
Q002-201MA | (ELECTRICAL) GROVER CLEVELAND PARK - COMFORT STATION @ STANHOPE ST. | 2001-10-01 | 2002-01-10 | 2000-08-16 | 25334 | 25000 | 2002-07-22 | 2003-07-21 | 2004-05-13 | GI | Q | Queens Team | 10.1399 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 297 | -1.318%
Q002-301M | (PLUMBING) GROVER CLEVELAND PARK - COMFORT STATION @ STANHOPE ST. | 2001-08-31 | 2001-10-01 | 2000-08-16 | 145000 | 145000 | 2002-07-22 | 2003-07-21 | 2004-05-13 | GI | Q | Queens Team | 11.8845 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 297 | 0%
Q002-401M | (H&V) GROVER CLEVELAND PARK - COMFORT STATION @ STANHOPE ST. | 2001-08-31 | 2001-10-01 | 2000-08-16 | 22800 | 23000 | 2002-07-22 | 2003-07-21 | 2004-05-13 | GI | Q | Queens Team | 10.0345 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 297 | 0.8772%
Q004-100M/200M | ASTORIA PARK - NO. PLGD. C.S. & BOCCI CTS WATER FOUNTAIN | 2000-01-20 | 1999-11-18 | 1999-08-09 | 186194 | 401000 | 2000-05-08 | 2000-11-03 | 2001-01-09 | GI | Q | Queens Team | 12.1345 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 67 | 115.4%
Q004-101M | ASTORIA PARK - EROSION CONTROL & LANDSCAPING | 2001-02-12 | 2001-03-30 | 2000-11-29 | 1096401 | 1513000 | 2001-12-03 | 2002-08-29 | 2004-04-06 | GI | CPM | Construction Project Manager | 13.9075 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586 | 38%
Q004-102MA1 | ASTORIA PARK - TENNIS COURTS DRAINAGE | 2002-08-07 | 2005-05-27 | 2001-11-16 | 365105 | 583000 | 2006-04-03 | 2006-09-29 | 2006-09-20 | GI | Q | Queens Team | 12.8079 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -9 | 59.68%
Q004-197T | ASTORIA PARK - LOWER PLAYGROUND | 1996-12-31 | 1997-08-07 | 1996-09-09 | 299687 | 400000 | 1997-11-11 | 1998-04-09 | 1998-07-01 | GI | CPM | Construction Project Manager | 12.6105 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 33.47%
Q004-198;498;598 | ASTORIA PARK POOL - ELECTRICAL SYSTEMS | 1998-01-31 | 1998-04-02 | 1997-07-28 | 231600 | 428000 | 1998-09-15 | 1999-03-13 | 1999-04-29 | FI | P | Other | 12.3528 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 84.8%
Q004-199 | ASTORIA POOL - MAIN POOL STRUCTURAL RECONSTR. | 1999-02-15 | 1999-04-08 | 1998-10-21 | 1181100 | 1320000 | 1999-11-01 | 2000-05-28 | 2000-06-20 | GI | TS | Technical Services (Randalls Isl.) | 13.982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 23 | 11.76%
Q004-200M | (PLUMBING) ASTORIA PARK - NO. PLGD C.S. & BOCCIE CTS WATER FOUNTAIN | 2000-01-20 | 1999-11-30 | 1999-08-09 | 43250 | 44000 | 2000-05-08 | 2000-11-03 | 2001-01-09 | GI | Q | Queens Team | 10.6748 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 67 | 1.734%
Q004-297 | ASTORIA PK - RUNNING TRACK LIGHTING | 1997-03-31 | 1997-04-08 | 1996-12-13 | 340250 | 585000 | 1997-09-15 | 1998-03-13 | 1998-07-01 | GI | CPM | Construction Project Manager | 12.7374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 71.93%
Q004-398 | ASTORIA POOL - FILTER HOUSE H & V | 1998-01-08 | 1998-01-14 | 1997-10-23 | 392575 | 450000 | 1998-04-22 | 1998-10-18 | 1999-09-22 | FI | TS | Technical Services (Randalls Isl.) | 12.8805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 339 | 14.63%
Q004-498 | ASTORIA PARK - ELECTRICAL ROOM & POOL DECK | 1998-01-31 | 1998-04-02 | 1997-10-28 | 334600 | 363000 | 1998-09-15 | 1999-03-13 | 1999-03-05 | FI | P | Other | 12.7207 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 8.488%
Q004-598 | ASTORIA PARK POOL - MECHANICAL SYSTEMS | 1998-03-31 | 1998-04-22 | 1997-10-28 | 109200 | 109000 | 1998-09-15 | 1999-03-13 | 2000-03-28 | FI | TS | Technical Services (Randalls Isl.) | 11.6009 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 381 | -0.1832%
Q004-698 | ASTORIA PARK RUNNING TRACK | 1998-11-27 | 1999-02-11 | 1998-02-04 | 1022333 | 1427000 | 1999-08-12 | 2000-05-17 | 2000-07-22 | GI | CPM | Construction Project Manager | 13.8376 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 39.58%
Q005-100M | BAISLEY POND PK - DEMO 155TH ST.PLGD.& CONSTR OF GAZEBO & SITTING AREA | 2000-02-28 | 2000-03-30 | 1999-11-09 | 639358 | 875000 | 2000-08-28 | 2001-02-23 | 2001-07-03 | GI | CPM | Construction Project Manager | 13.3682 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 36.86%
Q005-102M | BAISLEY POND PARK - WW1 WAR MEMORIAL MONUMENT | 2002-03-31 | 2003-03-21 | 2001-11-05 | 734358 | 961000 | 2003-08-25 | 2004-05-20 | 2004-06-02 | GI | Q | Queens Team | 13.5068 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 30.86%
Q005-105M | BAISLEY POND PARK - INTERIOR PATHS | 2004-10-15 | 2005-07-21 | 2004-09-01 | 636000.5 | 750000 | 2006-08-08 | 2007-02-03 | 2006-11-29 | GI | Q | Queens Team | 13.363 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -66 | 17.92%
Q005-195 | BAISLEY POND PK. LAKE DRAINAGE & PATHS | 1996-02-28 | 1996-04-29 | 1994-09-08 | 1549504 | 1707000 | 1996-11-18 | 1997-10-13 | 1998-05-21 | GI | Q | Queens Team | 14.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 220 | 10.16%
Q005-198 | BAISLEY POND PK - LAKE VIEW OVAL PLGD. | 1998-06-30 | 1998-11-19 | 1997-11-06 | 588251 | 738000 | 1999-07-05 | 2000-02-29 | 1999-12-22 | GI | Q | Queens Team | 13.2849 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -69 | 25.46%
Q005-199 | BAISLEY POND PARK - RUNNING TRACK | 1999-03-31 | 1999-04-02 | 1998-10-02 | 621247 | 855000 | 1999-08-02 | 2000-02-27 | 2000-02-16 | GI | Q | Queens Team | 13.3395 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -11 | 37.63%
Q005-398 | (ELECTRICAL) BAISLEY POND PARK COMFORT STATION | 1999-01-29 | 1999-01-26 | 1997-10-16 | 21995 | 22000 | 1999-09-13 | 2000-07-08 | 2000-07-11 | GI | Q | Queens Team | 9.9986 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0.02273%
Q005-498 | (PLUMBING) BAISLEY POND PARK COMFORT STATION | 1999-01-29 | 1999-01-26 | 1997-10-16 | 98249 | 109000 | 1999-09-13 | 2000-07-08 | 2000-07-11 | GI | Q | Queens Team | 11.4953 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 10.94%
Q005-598 | (H&V) BAISLEY POND PARK COMFORT STATION | 1999-01-29 | 1999-01-26 | 1997-10-16 | 17600 | 18000 | 1999-09-13 | 2000-07-08 | 2000-07-11 | GI | Q | Queens Team | 9.7757 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2.273%
Q005-698 | BAISLEY POND PK - 150TH ST. & ROCKAWAY BLVD PLGD. | 1998-03-31 | 1998-04-04 | 1997-12-05 | 837522 | 1004000 | 1998-09-28 | 1999-06-24 | 2000-04-20 | FI | Q | Queens Team | 13.6382 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 301 | 19.88%
Q006-103M | BOWNE PARK - AERATION SYSTEM |  | 2003-01-31 | 2002-09-06 | 180872 | 290000 | 2003-11-05 | 2004-03-03 | 2004-04-29 | GI | Q | Queens Team | 12.1055 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 57 | 60.33%
Q007-102M | BAYSWATER-MICHAELIS PARK - 2 BALLFIELDS | 2002-04-04 | 2002-09-27 | 2001-10-11 | 644594 | 875000 | 2003-05-19 | 2003-11-14 | 2003-12-18 | GI | Q | Queens Team | 13.3764 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 35.74%
Q008-105M | BROOKVILLE PARK - CONSTR OF A PLAYGROUND | 2005-05-06 | 2005-05-19 | 2004-11-17 | 627000 | 780000 | 2006-04-10 | 2007-01-04 | 2006-11-14 | GI | Q | Queens Team | 13.3487 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -51 | 24.4%
Q008-197/497 | CONSTR. OF C.S. IN BROOKVILLE PARK | 1997-03-31 | 1997-04-07 | 1996-09-06 | 387484 | 687000 | 1997-11-03 | 1998-11-02 | 1999-05-13 | GI | Q | Queens Team | 12.8674 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 192 | 77.3%
Q008-297 | (ELECTRICAL) CONSTR OF COMFORT STATION IN BROOKVILLE PARK | 1997-03-31 | 1997-03-31 | 1996-09-06 | 21000 | 21000 | 1997-11-03 | 1998-11-02 | 1999-05-13 | GI | Q | Queens Team | 9.9523 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 192 | 0%
Q008-397 | (PLUMBING) CONSTR OF COMFORT STATION IN BROOKVILLE PARK | 1997-03-31 | 1997-03-31 | 1996-09-06 | 38200 | 38000 | 1997-11-03 | 1998-11-02 | 1999-05-13 | GI | Q | Queens Team | 10.5506 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 192 | -0.5236%
Q010-297 | LITTLE BAY PARK ATHLETIC FIELDS & MISC ITEMS | 1997-03-31 | 1997-03-28 | 1996-09-09 | 434907 | 924000 | 1997-07-14 | 1998-01-09 | 1998-07-29 | GI | Q | Queens Team | 12.9829 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 201 | 112.5%
Q010-298 | LITTLE BAY PARK ROLLER HOCKEY RINK, BIKE PATHS & WATER SUPPLY | 1998-03-31 | 1998-04-27 | 1997-10-29 | 917060 | 1200000 | 1998-09-28 | 1999-05-25 | 1999-08-20 | GI | Q | Queens Team | 13.7289 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 87 | 30.85%
Q011-102MA | POPPENHUSEN PLAYGROUND | 2002-07-15 | 2003-03-20 | 2001-10-18 | 838800 | 1126000 | 2004-08-16 | 2005-05-12 | 2005-08-11 | GI | Q | Queens Team | 13.6397 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 91 | 34.24%
Q012-101M | CROCHERON PARK - SOUTH TENNIS COURTS RESTORATION |  | 2001-03-10 | 2000-08-14 | 473108 | 648000 | 2001-08-13 | 2002-01-09 | 2002-04-18 | GI | CPM | Construction Project Manager | 13.0671 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 36.97%
Q012-198 | BUZ O'ROURKE PLGD. @ 214 PL./33 RD/34 AVE. IN CROCHERON PARK | 1998-12-31 | 1998-12-30 | 1998-06-01 | 715477 | 867000 | 1999-04-19 | 1999-11-14 | 1999-09-09 | GI | Q | Queens Team | 13.4807 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -66 | 21.18%
Q012-201M | CROCHERON PARK - TWO LITTLE LEAGUE BALLFIELDS | 2001-02-26 | 2001-01-29 | 2000-08-30 | 365310 | 574000 | 2001-07-02 | 2001-11-28 | 2002-02-04 | GI | CPM | Construction Project Manager | 12.8085 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 57.13%
Q015-100M | FOREST PARK - BUDDY MONUMENT, MEMORIAL FLAGPOLE & SITEWORK | 2000-03-22 | 2000-03-29 | 1999-08-12 | 358107 | 470000 | 2001-03-26 | 2001-08-22 | 2001-12-21 | GI | CPM | Construction Project Manager | 12.7886 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 31.25%
Q015-101M | FOREST PARK - BRIDLE PATH RECONSTRUCTION | 2001-03-31 | 2001-04-05 | 2000-08-07 | 1362453 | 1905000 | 2001-08-13 | 2002-05-09 | 2002-05-09 | GI | CPM | Construction Project Manager | 14.1248 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.82%
Q015-102M | FOREST PARK - DRY HARBOR PLGD | 2002-03-29 | 2003-04-18 | 2001-11-08 | 1024489 | 1677000 | 2003-10-14 | 2004-07-09 | 2004-11-19 | GI | Q | Queens Team | 13.8397 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 133 | 63.69%
Q015-103M | FOREST PARK/OVERLOOK BUILDING - SANITARY HOUSE SEWER | 2003-01-27 | 2003-03-18 | 2002-11-12 | 131675 | 320000 | 2003-09-15 | 2004-03-12 | 2003-12-30 | GI | Q | Queens Team | 11.7881 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -73 | 143%
Q015-198A/299 | FOREST PARK - PORTIONS OF THE CAROUSEL | 1998-10-30 | 1998-11-16 | 1997-12-01 | 178800 | 295000 | 1999-11-01 | 2000-02-28 | 2000-02-28 | GI | CPM | Construction Project Manager | 12.094 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.99%
Q015-199 | FOREST PARK - KETTLE POND @ TWIN FIELDS | 1999-11-30 | 2000-02-16 | 1998-07-28 | 553933 | 793000 | 2000-09-11 | 2001-01-08 | 2001-07-13 | GI | CPM | Construction Project Manager | 13.2248 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 43.16%
Q015-200MA | FOREST PARK - SOBELSOHN PLAYGROUND | 2001-01-29 | 2001-09-04 | 2000-06-08 | 663789 | 920000 | 2002-03-01 | 2002-11-25 | 2002-08-16 | GI | CPM | Construction Project Manager | 13.4057 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101 | 38.6%
Q015-203M | FOREST PARK - VICTORY FIELD ATHLETIC FACILITIES (Q015) | 2003-03-16 | 2003-03-25 | 2002-11-21 | 1126118 | 1759000 | 2003-09-08 | 2004-05-04 | 2004-08-11 | GI | Q | Queens Team | 13.9343 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 99 | 56.2%
Q015-204M | FOREST PARK - SOBELSOHN PLAYGROUND/PORTION OF | 2005-08-01 | 2006-08-04 | 2004-05-04 | 587563.29 | 840000 | 2007-06-11 | 2008-03-06 | 2008-01-29 | FI | Q | Queens Team | 13.2837 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -37 | 42.96%
Q015-295A/495 | FOREST PARK - BANDSHELL & C.S. | 1996-12-22 | 1998-05-01 | 1995-03-29 | 2494797 | 3529000 | 1998-11-30 | 2000-03-23 | 2000-05-11 | GI | CPM | Construction Project Manager | 14.7297 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 41.45%
Q015-297 | FOREST PARK - JACKSON POND PLGD. | 1997-10-30 | 1997-12-08 | 1997-05-22 | 837429 | 1011000 | 1998-06-01 | 1999-05-31 | 1999-05-27 | GI | Q | Queens Team | 13.6381 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -4 | 20.73%
Q015-299 | (ELECTRICAL) FOREST PARK - PORTIONS OF THE CAROUSEL | 1998-10-30 | 1998-11-16 | 1997-12-01 | 24500 | 25000 | 1999-11-01 | 2000-02-28 | 2000-02-28 | GI | CPM | Construction Project Manager | 10.1064 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.041%
Q015-395 | (ELECTRICAL) FOREST PARK - BANDSHELL & C.S. | 1996-12-22 | 1998-01-26 | 1995-03-29 | 414010 | 466000 | 1998-11-30 | 2000-03-23 | 2000-05-11 | GI | CPM | Construction Project Manager | 12.9336 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 12.56%
Q015-399 | FOREST PARK - JACKSON POND - BASKETBALL CTS. | 1999-10-31 | 1999-12-17 | 1999-04-07 | 518079 | 974000 | 2000-05-22 | 2001-02-24 | 2001-02-23 | GI | CPM | Construction Project Manager | 13.1579 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 88%
Q015-495 | (MECHANICAL) FOREST PARK - BANDSHELL & C.S. | 1996-12-22 | 1998-01-26 | 1995-03-29 | 242350 | 242000 | 1998-11-30 | 2000-03-23 | 2000-05-11 | GI | CPM | Construction Project Manager | 12.3981 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | -0.1444%
Q017-104M | MARTIN'S FIELD PLGD | 2004-03-15 | 2005-03-15 | 2003-08-13 | 1049462 | 1317000 | 2005-01-24 | 2005-10-20 | 2005-12-12 | GI | Q | Queens Team | 13.8638 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 53 | 25.49%
Q017-105M | MARTINS FIELD PLGD - CENTRAL GROVE & LANDSCAPED AREAS | 2005-03-15 | 2005-03-11 | 2004-08-27 | 745162.2 | 1350000 | 2005-09-19 | 2006-09-18 | 2006-08-02 | GI | Q | Queens Team | 13.5214 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -47 | 81.17%
Q020-197 | HIGHLAND PK - TENNIS CTS. & REC. LIGHTING | 1997-01-31 | 1997-03-17 | 1996-07-12 | 1029915 | 1512000 | 1997-07-28 | 1998-04-23 | 1999-06-24 | GI | B | Brooklyn Team | 13.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427 | 46.81%
Q020-397 | HIGHLAND PK - BASEBALL FIELDS REC. LIGHTING | 1997-09-09 | 1997-09-23 | 1997-03-31 | 356139 | 489000 | 1998-01-26 | 1998-07-24 | 1998-11-19 | GI | Q | Queens Team | 12.7831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 118 | 37.31%
Q021-100M | CUNNINGHAM PARK - PONDEROSA SOCCER FIELDS | 2001-03-30 | 2001-03-30 | 1999-11-01 | 704000 | 1261000 | 2001-09-24 | 2002-02-20 | 2003-05-02 | FI | CPM | Construction Project Manager | 13.4645 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436 | 79.12%
Q021-102M/402M | CUNNINGHAM PARK - TENNIS HOUSE & COMMUNITY BLDG | 2002-09-15 | 2004-03-29 | 2002-02-04 | 1054268.5 | 2221000 | 2005-01-24 | 2006-01-23 | 2006-05-25 | GI | Q | Queens Team | 13.8684 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 122 | 110.7%
Q021-195/495 | CUNNINGHAM PK C.S. & BALLFIELDS | 1996-09-01 | 1998-04-09 | 1995-05-15 | 1017000.4 | 1395000 | 1998-09-08 | 1999-06-04 | 2000-04-07 | GI | CPM | Construction Project Manager | 13.8324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 37.17%
Q021-199 | CUNNINGHAM PARK - PORTION OF 193RD ST. PLGD. | 1999-03-27 | 1999-04-13 | 1998-07-13 | 232446 | 329000 | 1999-09-13 | 2000-01-10 | 2000-04-05 | GI | CPM | Construction Project Manager | 12.3564 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 41.54%
Q021-202M | (ELECTRICAL) CUNNINGHAM PARK - TENNIS HOUSE & COMMUNITY BLDG | 2002-09-15 | 2004-03-29 | 2002-02-04 | 89000 | 89000 | 2005-01-24 | 2006-01-23 | 2006-05-25 | GI | Q | Queens Team | 11.3964 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 122 | 0%
Q021-295 | (ELECTRICAL) CUNNINGHAM PK C.S. @ 73 AVE | 1996-09-01 | 1998-04-09 | 1995-05-15 | 24700 | 25000 | 1998-09-08 | 1999-06-04 | 2000-04-07 | GI | CPM | Construction Project Manager | 10.1146 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 1.215%
Q021-299 | CUNNINGHAM PARK - 2 BALLFIELDS RECONTR. | 1999-04-03 | 1999-04-16 | 1998-11-24 | 424845 | 564000 | 1999-08-09 | 2000-02-04 | 1999-12-10 | GI | CPM | Construction Project Manager | 12.9595 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56 | 32.75%
Q021-302M | (PLUMBING) CUNNINGHAM PARK - TENNIS HOUSE & COMMUNITY BLDG | 2002-09-15 | 2004-03-29 | 2002-02-04 | 373500 | 374000 | 2005-01-24 | 2006-01-23 | 2006-05-25 | GI | Q | Queens Team | 12.8307 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 122 | 0.1339%
Q021-395 | (PLUMBING) CUNNINGHAM PK C.S. @ 73 AVE | 1996-09-01 | 1998-04-09 | 1995-05-15 | 37200 | 37000 | 1998-09-08 | 1999-06-04 | 2000-04-07 | GI | CPM | Construction Project Manager | 10.5241 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | -0.5376%
Q021-402M | (H&V) CUNNINGHAM PARK - TENNIS HOUSE & COMMUNITY BLDG | 2002-09-15 | 2004-03-29 | 2002-02-04 | 119000 | 119000 | 2005-01-24 | 2006-01-23 | 2006-05-25 | GI | Q | Queens Team | 11.6869 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 122 | 0%
Q021-495 | (PLUMBING) CUNNINGHAM PK C.S. @ 73 AVE | 1996-09-01 | 1998-04-09 | 1995-05-15 | 15200 | 29000 | 1998-09-08 | 1999-06-04 | 2000-04-07 | GI | CPM | Construction Project Manager | 9.6291 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 90.79%
Q023-101M | (HVAC) RUFUS KING MANOR HOUSE | 2000-02-01 | 2001-01-16 | 1999-02-01 | 42000 | 42000 | 2002-05-13 | 2003-03-08 | 2003-04-23 | GI | Q | Queens Team | 10.6454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 46 | 0%
Q023-199A1/299A/101M | RUFUS KING MANOR HOUSE - MISCELLANEOUS WORK | 2001-06-08 | 2001-06-08 | 1998-10-20 | 257878.4 | 500000 | 2002-05-13 | 2005-08-31 | 2005-11-17 | GI | Q | Queens Team | 12.4602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 78 | 93.89%
Q023-205M | KING PARK - CONSTR OF SYNTH TURF & RECONSTR OF DRAINAGE SYS | 2005-02-15 | 2006-04-06 | 2005-01-24 | 1798536.6 | 2780000 | 2007-04-30 | 2008-04-28 | 2008-01-17 | FI | Q | Queens Team | 14.4025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -102 | 54.57%
Q023-299A1 | (ELECTRICAL) RUFUS KING MANOR HOUSE | 2000-02-01 | 2001-06-08 | 1999-02-01 | 42050 | 43000 | 2002-05-13 | 2003-03-08 | 2004-01-26 | GI | Q | Queens Team | 10.6466 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 324 | 2.259%
Q024-100M | KISSENA PARK - 160TH ST. & BOOTH MEMORIAL PLGD. | 2000-02-28 | 2000-03-13 | 1999-09-10 | 454800 | 668000 | 2000-10-10 | 2001-04-07 | 2001-09-06 | GI | CPM | Construction Project Manager | 13.0276 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 46.88%
Q024-101M | KISSENA PARK - 160TH ST PLGD - BASKETBALL & HANDBALL CTS. (SEVEN SEAS SPORTS CTS.) | 2001-02-09 | 2001-01-26 | 2000-08-17 | 287900 | 400000 | 2001-07-16 | 2001-12-12 | 2001-12-19 | GI | CPM | Construction Project Manager | 12.5704 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 38.94%
Q024-104MA | KISSENA PARK - CONSTR OF FOUNDATION & ADJ LANDSCAPE FOR KOREAN WAR MEMORIAL | 2004-12-15 | 2005-02-01 | 2004-04-30 | 358285 | 692000 | 2007-03-12 | 2007-09-07 | 2007-09-26 | FI | Q | Queens Team | 12.7891 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 93.14%
Q024-198 | KISSENA PARK - WEIR & RELATED DRAINAGE AT KISSENA LAKE | 1998-06-30 | 1998-06-26 | 1997-08-05 | 52551 | 101000 | 1999-02-08 | 1999-06-07 | 1999-05-19 | GI | Q | Queens Team | 10.8695 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -19 | 92.19%
Q024-199 | KISSENA PARK - BOCCI CT. & STORAGE SHED | 1998-12-31 | 1999-04-02 | 1998-11-17 | 174960 | 425000 | 1999-08-16 | 1999-12-13 | 1999-12-30 | GI | Q | Queens Team | 12.0723 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 142.9%
Q024-200MA1 | KISSENA PARK - KISSENA LAKE RESTORATION | 2001-11-01 | 2002-01-30 | 1999-12-10 | 1997903 | 2606000 | 2002-08-05 | 2003-07-30 | 2004-02-26 | GI | Q | Queens Team | 14.5076 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 211 | 30.44%
Q026-103M | LINDEN PARK - BALLFIELD RECONSTRUCTION | 2003-03-16 | 2003-04-02 | 2002-10-31 | 344004 | 507000 | 2004-01-12 | 2004-05-10 | 2004-05-10 | GI | Q | Queens Team | 12.7484 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 47.38%
Q027-198 | LAURELTON WEST BALLFIELD | 1998-02-15 | 1998-03-04 | 1997-12-05 | 387060 | 474000 | 1998-07-06 | 1999-01-01 | 1998-12-30 | GI | Q | Queens Team | 12.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -2 | 22.46%
Q029-100M | WILLIAM F. MOORE PARK - LIGHTING @ BOCCIE CT. | 1999-11-25 | 2000-01-07 | 1999-08-30 | 76853 | 106000 | 2000-09-11 | 2001-01-08 | 2001-01-04 | GI | Q | Queens Team | 11.2496 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -4 | 37.93%
Q029-199 | WILLIAM F. MOORE PARK - BOCCI CTS, PVMTS, FENCING | 2000-12-30 | 2001-01-03 | 2000-07-27 | 482158 | 674000 | 2001-09-17 | 2002-03-15 | 2002-05-10 | GI | Q | Queens Team | 13.086 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 56 | 39.79%
Q031-100M | DOUGHBOY PARK - DOUGHBOY MONUMENT SITTING AREA | 2000-10-13 | 2000-09-27 | 2000-03-05 | 137903 | 200000 | 2001-08-06 | 2001-12-03 | 2001-11-30 | GI | Q | Queens Team | 11.8343 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -3 | 45.03%
Q031-104M | WINDMULLER PARK | 2004-12-15 | 2005-05-01 | 2004-04-21 | 1596106.5 | 2104000 | 2006-02-13 | 2006-11-09 | 2007-05-01 | FI | Q | Queens Team | 14.2831 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 173 | 31.82%
Q034-100M | VETERANS MEMORIAL PLAZA @ QUEENS BLVD & 48TH ST. | 2000-09-14 | 2000-09-25 | 2000-05-11 | 377000 | 549000 | 2001-04-16 | 2001-09-12 | 2001-12-07 | GI | Q | Queens Team | 12.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 86 | 45.62%
Q040-100M | ELMJACK MALL | 2000-02-28 | 2000-03-31 | 1999-11-04 | 140600 | 412000 | 2000-10-11 | 2001-02-07 | 2001-05-04 | GI | CPM | Construction Project Manager | 11.8537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 193%
Q041-194 | NEWTOWN PLGD. & C.S. | 1996-11-30 | 1996-12-16 | 1993-07-01 | 673290 | 1035000 | 1997-07-07 | 1998-03-03 | 1998-10-27 | GI | Q | Queens Team | 13.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 238 | 53.72%
Q044-198 | NOONAN (THOMSON HILL) PLAYGROUND | 1998-12-31 | 1999-01-28 | 1997-09-07 | 564702 | 714000 | 1999-09-20 | 2000-03-17 | 2000-06-01 | GI | Q | Queens Team | 13.2441 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 76 | 26.44%
Q045-101M | JOHN ANDREWS PLAYGROUND | 2001-12-05 | 2001-12-18 | 2001-05-03 | 427000 | 600000 | 2002-07-08 | 2003-01-03 | 2003-04-25 | GI | CPM | Construction Project Manager | 12.9645 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 40.52%
Q046-197 | ALSTYNE (CORONA) PLAYGROUND | 1997-09-08 | 1997-10-06 | 1996-07-08 | 249912 | 325000 | 1998-04-01 | 1998-08-28 | 1998-12-10 | GI | Q | Queens Team | 12.4289 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 104 | 30.05%
Q051-102M | ST. ALBANS PARK - BASKETBALL, TENNIS & HANDBALL CTS. | 2002-03-05 | 2002-03-11 | 2001-10-15 | 596313 | 900000 | 2002-08-19 | 2003-02-14 | 2003-04-24 | GI | CPM | Construction Project Manager | 13.2985 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 50.93%
Q051-199 | ST. ALBAN'S PARK - PATHS & SITE WORK | 2000-02-28 | 2000-03-22 | 1998-12-28 | 662123 | 881000 | 2000-08-21 | 2001-01-17 | 2001-06-21 | GI | CPM | Construction Project Manager | 13.4032 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 33.06%
Q052-198 | CAPTAIN TILLY PARK PLGD. | 1998-03-25 | 1998-04-02 | 1997-11-17 | 377455 | 500000 | 1998-09-09 | 1999-03-07 | 1999-05-04 | GI | CPM | Construction Project Manager | 12.8412 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 32.47%
Q052-396 | (MECHANICAL) CAPT. GEORGE R. TILLY PARK COMFORT STATION | 1996-11-27 | 1996-11-27 | 1996-03-29 | 64000 | 58493 | 1997-05-19 | 1998-02-12 | 1998-05-01 | GI | CPM | Construction Project Manager | 11.0666 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | -8.605%
Q058-198 | JABEZ E. DUNNINGHAM SQUARE | 1998-11-30 | 1998-12-07 | 1998-05-29 | 142800 | 300000 | 1999-06-28 | 1999-11-24 | 1999-11-19 | GI | Q | Queens Team | 11.8692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -5 | 110.1%
Q059-198 | CATHARINE TURNER RICHARDSON PARK | 1998-03-28 | 1998-09-02 | 1997-10-24 | 187689 | 309000 | 1999-04-07 | 1999-10-03 | 1999-11-16 | GI | CPM | Construction Project Manager | 12.1425 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 64.63%
Q060-195 | BROADWAY & 76TH ST. & 41ST AVE (ELMHURST OCTAGON) TRIANGLE | 1996-12-31 | 1997-02-19 | 1995-04-03 | 147800 | 271000 | 1997-09-08 | 1998-06-04 | 1998-05-29 | GI | Q | Queens Team | 11.9036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -6 | 83.36%
Q062-197 | FLEETWOOD TRIANGLE @ PENELOPE AVE, 63 DR & WOODHAVEN BLVD. | 1997-06-23 | 1997-09-18 | 1996-11-01 | 198967 | 302000 | 1998-06-01 | 1998-11-27 | 1998-11-13 | GI | CPM | Construction Project Manager | 12.2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14 | 51.78%
Q066-101MA | HOYT PLAYGROUND - RECONSTRUCTION OF A PORTION | 2001-01-26 | 2001-05-24 | 2000-09-13 | 389355 | 612000 | 2001-12-03 | 2002-05-31 | 2002-07-24 | FI | CPM | Construction Project Manager | 12.8722 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 57.18%
Q066-198 | TRIBOROUGH BRIDGE & HOYT AVE. PLGDS. | 1998-04-01 | 1998-04-02 | 1997-11-04 | 477834 | 623000 | 1998-10-28 | 1999-04-25 | 1999-07-01 | GI | CPM | Construction Project Manager | 13.077 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 30.38%
Q082-198/498 | WAYANDA PARK COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-08-19 | 154359 | 209000 | 1998-07-06 | 1999-07-05 | 1999-07-28 | GI | Q | Queens Team | 11.947 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 35.4%
Q082-298 | (ELECTRICAL) WAYANDA PARK COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-08-19 | 9770 | 328000 | 1998-07-06 | 1999-07-05 | 1999-07-28 | GI | Q | Queens Team | 9.1871 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 3257%
Q082-398 | (PLUMBING) WAYANDA PARK COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-08-19 | 82410 | 82000 | 1998-07-06 | 1999-07-05 | 1999-07-28 | GI | Q | Queens Team | 11.3195 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | -0.4975%
Q082-498 | (H&V) WAYANDA PARK COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-08-19 | 24207 | 24000 | 1998-07-06 | 1999-07-05 | 1999-07-28 | GI | Q | Queens Team | 10.0944 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | -0.8551%
Q085-101M | GORMAN PLAYGROUND - HANDBALL & FITNESS AREA | 2001-03-31 | 2001-04-11 | 2000-08-10 | 622276 | 851000 | 2001-10-15 | 2002-04-12 | 2002-10-18 | GI | Q | Queens Team | 13.3411 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 189 | 36.76%
Q085-102MA1 | GORMAN PLAYGROUND - PRE-SCHOOL & DISTRICT HEADQUARTERS | 2002-01-15 | 2002-03-24 | 2001-10-18 | 188982 | 413000 | 2004-06-14 | 2004-12-10 | 2004-10-01 | GI | Q | Queens Team | 12.1494 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -70 | 118.5%
Q085-198 | PORTION OF GORMAN PARK PLGD. | 1998-03-31 | 1998-04-06 | 1997-09-17 | 548258 | 676000 | 1998-09-08 | 1999-03-06 | 1999-07-16 | GI | CPM | Construction Project Manager | 13.2145 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 23.3%
Q086-199 | MEMORIAL FIELD OF FLUSHING @ BAYSIDE AVE. (PORTION OF) | 1999-01-15 | 1999-02-02 | 1998-10-02 | 422074 | 548000 | 1999-09-20 | 2000-04-16 | 2000-09-08 | GI | Q | Queens Team | 12.9529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 145 | 29.84%
Q094-106M | CEDAR LANE STABLES TUDOR PARK - DRAINAGE | 2005-09-01 | 2006-02-23 | 2005-07-28 | 163025 | 250000 | 2006-08-28 | 2006-10-26 | 2006-11-29 | GI | Q | Queens Team | 12.0017 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 53.35%
Q095-101MA | LORING PARK - ATHLETIC FIELDS & PRE-FAB C.S. | 2001-02-09 | 2001-07-13 | 2000-07-24 | 918443 | 1409000 | 2002-02-04 | 2002-10-31 | 2003-04-10 | FI | CPM | Construction Project Manager | 13.7304 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 53.41%
Q096-100M | LEFFERTS PLAYGROUND RECONSTRUCTION | 2000-11-10 | 2000-10-31 | 2000-06-02 | 1030536 | 1403000 | 2001-03-28 | 2002-01-21 | 2001-10-19 | GI | Q | Queens Team | 13.8456 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -94 | 36.14%
Q096-104M | CONSTR OF SYNTH TURF IN SOUTHERN FIELDS (LEFFERTS PK) |  | 2004-03-01 | 2003-08-29 | 962403 | 1257000 | 2004-12-13 | 2005-08-09 | 2005-08-09 | GI | Q | Queens Team | 13.7772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30.61%
Q099-101M | FLUSHING MEADOW/CORONA PARK - 2 SOCCER FIELDS | 2001-01-22 | 2001-02-15 | 2000-08-02 | 1531818 | 1836000 | 2001-09-04 | 2002-08-29 | 2002-04-26 | GI | CPM | Construction Project Manager | 14.242 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -125 | 19.86%
Q099-102M | FMCP - SHEA STADIUM - INFIELD FLOODLIGHT FIXTURES ON THE ROOF | 2001-09-30 | 2001-08-06 | 2001-07-18 | 930436 | 1299000 | 2001-12-08 | 2002-09-03 | 2002-05-15 | FI | TS | Technical Services (Randalls Isl.) | 13.7434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -111 | 39.61%
Q099-103M | SHEA STADIUM - ROOFS, CATCH BASINS, MANHOLES, PVMTS, ETC. |  | 2003-06-18 | 2003-04-11 | 750000 | 900000 | 2004-03-30 | 2005-03-29 | 2005-03-28 | GI | TS | Technical Services (Randalls Isl.) | 13.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -1 | 20%
Q099-103MR | SHEA STADIUM - ROOFS, CATCH BASINS, MANHOLES, PVMTS, |  | 2003-06-18 | 2003-04-11 | 200000 | 240000 | 2005-10-28 | 2006-10-27 | 2006-10-18 | FI | TS | Technical Services (Randalls Isl.) | 12.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -9 | 20%
Q099-104M;304M | OLMSTED CENTER - PORTIONS OF | 2004-10-15 | 2006-03-21 | 2003-08-05 | 154440 | 809000 | 2007-05-29 | 2007-11-24 | 2007-11-15 | FI | Q | Queens Team | 11.9476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -9 | 423.8%
Q099-105M | SHEA STADIUM - INFRA SYS, STRUC SYS & MISC WORK |  | 2004-11-03 | 2004-07-01 | 550000 | 670000 | 2005-06-07 | 2006-06-06 | 2006-11-03 | FI | TS | Technical Services (Randalls Isl.) | 13.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 150 | 21.82%
Q099-1296 | FMCP - PEDESTRIAN CULTURAL WALK | 1996-11-30 | 1996-11-12 | 1996-05-09 | 65926 | 124000 | 1997-09-09 | 1998-01-06 | 1998-10-29 | GI | CPM | Construction Project Manager | 11.0963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 88.09%
Q099-1497 | FMCP - SHEA STADIUM ROOFS & CONCRETE & STEEL RESTORATION | 1997-03-25 | 1997-03-25 | 1997-01-10 | 1927700 | 2290000 | 1997-08-12 | 1998-05-08 | 1998-03-26 | FI | X | Bronx Team | 14.4718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43 | 18.79%
Q099-1697 | FMCP - PASSARELLE PEDESTRIAN OVERPASS - PLUMBING | 1996-12-17 | 1997-05-29 | 1997-04-29 | 108420 | 112000 | 1997-09-09 | 1998-08-14 | 1998-07-31 | GI | CPM | Construction Project Manager | 11.5938 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14 | 3.302%
Q099-197/497 | FMCP - CAROUSEL COMFORT STATION | 2000-02-01 | 2000-03-01 | 1999-09-08 | 343013 | 567000 | 2000-10-16 | 2001-10-10 | 2001-10-10 | GI | Q | Queens Team | 12.7455 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 65.3%
Q099-200M | FMCP - SHEA STADIUM - CONCRETE SURFACES & SEALER & STRUCTURAL STEEL | 1999-09-30 | 1999-09-21 | 1999-07-27 | 564079 | 800000 | 2000-02-08 | 2001-02-06 | 2001-01-17 | GI | TS | Technical Services (Randalls Isl.) | 13.2429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -20 | 41.82%
Q099-201M | FMCP - QUEENS WILDLIFE CENTER - THICK-BILLED PARROT EXHIBIT | 2002-07-05 | 2002-07-05 | 2000-08-17 | 773820 | 892000 | 2001-07-06 | 2002-07-05 | 2004-07-22 | GI | SS;Q | Other | 13.5591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748 | 15.27%
Q099-203MA/503MA | FMCP - PORTION OF THE PASSARELLE BLDG FOR THE PARKS ACADEMY |  | 2004-06-15 | 2004-05-15 | 397635 | 1316000 | 2005-12-19 | 2006-06-16 | 2007-09-13 | FI | Q | Queens Team | 12.8933 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 454 | 231%
Q099-2386 | FMCP - FLUSHING BAY PROMENADE | 1998-06-30 | 1998-12-11 | 1986-12-18 | 11387325 | 14765000 | 1999-05-01 | 2000-10-21 | 2001-11-02 | GI | Q | Queens Team | 16.248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 377 | 29.66%
Q099-296D | FMCP - CAROUSEL FIRE DETECTION/SUPPRESSION SYS. | 1998-06-30 | 1998-06-26 | 1995-09-19 | 186185 | 242000 | 1999-11-01 | 2000-04-28 | 2000-04-28 | GI | Q | Queens Team | 12.1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 29.98%
Q099-297 | (ELECTRICAL) FMCP - CAROUSEL COMFORT STATION | 2000-02-01 | 2000-03-31 | 1999-09-08 | 30450 | 31000 | 2000-10-16 | 2001-10-10 | 2001-10-10 | GI | Q | Queens Team | 10.3238 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1.806%
Q099-299 | FMCP - ILSE METZGER GROVE SEATING AREA - SIDEWALK, BENCHES, GARDEN | 1999-01-30 | 1999-04-19 | 1998-09-24 | 343120 | 350000 | 1999-08-23 | 1999-12-20 | 2000-01-19 | GI | Q | Queens Team | 12.7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 2.005%
Q099-300M | FMCP - DREDGING FLUSHING BAY & CONSTR. OF BOAT RAMP | 1999-11-15 | 1999-11-12 | 1999-09-14 | 1364445 | 1800000 | 2000-05-22 | 2000-12-07 | 2001-03-21 | GI | Q | Queens Team | 14.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 104 | 31.92%
Q099-301M | (PILES, PILES CAPS,ETC.) FMCP - POOL FACILITY & ICE HOCKEY RINK | 2000-11-30 | 2000-12-15 | 2000-09-07 | 3738500 | 3739000 | 2001-04-20 | 2001-08-17 | 2002-09-12 | FI | CR | Construction Resources | 15.1342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391 | 0.01337%
Q099-303MA | (ELECTRICAL) FMCP - PORTION OF THE PASSARELLE BLDG |  | 2004-06-15 | 2004-05-15 | 169520 | 170000 | 2005-12-19 | 2006-06-16 | 2007-03-06 | FI | Q | Queens Team | 12.0407 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 263 | 0.2832%
Q099-304M | (PLUMBING) OLMSTED CENTER - PORTIONS OF |  | 2005-09-01 | 2003-08-05 | 212000 | 212000 | 2007-05-29 | 2007-11-24 | 2007-11-15 | FI | Q | Queens Team | 12.2643 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -9 | 0%
Q099-397 | (PLUMBING) FMCP - CAROUSEL COMFORT STATION | 2000-02-01 | 2000-03-31 | 1999-09-08 | 94935 | 95000 | 2000-10-16 | 2001-10-10 | 2001-10-10 | GI | Q | Queens Team | 11.4609 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.06847%
Q099-399 | FMPC - MEADOW LAKE EAST (TRIASSIC) PLGD. | 1999-03-31 | 1999-04-19 | 1998-10-02 | 773811 | 1061000 | 1999-10-04 | 2000-03-31 | 2000-08-01 | GI | Q | Queens Team | 13.5591 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 123 | 37.11%
Q099-401M | FMCP - SHEA STADIUM - FLOODLIGHT FIXTURES | 2000-11-30 | 2001-03-19 | 2000-09-26 | 352672 | 428000 | 2001-07-30 | 2002-07-29 | 2002-05-15 | FI | TS | Technical Services (Randalls Isl.) | 12.7733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -75 | 21.36%
Q099-403MA | (PLUMBING) FMCP - PORTION OF THE PASSARELLE BLDG |  | 2004-06-14 | 2004-05-15 | 119235 | 120000 | 2005-12-19 | 2006-06-16 | 2007-03-06 | GI | Q | Queens Team | 11.6889 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 263 | 0.6416%
Q099-497 | (H&V) FMCP - CAROUSEL COMFORT STATION | 2000-02-01 | 2000-03-31 | 1999-09-08 | 17572 | 18000 | 2000-10-16 | 2001-10-10 | 2001-10-10 | GI | Q | Queens Team | 9.7741 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2.436%
Q099-498 | FMCP - JURASSIC (MEADOW LAKE WEST) PLAYGROUND | 1998-03-15 | 1998-04-15 | 1997-09-30 | 821421 | 1030000 | 1998-08-24 | 1999-03-21 | 1999-08-13 | GI | Q | Queens Team | 13.6188 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 145 | 25.39%
Q099-499A | FMCP - PLGD FOR ALL CHILDREN (PHASE I) | 2001-03-15 | 2001-03-27 | 1999-04-27 | 2721297 | 3808000 | 2002-02-11 | 2003-05-06 | 2003-12-02 | GI | CPM | Construction Project Manager | 14.8166 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 39.93%
Q099-500M | FMCP - SHEA STADIUM - ASPHALT, CONCRETE, STRUCTURAL & MISC. WORK | 2000-09-06 | 2001-02-15 | 2000-06-13 | 596940 | 772000 | 2001-07-02 | 2002-07-01 | 2002-06-25 | GI | TS | Technical Services (Randalls Isl.) | 13.2996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -6 | 29.33%
Q099-501M | FMCP - WORLD'S FAIR MARINA RESTAURANT-SEWAGE EJECTORS (EMERGENCY) | 2001-02-01 | 2001-02-01 | 2001-01-26 | 58700 | 70000 | 2001-02-12 | 2001-03-13 | 2001-03-13 | GI | Q | Queens Team | 10.9802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 19.25%
Q099-503MA | (H&V) FMCP - PORTION OF THE PASSARELLE BLDG |  | 2004-06-15 | 2004-05-15 | 335250 | 335250 | 2006-02-27 | 2006-08-25 | 2007-09-13 | FI | Q | Queens Team | 12.7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 384 | 0%
Q099-504M | SHEA STADIUM |  | 2004-01-23 | 2004-01-06 | 300000 | 360000 | 2004-07-12 | 2005-07-11 | 2004-12-28 | GI | TS | Technical Services (Randalls Isl.) | 12.6115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -195 | 20%
Q099-598A | FMCP - SHEA STADIUM - PLUMBING, PAVEMENTS, & STEEL | 1998-05-15 | 1998-06-23 | 1997-10-17 | 478800 | 611000 | 1998-11-19 | 1999-08-15 | 1999-04-06 | GI | TS | Technical Services (Randalls Isl.) | 13.079 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -131 | 27.61%
Q099-599/899 | FMCP - FORMER GERTRUDE B. EDERLE SITE - C.S. & CONCESSION PAVILION | 2000-02-28 | 2000-03-31 | 1999-06-29 | 9857019 | 13482000 | 2000-11-13 | 2002-05-13 | 2004-06-30 | GI | Q | Queens Team | 16.1037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 779 | 36.78%
Q099-601M | FLUSHING MEADOW/CORONA PARK - 3 SOCCER FIELDS | 2001-12-18 | 2001-12-27 | 2001-06-07 | 2385434 | 2736000 | 2002-11-12 | 2003-08-08 | 2003-11-20 | GI | Q | Queens Team | 14.6849 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 104 | 14.7%
Q099-695 | FMCP - CORE AREA II, PASSARELLE OVERPASS & FOUNTAIN OF FAIRS | 1996-12-17 | 1997-04-01 | 1994-11-07 | 3736190 | 5868000 | 1997-09-09 | 1999-01-01 | 2000-08-14 | GI | CPM | Construction Project Manager | 15.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591 | 57.06%
Q099-699 | (ELECTRICAL) FMCP - FORMER GERTRUDE B. EDERLE SITE - C.S. & CONCESSION PAVILION | 2000-02-28 | 2000-04-03 | 1999-06-29 | 579000 | 579000 | 2000-11-13 | 2002-05-13 | 2004-06-30 | GI | Q | Queens Team | 13.2691 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 779 | 0%
Q099-701M | FMCP - SHEA STADIUM - FIELD LEVEL SEATING, TILE, & MISC. WORK | 2001-09-07 | 2002-02-22 | 2001-06-13 | 634790 | 975000 | 2002-11-21 | 2003-11-20 | 2003-02-04 | GI | TS | Technical Services (Randalls Isl.) | 13.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -289 | 53.59%
Q099-799 | (PLUMBING) FMCP - FORMER GERTRUDE B. EDERLE SITE - C.S. & CONCESSION PAVILION | 2000-02-28 | 2000-03-31 | 1999-06-29 | 417910 | 418000 | 2000-11-13 | 2002-05-13 | 2004-06-30 | GI | Q | Queens Team | 12.943 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 779 | 0.02154%
Q099-801M | FMCP - OLMSTED CENTER - CADD & COMPUTER ELECTRICAL UPGRADE | 2001-10-15 | 2001-10-23 | 2001-06-25 | 133121 | 179000 | 2002-11-07 | 2003-03-06 | 2003-03-06 | GI | Q | Queens Team | 11.799 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 34.46%
Q099-802M | FMCP - SHEA STADIUM - INFIELD & OUTFIELD & SOUND SYSTEM | 2002-03-14 | 2002-03-14 | 2002-03-14 | 1000000 | 1000000 | 2001-12-17 | 2002-12-16 | 2003-07-28 | GI | TS | Technical Services (Randalls Isl.) | 13.8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 224 | 0%
Q099-899 | (H&V) FMCP - FORMER GERTRUDE B. EDERLE SITE - C.S. & CONCESSION PAVILION | 2000-02-28 | 2000-03-31 | 1999-06-29 | 53000 | 53000 | 2000-11-13 | 2002-05-13 | 2004-06-30 | GI | Q | Queens Team | 10.878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 779 | 0%
Q099-996 | FMCP - BOILER & MECHANICAL SYSTEMS FOR PASSARELLE BLDG. | 1996-05-31 | 1997-02-18 | 1996-04-23 | 138000 | 152000 | 1997-09-09 | 1998-01-06 | 1998-03-27 | GI | CPM | Construction Project Manager | 11.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 10.14%
Q099-998 | FMCP - OLMSTED CTR. - PORTIONS OF EXTERIOR | 1998-10-30 | 1999-01-11 | 1998-06-30 | 136469 | 216000 | 1999-08-09 | 2000-02-04 | 2000-02-04 | GI | Q | Queens Team | 11.8239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 58.28%
Q102-100M | JUNIPER VALLEY PARK - BALLFIELDS | 2000-07-17 | 2001-01-12 | 1999-07-26 | 1456485 | 2139000 | 2002-04-08 | 2002-10-04 | 2003-06-16 | GI | CPM | Construction Project Manager | 14.1915 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 46.86%
Q102-101M | JUNIPER PARK - BLEACHERS F/FIELDS 1 & 2 | 2001-03-15 | 2001-03-09 | 2000-07-28 | 73658 | 300000 | 2001-12-10 | 2002-04-08 | 2002-04-05 | GI | Q | Queens Team | 11.2072 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -3 | 307.3%
Q102-102M | JUNIPER PARK (BRENNAN FIELD) - SYNTHETIC TURF ATHLETIC FIELD | 2002-06-24 | 2002-07-25 | 2001-09-28 | 990600 | 1200000 | 2003-03-17 | 2003-07-04 | 2003-07-31 | GI | Q | Queens Team | 13.8061 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 21.14%
Q102-104MA | UPPER JUNIPER PLGD & WADING POOL RECONSTRUCTION | 2004-03-15 | 2004-03-05 | 2003-09-03 | 844611 | 1158000 | 2005-03-28 | 2005-12-22 | 2005-12-13 | GI | Q | Queens Team | 13.6466 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -9 | 37.1%
Q102-197 | JUNIPER VALLEY PK. - ROLLER HOCKEY RINK | 1998-03-31 | 1998-04-13 | 1996-12-09 | 535171 | 702000 | 1998-08-10 | 1999-02-05 | 1999-08-16 | GI | Q | Queens Team | 13.1903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 192 | 31.17%
Q102-200M | JUNIPER VALLEY PARK - WATER SERVICE | 1999-12-22 | 2000-02-09 | 1999-08-31 | 177118 | 251000 | 2000-09-11 | 2001-03-09 | 2001-08-04 | GI | CPM | Construction Project Manager | 12.0846 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 41.71%
Q102-300M | JUNIPER VALLEY PARK - BRENNAN FIELD RUNNING TRACK & BLEACHERS | 2000-03-31 | 2000-03-17 | 1999-09-28 | 1172340 | 1560000 | 2000-08-02 | 2001-04-28 | 2001-04-26 | GI | CPM | Construction Project Manager | 13.9745 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 33.07%
Q103-102M | RAYMOND O'CONNOR FIELD - SYNTHETIC TURF SOCCER FIELD | 2002-11-26 | 2002-12-18 | 2001-10-18 | 629243 | 1000000 | 2003-06-16 | 2003-10-13 | 2003-11-07 | GI | Q | Queens Team | 13.3523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 58.92%
Q104-101M/401M | QUEENSBRIDGE PARK - COMFORT STATION & SITE WORK | 2001-01-31 | 2001-03-26 | 2000-08-30 | 279450 | 692000 | 2001-09-10 | 2002-09-04 | 2002-08-22 | GI | Q | Queens Team | 12.5406 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -13 | 147.6%
Q104-196 | QUEENSBRIDGE PK BALLFIELDS | 1996-12-16 | 1997-04-01 | 1996-05-03 | 418758 | 619000 | 1997-10-14 | 1998-03-22 | 1998-07-29 | GI | Q | Queens Team | 12.945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 129 | 47.82%
Q104-199 | QUEENSBRIDGE PARK - 2 BALLFIELDS - LIGHTING | 1999-11-12 | 1999-11-19 | 1999-04-28 | 356284 | 427000 | 2000-05-15 | 2000-11-10 | 2000-11-30 | GI | Q | Queens Team | 12.7835 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 19.85%
Q104-201M | (ELECTRICAL) QUEENSBRIDGE PARK - COMFORT STATION | 2001-01-31 | 2001-03-26 | 2000-08-30 | 21166 | 37000 | 2001-09-10 | 2002-09-04 | 2002-08-22 | GI | Q | Queens Team | 9.9602 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -13 | 74.81%
Q104-301M | (PLUMBING) QUEENSBRIDGE PARK - COMFORT STATION | 2001-01-31 | 2001-03-26 | 2000-08-30 | 105287 | 105000 | 2001-09-10 | 2002-09-04 | 2002-08-22 | GI | Q | Queens Team | 11.5644 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -13 | -0.2726%
Q104-401M | (H&V) QUEENSBRIDGE PARK - COMFORT STATION | 2001-01-31 | 2001-03-26 | 2000-08-30 | 15600 | 16000 | 2001-09-10 | 2002-09-04 | 2002-08-22 | GI | Q | Queens Team | 9.655 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -13 | 2.564%
Q106-197 | DANIEL O'CONNELL PLGD. | 1997-08-18 | 1998-01-08 | 1997-12-16 | 359747 | 490000 | 1998-07-14 | 1999-01-09 | 1999-01-08 | FI | CPM | Construction Project Manager | 12.7932 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 36.21%
Q107-198 | SPRINGFIELD PARK - 184TH ST. PLAYGROUND | 1998-03-30 | 1998-04-07 | 1997-10-20 | 657473 | 816000 | 1998-09-08 | 1999-05-05 | 1999-06-30 | GI | Q | Queens Team | 13.3962 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 56 | 24.11%
Q108-197 | LAURELTON PLGD. | 1997-11-30 | 1997-12-04 | 1997-01-15 | 610647 | 714000 | 1998-08-24 | 1999-05-20 | 1999-05-20 | GI | Q | Queens Team | 13.3223 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16.93%
Q120-197 | HARVARD PLAYGROUND | 1997-10-01 | 1997-10-06 | 1996-11-20 | 715799 | 858000 | 1998-02-17 | 1998-09-14 | 1998-09-25 | GI | Q | Queens Team | 13.4812 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 19.87%
Q121-103M | KEITH WILLIAMS PARK - TRACK RECONSTRUCTION | 2003-03-15 | 2003-12-24 | 2002-11-27 | 862427 | 1150000 | 2004-09-13 | 2005-07-09 | 2005-06-23 | GI | Q | Queens Team | 13.6675 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -16 | 33.34%
Q121-197 | DET. KEITH WILLIAMS (LIBERTY) PARK - TENNIS CTS. & WATER SV. | 1997-09-30 | 1997-10-28 | 1997-05-15 | 620200 | 818000 | 1998-03-02 | 1998-10-27 | 1998-10-27 | FI | Q | Queens Team | 13.3378 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 31.89%
Q121-198/298 | LIBERTY POOL - MECHANICAL SYSTEMS | 1997-12-30 | 1998-02-09 | 1997-10-07 | 108559 | 186000 | 1998-09-15 | 1999-09-14 | 1999-09-08 | FI | TS | Technical Services (Randalls Isl.) | 11.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -6 | 71.34%
Q121-298 | LIBERTY POOL - ELECTRICAL SYSTEMS | 1997-12-30 | 1998-02-04 | 1997-10-07 | 23950 | 210000 | 1998-09-15 | 1999-09-14 | 1999-09-15 | FI | TS | Technical Services (Randalls Isl.) | 10.0837 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 776.8%
Q122-100M | JUNCTION PLAYGROUND - PLAY EQUIP & SAFETY SURFACING | 2000-02-28 | 2000-02-01 | 1999-08-11 | 357223 | 480000 | 2000-07-20 | 2000-12-16 | 2000-12-15 | GI | CPM | Construction Project Manager | 12.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 34.37%
Q129-101M | SMOKEY OVAL PLAYGROUND - BALLFIELDS | 2001-09-30 | 2001-09-30 | 2000-07-27 | 775535 | 1000000 | 2002-04-29 | 2002-10-25 | 2002-10-24 | GI | Q | Queens Team | 13.5613 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 28.94%
Q130-198 | FIVE MOTOR PARKWAY OVERPASSES (EMERGENCY) | 1998-05-15 | 1998-07-01 | 1998-04-06 | 830210 | 1072000 | 1998-08-10 | 1998-12-10 | 1998-12-10 | GI | CPM | Construction Project Manager | 13.6294 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.12%
Q131-199 | MAURICE PARK - SECURITY LIGHTING | 1999-08-15 | 1999-08-19 | 1999-03-01 | 22900 | 100000 | 2000-01-10 | 2000-04-08 | 2000-03-24 | GI | Q | Queens Team | 10.0389 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -15 | 336.7%
Q134-101M | BREININGER PARK - TOT PLAYGROUND & BALLFIELD | 2001-10-31 | 2002-03-21 | 2001-10-26 | 678563 | 1050000 | 2002-09-03 | 2003-05-30 | 2003-07-28 | GI | Q | Queens Team | 13.4277 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 59 | 54.74%
Q141-199/299 | JOHN F. MURRAY PLGD. - SECURITY LIGHTING & SPRAY SHOWER | 1999-02-28 | 1999-04-21 | 1998-07-29 | 36695 | 100000 | 2000-05-01 | 2000-08-28 | 2000-09-20 | GI | Q | Queens Team | 10.5104 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 172.5%
Q141-299A | (PLUMBING) JOHN F. MURRAY PLGD | 1999-09-30 | 1999-12-08 | 1999-04-07 | 33190 | 40000 | 2000-05-01 | 2000-08-28 | 2000-09-20 | GI | Q | Queens Team | 10.41 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 20.52%
Q162-100M | ROCKAWAY BEACH BOARDWALK - BEACH 19TH TO BEACH 126TH STS. | 2000-01-21 | 2000-02-04 | 1999-07-29 | 1002840 | 1250000 | 2000-08-01 | 2001-07-31 | 2002-03-06 | GI | R | Staten Island Team | 13.8183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 218 | 24.65%
Q162-199 | ROCKAWAY BEACH BOARDWALK - BEACH 19TH TO BEACH 72ND STS. | 1999-01-31 | 1999-03-08 | 1998-07-08 | 491839 | 650000 | 1999-07-19 | 2000-07-17 | 2000-07-17 | GI | R | Staten Island Team | 13.1059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 32.16%
Q163-101M | ROCKAWAY PARK (Q163) - B. 73RD ST. & SHOREFRONT PKWY PLGD | 2001-03-15 | 2001-03-15 | 2000-09-22 | 581821 | 761000 | 2001-08-06 | 2002-02-01 | 2002-06-06 | GI | R | Staten Island Team | 13.2739 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 125 | 30.8%
Q163-103MA | ROCKAWAY BEACH - CONSTR. OF SKATE PARK BET 91ST-92ND STS. | 2003-03-31 | 2003-06-10 | 2002-09-20 | 469634 | 773000 | 2004-01-20 | 2004-07-17 | 2004-08-05 | GI | Q | Queens Team | 13.0597 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 64.6%
Q163-198 | PARKING LOT & PLAZA @ ROCKAWAY BEACH BLVD & B94 & B95 STS. | 1998-04-01 | 1998-04-10 | 1997-08-21 | 417357 | 565000 | 1998-11-30 | 1999-08-26 | 1999-07-29 | GI | R | Staten Island Team | 12.9417 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -28 | 35.38%
Q205-198 | RECONSTR OF LITTLE BUSH (NATHAN WEIDENBAUM) PARK | 2000-03-15 | 2000-03-11 | 1997-08-14 | 839782 | 1300000 | 2000-10-30 | 2001-04-27 | 2001-06-07 | GI | CPM | Construction Project Manager | 13.6409 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 54.8%
Q207-103M | MACDONALD PARK | 2003-03-17 | 2003-12-19 | 2002-09-11 | 503939 | 891000 | 2004-08-09 | 2005-05-05 | 2005-05-20 | GI | Q | Queens Team | 13.1302 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 76.81%
Q212-197 | P.S. 164 (QUEENS VALLEY) PLGD. | 1997-06-30 | 1997-09-22 | 1996-08-22 | 146393 | 260000 | 1998-05-11 | 1998-11-06 | 1999-01-19 | GI | CPM | Construction Project Manager | 11.8941 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 77.6%
Q215-100M | ASTORIA ATHLETIC (HELLGATE) FIELDS - LIGHTING | 1999-11-20 | 1999-11-16 | 1999-08-09 | 203000 | 271000 | 2000-04-24 | 2000-10-20 | 2000-11-30 | GI | Q | Queens Team | 12.221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41 | 33.5%
Q217-103M | MCCONNELL MEMORIAL PARK | 2003-09-01 | 2004-03-09 | 2003-04-25 | 245599 | 431000 | 2004-11-08 | 2005-05-06 | 2005-05-05 | GI | Q | Queens Team | 12.4115 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 75.49%
Q218-196 | DUTCH KILLS (P.S. 112) PLAYGROUND | 1997-03-31 | 1997-03-13 | 1996-09-04 | 628690 | 762000 | 1997-07-07 | 1998-01-02 | 1998-03-04 | GI | Q | Queens Team | 13.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 61 | 21.2%
Q220-100M | DREW PARK - BASKETBALL COURTS | 2000-02-15 | 2000-03-06 | 1999-10-26 | 273974 | 386000 | 2000-08-21 | 2000-11-18 | 2000-11-29 | GI | CPM | Construction Project Manager | 12.5208 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40.89%
Q226-199 | HALLETS COVE #1 PLGD - ELECTRICAL SYSTEM FOR COMFORT STATION | 1999-02-15 | 1999-03-24 | 1998-10-28 | 13978 | 71000 | 1999-08-30 | 2000-02-25 | 2000-02-25 | GI | Q | Queens Team | 9.5452 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 407.9%
Q226-299 | HALLETS COVE #1 PLGD - PLUMBING SYSTEM FOR COMFORT STATION | 1999-02-15 | 1999-03-26 | 1998-10-28 | 77626 | 108000 | 1999-08-30 | 2000-02-25 | 2000-02-25 | GI | Q | Queens Team | 11.2597 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 39.13%
Q226-399 | HALLETS COVE #1 PLGD - H&V SYSTEM FOR COMFORT STATION | 1999-02-15 | 1999-03-26 | 1998-10-28 | 16400 | 21000 | 1999-08-30 | 2000-02-25 | 2000-02-25 | GI | Q | Queens Team | 9.705 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28.05%
Q265-197 | SCHNEIDER TRIANGLE | 1997-11-06 | 1998-03-17 | 1996-12-12 | 279115 | 345000 | 1998-07-20 | 1999-01-15 | 1998-12-28 | FI | CPM | Construction Project Manager | 12.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18 | 23.6%
Q271-101M | 111TH ST. MALLS - 48TH AVE TO 51ST AVE. | 2001-08-30 | 2001-09-18 | 2001-06-04 | 269814 | 303000 | 2002-06-03 | 2002-10-30 | 2002-10-11 | GI | Q | Queens Team | 12.5055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -19 | 12.3%
Q274-199 | GWIRTZMAN TRIANGLE RECONSTRUCTION | 1999-10-30 | 1999-11-30 | 1999-05-26 | 240241 | 300000 | 2000-05-15 | 2000-10-11 | 2000-11-01 | GI | R | Staten Island Team | 12.3894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 21 | 24.87%
Q293-100M | SAUL WEPRIN (P.S. 162) PARK PLAYGROUND RECONSTRUCTION | 2001-03-31 | 2001-03-15 | 2000-06-30 | 612451 | 800000 | 2001-07-23 | 2001-12-19 | 2002-01-03 | GI | Q | Queens Team | 13.3252 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 30.62%
Q300-100M | KISSENA CORRIDOR PARK - RACHEL CARSON PLGD. - BALLFIELD & COURT AREAS | 2000-02-22 | 2000-02-02 | 1999-09-15 | 337075 | 475000 | 2000-07-10 | 2000-12-06 | 2000-12-27 | GI | Q | Queens Team | 12.7281 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 40.92%
Q300-197 | P.S. 179 (PECK) PLGD. | 1997-06-16 | 1997-11-03 | 1996-09-25 | 327814 | 410000 | 1998-06-01 | 1998-11-27 | 1999-06-28 | GI | CPM | Construction Project Manager | 12.7002 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 25.07%
Q300-198 | KISSENA CORRIDOR PK. - PLGD. @ COLDEN & JUNIPER | 1998-12-15 | 1999-01-05 | 1997-09-03 | 485486 | 644000 | 1999-06-07 | 1999-12-03 | 1999-11-22 | GI | Q | Queens Team | 13.0929 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -11 | 32.65%
Q300-298 | KISSENA CORRIDOR PK. - UNDERHILL PLGD COURT AREAS | 1998-09-15 | 1998-09-15 | 1998-05-28 | 450150 | 584000 | 1999-03-15 | 1999-08-31 | 1999-09-09 | GI | Q | Queens Team | 13.0173 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 29.73%
Q303-103M | TRAVERS PARK - PORTION OF PLGD | 2003-03-03 | 2003-10-20 | 2003-04-16 | 373421 | 641000 | 2004-09-13 | 2005-03-11 | 2005-06-15 | GI | Q | Queens Team | 12.8305 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96 | 71.66%
Q303-198 | TRAVERS PARK C.S. UTILITIES | 1998-02-28 | 1998-04-03 | 1997-07-01 | 148889 | 218000 | 1998-09-08 | 1999-09-07 | 2000-01-19 | GI | Q | Queens Team | 11.911 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 134 | 46.42%
Q304-103M | AUSTIN STREET PLAYGROUND REHAB | 2003-03-28 | 2004-02-24 | 2002-09-30 | 617308 | 903000 | 2004-09-27 | 2005-06-23 | 2005-06-29 | GI | Q | Queens Team | 13.3331 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 46.28%
Q306-197 | MOUNT PLAYGROUND (P.S.174) | 1997-12-31 | 1998-02-03 | 1996-08-26 | 620803 | 787000 | 1998-06-08 | 1998-12-04 | 1998-12-04 | GI | Q | Queens Team | 13.3388 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 26.77%
Q306-199/499 | MOUNT PLAYGROUND - COMFORT STATION | 1999-02-28 | 1999-04-05 | 1998-10-07 | 127485 | 202000 | 1999-09-27 | 2000-05-13 | 2000-05-12 | GI | Q | Queens Team | 11.7558 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 58.45%
Q306-299 | (ELECTRICAL) MOUNT PLAYGROUND - COMFORT STATION | 1999-02-28 | 1999-04-08 | 1998-10-07 | 12961 | 13000 | 1999-09-27 | 2000-05-13 | 2000-05-12 | GI | Q | Queens Team | 9.4697 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 0.3009%
Q306-399 | (PLUMBING) MOUNT PLAYGROUND - COMFORT STATION | 1999-02-28 | 1999-04-06 | 1998-10-07 | 58514 | 59000 | 1999-09-27 | 2000-05-13 | 2000-05-12 | GI | Q | Queens Team | 10.977 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 0.8306%
Q306-499 | (H&V) MOUNT PLAYGROUND - COMFORT STATION | 1999-02-28 | 1999-04-06 | 1998-10-07 | 21420 | 22000 | 1999-09-27 | 2000-05-13 | 2000-05-12 | GI | Q | Queens Team | 9.9721 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 2.708%
Q317-100M | P.S. 46 (64TH AVE.) PLGD. - BASKETBALL CTS | 2000-02-28 | 2000-02-07 | 1999-11-03 | 249673 | 450000 | 2000-07-10 | 2001-01-05 | 2001-03-01 | GI | RCU | Requirements Contract Unit | 12.4279 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 55 | 80.24%
Q318-196 | P.S. 115 (GLEN OAKS) PLGD.DRAINAGE SYSTEM | 1997-01-02 | 1997-03-05 | 1995-10-11 | 249891 | 350000 | 1997-07-07 | 1998-01-02 | 1998-05-11 | GI | CPM | Construction Project Manager | 12.4288 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 40.06%
Q320-197 | P.S. 165 (VLEIGH) PLAYGROUND | 1997-11-30 | 1998-02-03 | 1997-06-16 | 268508 | 350000 | 1998-06-01 | 1998-10-28 | 1998-10-27 | GI | Q | Queens Team | 12.5006 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 30.35%
Q322-197 | P.S. 135 (BELLAIRE) PLAYGROUND | 1999-03-23 | 1999-04-02 | 1998-06-30 | 527900 | 625000 | 1999-08-09 | 2000-04-16 | 2000-05-18 | GI | Q | Queens Team | 13.1767 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 18.39%
Q329-102M | POMONOK (PS 201) PLGD RECONSTRUCTION | 2002-03-29 | 2003-03-24 | 2002-01-08 | 1587044 | 2071000 | 2004-05-24 | 2005-02-17 | 2005-05-11 | GI | Q | Queens Team | 14.2774 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 83 | 30.49%
Q330-198/298 | LOCUST MANOR (P.S.15) PLGD. - MECHANICAL SYSTEMS @ C.S. | 1998-03-15 | 1998-05-05 | 1997-12-17 | 151200 | 400000 | 1998-09-08 | 1999-03-06 | 1999-05-07 | GI | Q | Queens Team | 11.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 62 | 164.6%
Q330-298 | LOCUST MANOR (P.S.15) PLGD - H&V SYSTEM @ C.S. | 1998-03-15 | 1998-05-14 | 1998-05-08 | 13900 | 14000 | 1998-09-08 | 1999-03-06 | 1999-05-07 | GI | Q | Queens Team | 9.5396 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 62 | 0.7194%
Q335-102M | RUSSELL SAGE (JHS 190) PLAYGROUND | 2002-10-15 | 2003-03-14 | 2002-04-24 | 1103104 | 1212000 | 2003-10-06 | 2004-07-01 | 2004-07-23 | GI | Q | Queens Team | 13.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 9.872%
Q337-198 | FITZGERALD PLAYGROUND | 1998-04-01 | 1998-04-07 | 1997-10-24 | 468433 | 564000 | 1998-10-15 | 1999-06-11 | 1999-07-16 | GI | CPM | Construction Project Manager | 13.0571 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 20.4%
Q338-199/399/499 | SY SEPLOWE (P.S. 94) PLGD. COMFORT STATION IN ADMIRAL PARK | 1999-01-31 | 1999-03-15 | 1998-08-27 | 115670 | 207000 | 1999-09-07 | 2000-04-23 | 2000-05-12 | GI | Q | Queens Team | 11.6585 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 78.96%
Q338-399 | (PLUMBING) SY SEPLOWE (P.S. 94) PLGD. COMFORT STATION IN ADMIRAL PK | 1999-01-31 | 1999-03-15 | 1998-08-27 | 47511 | 48000 | 1999-09-07 | 2000-04-23 | 2000-05-12 | GI | Q | Queens Team | 10.7687 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1.029%
Q338-499 | (H&V) SY SEPLOWE (P.S. 94) PLGD COMFORT STATION IN ADMIRAL PK | 1999-01-31 | 1999-03-15 | 1998-08-27 | 18919 | 19000 | 1999-09-07 | 2000-04-23 | 2000-05-12 | GI | Q | Queens Team | 9.8479 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0.4281%
Q339-198 | FREDERICK CABBELL (CAMBRIA PLGD) PARK & BALLFIELDS | 1998-03-24 | 1998-03-27 | 1997-10-16 | 1229891 | 1600000 | 1998-08-03 | 1999-04-29 | 1999-05-20 | GI | Q | Queens Team | 14.0224 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 30.09%
Q342-101M/401M | ELECTRIC (ELECTCHESTER) PLAYGROUND - C.S. | 2001-01-31 | 2001-03-08 | 2000-08-30 | 315995 | 854000 | 2001-09-10 | 2002-07-06 | 2004-06-16 | GI | CPM | Construction Project Manager | 12.6635 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 170.3%
Q342-102M | ELECTRIC (ELECTCHESTER) PLAYGROUND - ASPHALT BALLFIELD | 2002-07-17 | 2002-10-15 | 2001-10-16 | 385681 | 550000 | 2003-06-23 | 2003-12-19 | 2003-12-18 | GI | Q | Queens Team | 12.8628 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 42.6%
Q342-196 | ELECTRIC (ELECTCHESTER) PLGD. | 1998-02-28 | 1998-04-07 | 1996-06-05 | 589055 | 772000 | 1998-08-03 | 1999-01-29 | 1999-01-27 | GI | Q | Queens Team | 13.2863 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -2 | 31.06%
Q342-201M | (ELECTRICAL) ELECTRIC (ELECTCHESTER) PLAYGROUND - C.S. | 2001-01-31 | 2001-03-08 | 2000-08-30 | 12840 | 13000 | 2001-09-10 | 2002-07-06 | 2004-06-16 | GI | CPM | Construction Project Manager | 9.4603 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 1.246%
Q342-301M | (PLUMBING) ELECTRIC (ELECTCHESTER) PLAYGROUND - C.S. | 2001-01-31 | 2001-03-08 | 2000-08-30 | 66825 | 67000 | 2001-09-10 | 2002-07-06 | 2004-06-16 | GI | CPM | Construction Project Manager | 11.1098 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 0.2619%
Q342-401M | (H&V) ELECTRIC (ELECTCHESTER) PLAYGROUND - C.S. | 2001-01-31 | 2001-03-07 | 2000-08-30 | 15700 | 16000 | 2001-09-10 | 2002-07-06 | 2004-06-16 | GI | CPM | Construction Project Manager | 9.6614 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 1.911%
Q343-198/498 | WHITESTONE (P.S. 193) PLGD. COMFORT STATION | 1997-12-31 | 1998-02-26 | 1997-09-09 | 247279 | 392000 | 1998-08-03 | 1999-08-02 | 1999-12-21 | GI | Q | Queens Team | 12.4183 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 141 | 58.53%
Q343-298 | (ELECTRICAL) WHITESTONE PLAYGROUND COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-09-09 | 18200 | 19000 | 1998-08-03 | 1999-08-02 | 1999-12-21 | GI | Q | Queens Team | 9.8092 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 141 | 4.396%
Q343-398 | (PLUMBING) WHITESTONE PLAYGROUND COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-09-09 | 74325 | 74000 | 1998-08-03 | 1999-08-02 | 1999-12-21 | GI | Q | Queens Team | 11.2162 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 141 | -0.4373%
Q343-498 | (H&V) WHITESTONE PLAYGROUND COMFORT STATION | 1997-12-31 | 1998-02-25 | 1997-09-09 | 15400 | 15000 | 1998-08-03 | 1999-08-02 | 1999-12-21 | GI | Q | Queens Team | 9.6421 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 141 | -2.597%
Q345-100M/400M | REDFERN PLAYGROUND - COMFORT STATION | 2000-02-28 | 2000-03-21 | 1999-09-07 | 96980 | 311000 | 2000-10-10 | 2001-05-27 | 2001-07-27 | GI | R | Staten Island Team | 11.4823 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 61 | 220.7%
Q345-198 | REDFERN HOUSES BALLFIELD | 1998-03-30 | 1998-04-04 | 1997-08-15 | 319086 | 405000 | 1998-12-15 | 1999-04-13 | 1999-07-15 | GI | R | Staten Island Team | 12.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 93 | 26.93%
Q345-200M | (ELECTRICAL) REDFERN PLAYGROUND - COMFORT STATION | 2000-02-28 | 2000-03-21 | 1999-09-07 | 6633 | 7000 | 2000-10-10 | 2001-05-27 | 2001-07-27 | GI | R | Staten Island Team | 8.7998 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 61 | 5.533%
Q345-300M | (PLUMBING) REDFERN PLAYGROUND - COMFORT STATION | 2000-02-28 | 2000-03-21 | 1999-09-07 | 31742 | 32000 | 2000-10-10 | 2001-05-27 | 2001-07-27 | GI | R | Staten Island Team | 10.3654 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 61 | 0.8128%
Q345-400M | (H&V) REDFERN PLAYGROUND - COMFORT STATION | 2000-02-28 | 2000-03-21 | 1999-09-07 | 15575 | 16000 | 2000-10-10 | 2001-05-27 | 2001-07-27 | GI | R | Staten Island Team | 9.6534 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 61 | 2.729%
Q347-101M/401M | CADWALLADER COLDEN PLGD. - COMFORT STATION | 2001-01-15 | 2001-01-18 | 2000-08-09 | 86554 | 499000 | 2001-08-21 | 2002-03-18 | 2002-04-03 | GI | Q | Queens Team | 11.3685 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 476.5%
Q347-199 | P.S. 214 (CADWALLADER COLDEN) PLGD. | 1999-12-22 | 2000-01-19 | 1999-05-03 | 912310 | 1210000 | 2000-06-26 | 2001-03-22 | 2001-04-03 | GI | Q | Queens Team | 13.7237 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 32.63%
Q347-201M | (ELECTRICAL) CADWALLADER COLDEN PLGD - COMFORT STATION | 2001-01-15 | 2001-01-18 | 2000-08-09 | 8430 | 8000 | 2001-08-21 | 2002-03-18 | 2002-04-03 | GI | Q | Queens Team | 9.0396 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | -5.101%
Q347-301M | (PLUMBING) CADWALLADER COLDEN PLGD - COMFORT STATION | 2001-01-15 | 2001-01-18 | 2000-08-09 | 37838 | 38000 | 2001-08-21 | 2002-03-18 | 2002-04-03 | GI | Q | Queens Team | 10.5411 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0.4281%
Q347-401M | (H&V) CADWALLADER COLDEN PLGD - COMFORT STATION | 2001-01-15 | 2001-01-18 | 2000-08-09 | 14525 | 15000 | 2001-08-21 | 2002-03-18 | 2002-04-03 | GI | Q | Queens Team | 9.5836 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 3.27%
Q348-100M | WILLOW LAKE (P.S. 196) PLAYGROUND | 2002-01-29 | 2002-02-25 | 2000-05-30 | 930000 | 1400000 | 2003-03-10 | 2003-12-04 | 2004-04-29 | GI | Q | Queens Team | 13.7429 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 147 | 50.54%
Q352-195 | HILLSIDE (JHS 172) PLGD. | 1996-09-30 | 1996-09-18 | 1996-07-02 | 606519 | 749000 | 1997-03-18 | 1997-12-12 | 1998-03-11 | FI | Q | Queens Team | 13.3155 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 89 | 23.49%
Q356-196 | P.S. 213 (ALLEY) PLGD. | 1998-03-27 | 1999-11-01 | 1996-06-12 | 556552 | 630000 | 2000-05-22 | 2000-11-17 | 2000-11-16 | GI | Q | Queens Team | 13.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 13.2%
Q359-197 | HAGGERTY PARK - PARTIAL RECONSTR. | 1999-11-22 | 1999-11-18 | 1997-06-18 | 518248 | 617000 | 2000-06-05 | 2000-12-01 | 2001-04-11 | GI | Q | Queens Team | 13.1582 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 131 | 19.05%
Q360-100M | TRIANGLES @ 58TH AVE/69TH ST & 57TH RD & 73RD ST./QUEENS MIDTOWN EXPWY | 2000-09-14 | 2000-09-11 | 2000-06-01 | 406690 | 600000 | 2001-03-05 | 2001-09-30 | 2001-08-29 | GI | Q | Queens Team | 12.9158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -32 | 47.53%
Q360-101M | FRONTERA PARK - RECONSTRUCTION OF PLAYGROUND | 2001-03-31 | 2001-03-30 | 2000-06-30 | 614444 | 750000 | 2001-10-22 | 2002-04-19 | 2002-05-24 | GI | Q | Queens Team | 13.3285 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 22.06%
Q360-198 | OLIVER HAZARD (HAMILTON PLACE) TRIANGLE | 1998-03-31 | 1998-04-03 | 1997-08-29 | 386000 | 513000 | 1998-10-19 | 1999-02-15 | 1999-05-13 | GI | CPM | Construction Project Manager | 12.8636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 32.9%
Q360-304M | (PLUMBING) FRONTERA PARK - CONSTR OF COMFORT STATION | 2004-03-15 | 2004-03-26 | 2003-09-12 | 97996 | 98000 | 2006-05-15 | 2007-05-09 | 2007-11-16 | FI | Q | Queens Team | 11.4927 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 191 | 0.004082%
Q360-404MA | (H&V) FRONTERA PARK - CONSTR OF COMFORT STATION | 2004-03-15 | 2004-03-26 | 2003-09-12 | 24550 | 24550 | 2006-05-15 | 2007-05-14 | 2007-11-16 | FI | Q | Queens Team | 10.1085 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 186 | 0%
Q362-100M | PLAYGROUND NINETY (PS 148) PLAYGROUND | 2000-10-31 | 2000-10-16 | 2000-04-14 | 533507 | 683000 | 2001-04-23 | 2001-10-19 | 2001-12-18 | GI | Q | Queens Team | 13.1872 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 28.02%
Q364-100M | MARIE CURIE PARK (JHS 158 PLGD.) - PORTION OF | 1999-11-30 | 1999-12-13 | 1999-07-07 | 672350 | 789000 | 2000-06-05 | 2000-12-01 | 2000-12-27 | GI | Q | Queens Team | 13.4185 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 17.35%
Q364-196 | MARIE CURIE (JHS 158) PLGD. | 1998-02-26 | 1998-03-18 | 1995-12-11 | 554591 | 738000 | 1998-08-17 | 1999-04-13 | 1999-06-02 | GI | Q | Queens Team | 13.226 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 50 | 33.07%
Q370-197 | FREEDOM SQUARE PARK | 1997-06-01 | 1997-09-16 | 1996-08-22 | 426213 | 520000 | 1998-03-23 | 1998-09-18 | 1998-09-16 | GI | CPM | Construction Project Manager | 12.9627 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 22%
Q375-199 | WILLETS POINT (PS 209) PLGD. | 2000-02-23 | 2000-02-27 | 1998-12-02 | 687006 | 1000000 | 2000-09-11 | 2001-03-09 | 2001-06-29 | GI | CPM | Construction Project Manager | 13.4401 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 45.56%
Q385-199 | DITMARS PARK COMFORT STATION - WATER SERVICE | 1998-11-15 | 1998-11-17 | 1998-09-01 | 46488 | 100000 | 1999-05-17 | 1999-08-14 | 1999-09-17 | GI | Q | Queens Team | 10.7469 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 115.1%
Q386-100M | OZONE PARK CIVIC (CENTREVILLE) PLGD - BALLFIELD & PARTIAL PLGD | 2000-02-28 | 2000-02-28 | 1999-08-12 | 714684 | 980000 | 2000-08-14 | 2001-03-11 | 2001-06-07 | GI | Q | Queens Team | 13.4796 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 88 | 37.12%
Q386-101M | CENTREVILLE PK - HANDBALL & BASKETBALL CTS, PORTION OF PLGD, SEATING PLAZA | 2001-03-15 | 2001-04-02 | 2000-09-22 | 383128 | 500000 | 2001-08-13 | 2002-02-08 | 2002-02-06 | GI | Q | Queens Team | 12.8561 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -2 | 30.5%
Q387-198/498 | BAYSIDE H.S. SOCCER FIELD & C.S. | 1998-05-05 | 1999-04-08 | 1997-11-05 | 714236 | 1013000 | 1999-08-09 | 2000-05-14 | 2000-09-21 | GI | Q | Queens Team | 13.479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 130 | 41.83%
Q387-298 | (ELECTRICAL) BAYSIDE H.S. SOCCER FIELD & C.S. | 1998-05-05 | 1999-04-08 | 1997-11-05 | 13056 | 15000 | 1999-08-09 | 2000-05-14 | 2000-09-21 | GI | Q | Queens Team | 9.477 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 130 | 14.89%
Q387-398 | (PLUMBING) BAYSIDE H.S. SOCCER FIELD & C.S. | 1998-05-05 | 1999-04-08 | 1997-11-05 | 39936 | 45000 | 1999-10-25 | 2000-07-30 | 2000-09-21 | GI | Q | Queens Team | 10.595 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 53 | 12.68%
Q387-498 | (H&V) BAYSIDE H.S. SOCCER FIELD & C.S. | 1998-05-05 | 1999-04-09 | 1997-11-05 | 15151 | 15000 | 1999-08-09 | 2000-05-14 | 2000-09-21 | GI | Q | Queens Team | 9.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 130 | -0.9966%
Q390-100M | CLINTONVILLE (JHS 194) PLAYGROUND | 2000-01-31 | 2000-02-28 | 1999-09-08 | 576038 | 800000 | 2000-09-12 | 2001-03-10 | 2001-05-07 | GI | CPM | Construction Project Manager | 13.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 38.88%
Q392-104M | IDLEWILD PARK - CONSTR OF SYNTH TURF | 2004-09-01 | 2005-03-08 | 2004-04-26 | 1088996 | 1407000 | 2005-08-22 | 2006-06-17 | 2006-04-19 | GI | Q | Queens Team | 13.9008 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -59 | 29.2%
Q398-100M | ROSEMARY'S (JHS 93-RIDGEWOOD) PLAYGROUND - ASPHALT BALLFIELD | 2000-10-30 | 2000-11-17 | 2000-08-09 | 407973 | 600000 | 2001-06-25 | 2002-03-21 | 2002-08-15 | GI | Q | Queens Team | 12.919 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 147 | 47.07%
Q398-197 | ROSEMARY'S (JHS 93-RIDGEWOOD) PLGD. | 1997-12-31 | 1998-03-09 | 1997-04-18 | 708452 | 922000 | 1998-09-08 | 1999-06-04 | 1999-05-06 | GI | Q | Queens Team | 13.4708 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -29 | 30.14%
Q400-198 | OAKLAND GARDENS (PS 203) PLGD. | 1998-11-30 | 1999-02-04 | 1997-10-17 | 701385 | 912000 | 1999-06-07 | 2000-01-02 | 1999-12-29 | GI | Q | Queens Team | 13.4608 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -4 | 30.03%
Q401-100M | LOST BATTALION HALL - AC F/GYMNASIUM | 2000-02-22 | 2000-03-09 | 1999-12-14 | 146280 | 188000 | 2000-09-18 | 2001-02-14 | 2001-04-04 | GI | Q | Queens Team | 11.8933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 49 | 28.52%
Q401-101M | LOST BATTALION HALL - ADJACENT PLAYGROUND | 2000-11-30 | 2000-11-15 | 2000-07-24 | 435017 | 568000 | 2001-04-30 | 2001-10-26 | 2002-02-01 | GI | Q | Queens Team | 12.9831 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 98 | 30.57%
Q401-196 | LOST BATTALION HALL REC.CTR. - BOILER & MECHANICAL SYSTEMS | 1997-01-31 | 1997-02-10 | 1996-04-22 | 196200 | 312000 | 1997-08-18 | 1997-12-15 | 1998-11-19 | GI | CPM | Construction Project Manager | 12.1869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 59.02%
Q401-197 | RECONSTR. OF PORTIONS OF LOST BATTALION HALL REC. CTR. | 1997-01-15 | 1997-04-08 | 1996-08-30 | 255628 | 375000 | 1997-08-18 | 1998-02-13 | 1998-04-02 | GI | CPM | Construction Project Manager | 12.4515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 46.7%
Q402-197 | MERRICK (I.S.8) PLAYGROUND | 1997-08-11 | 1997-10-28 | 1996-12-10 | 401314 | 600000 | 1998-03-16 | 1998-09-11 | 1998-10-05 | GI | CPM | Construction Project Manager | 12.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 49.51%
Q405-104M | HOLLIS PLAYGROUND/JHS 192 |  | 2004-03-18 | 2003-08-25 | 1006016.85 | 1322000 | 2004-11-29 | 2005-06-26 | 2005-10-27 | GI | Q | Queens Team | 13.8215 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 123 | 31.41%
Q410-195 | REV. HINTON PARK SITTING AREAS & EXTENSION | 1996-11-30 | 1997-01-28 | 1995-05-08 | 736450 | 912000 | 1997-06-16 | 1998-03-12 | 1998-06-23 | GI | Q | Queens Team | 13.5096 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 103 | 23.84%
Q413-101M/401M | ROCHDALE PARK - VICTOR HANSON RECREATION CTR. | 2001-02-15 | 2001-03-30 | 2000-09-18 | 529744 | 984000 | 2001-09-10 | 2002-07-06 | 2002-09-19 | GI | CPM | Construction Project Manager | 13.1801 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 85.75%
Q413-201M | (ELECTRICAL) ROCHDALE PARK - VICTOR HANSON RECREATION CTR | 2001-01-22 | 2001-03-30 | 2000-09-18 | 39994 | 40000 | 2001-09-10 | 2002-07-06 | 2002-09-19 | GI | CPM | Construction Project Manager | 10.5965 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0.015%
Q413-301M | (PLUMBING) ROCHDALE PARK - VICTOR HANSON RECREATION CTR | 2001-01-22 | 2001-03-30 | 2000-09-18 | 62128 | 62000 | 2001-09-10 | 2002-07-06 | 2002-09-19 | GI | CPM | Construction Project Manager | 11.037 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | -0.206%
Q413-401M | (HVAC) ROCHDALE PARK - VICTOR HANSON RECREATION CTR | 2001-01-22 | 2001-03-30 | 2000-09-18 | 59488 | 60000 | 2001-09-10 | 2002-07-06 | 2002-09-19 | GI | CPM | Construction Project Manager | 10.9935 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0.8607%
Q429-102MA | SPIRIT (P.S.76) PLAYGROUND | 2002-03-15 | 2003-05-29 | 2001-10-26 | 600240 | 862000 | 2004-04-12 | 2004-12-07 | 2004-12-03 | GI | Q | Queens Team | 13.3051 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -4 | 43.61%
Q430-197 | SUNRISE PLGD. (HOOK CREEK PARK) ADJ TO P.S. 195 | 1997-11-30 | 1998-01-07 | 1997-07-16 | 587665 | 749000 | 1998-05-26 | 1998-12-21 | 1999-04-13 | GI | Q | Queens Team | 13.2839 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 113 | 27.45%
Q434-197 | BELL PARK/LONG ISLAND MEWS | 1997-03-31 | 1997-04-01 | 1997-01-02 | 463813 | 670000 | 1997-09-22 | 1998-05-19 | 1998-07-22 | GI | Q | Queens Team | 13.0472 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 64 | 44.45%
Q436-100M | ATHENS SQUARE (P.S.17) PARK | 2000-09-14 | 2000-09-11 | 2000-05-17 | 179383 | 303000 | 2001-04-02 | 2001-09-28 | 2001-07-06 | GI | Q | Queens Team | 12.0973 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -84 | 68.91%
Q437-100M | MURRAY HILL (P.S.22) PLAYGROUND - FENCING & LANDSCAPING | 2000-11-15 | 2000-11-13 | 2000-06-29 | 489337 | 680000 | 2001-04-09 | 2001-10-05 | 2001-11-07 | GI | Q | Queens Team | 13.1008 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 38.96%
Q444-197 | SEANS PLACE PLGD @ 38TH ST BET 31ST AVE.& BDWY | 1997-02-28 | 1997-04-01 | 1996-11-12 | 680331 | 812000 | 1997-10-14 | 1998-05-11 | 1998-05-11 | GI | Q | Queens Team | 13.4303 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 19.35%
Q446-106M | SORRENTINO RECREATION CENTER - CONSTR OF AN ENCLOSED ADA PLATFORM LIFT | 2005-10-01 | 2005-10-01 | 2005-09-30 | 227655.33 | 690000 | 2006-09-07 | 2007-06-03 | 2007-08-27 | FI | TS | Technical Services (Randalls Isl.) | 12.3356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 85 | 203.1%
Q446-198 | SORRENTINO RECREATION CENTER - ROOF | 1997-11-30 | 1997-12-21 | 1997-07-01 | 110980 | 170000 | 1998-04-27 | 1998-08-24 | 1998-08-20 | GI | R | Staten Island Team | 11.6171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -4 | 53.18%
Q448-104M | ROY WILKINS - CONSTR OF SYNTHETIC TURF ATHLETIC FIELD | 2004-03-15 | 2004-03-02 | 2003-10-17 | 1019143 | 1317000 | 2004-09-27 | 2005-03-25 | 2005-06-30 | GI | Q | Queens Team | 13.8345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 97 | 29.23%
Q448-197A;397 | ROY WILKINS PARK - CONSTR OF C.S. | 1997-02-28 | 1997-04-08 | 1996-08-06 | 2201578 | 2856000 | 1997-10-27 | 1998-10-21 | 1999-06-18 | GI | Q | Queens Team | 14.6047 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 240 | 29.73%
Q448-199 | ROY WILKINS PARK - BLACK SPECTRUM THEATRE - PORTIONS OF | 2000-01-27 | 2000-01-27 | 1998-10-02 | 97945 | 195000 | 2000-06-19 | 2000-09-16 | 2000-09-15 | GI | Q | Queens Team | 11.4922 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 99.09%
Q448-299 | ROY WILKINS REC. CTR. - GYM FLOOR & MISCELLANEOUS WORK | 1998-02-26 | 1999-03-10 | 1998-10-01 | 128448 | 160000 | 1999-08-02 | 1999-11-14 | 1999-12-10 | GI | Q | Queens Team | 11.7633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 24.56%
Q448-397 | ROY WILKENS PK & C.S. - PLUMBING WORK | 1997-02-28 | 1997-05-02 | 1996-08-06 | 86590 | 86590 | 1997-10-27 | 1998-10-21 | 1999-06-18 | GI | Q | Queens Team | 11.3689 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 240 | 0%
Q448-398 | ROY WILKINS PARK REC - ELECTRICAL SYSTEMS | 1998-01-31 | 1998-04-09 | 1997-09-10 | 58183 | 58000 | 1998-08-10 | 1999-02-05 | 1999-06-08 | GI | Q | Queens Team | 10.9713 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 123 | -0.3145%
Q448-399 | ROY WILKINS PARK - AERATION SYSTEM @ POND | 1998-10-23 | 1998-10-23 | 1998-09-04 | 90896 | 117000 | 1999-07-06 | 1999-11-02 | 2000-03-14 | GI | Q | Queens Team | 11.4175 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 133 | 28.72%
Q448-498 | ROY WILKINS REC. CTR - MECHANICAL SYSTEMS | 1998-01-31 | 1998-04-17 | 1998-01-21 | 202020 | 379000 | 1998-08-10 | 1999-02-05 | 1999-06-08 | GI | Q | Queens Team | 12.2161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 123 | 87.61%
Q448-499 | ROY WILKINS COMMUNITY GARDENS IRRIGATION SYSTEM | 1999-07-07 | 1999-06-25 | 1998-09-13 | 152162 | 260000 | 1999-12-13 | 2000-03-11 | 2000-03-31 | GI | Q | Queens Team | 11.9327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 70.87%
Q448-597 | ROY WILKINS PARK - FOOTBALL & RUNNING TRACK LIGHTING | 1997-01-31 | 1997-02-14 | 1996-08-16 | 449300 | 595000 | 1997-06-30 | 1997-12-26 | 1998-01-16 | FI | Q | Queens Team | 13.0154 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 32.43%
Q448-699 | ROY WILKINS PARK - E. & W. BUNKER ROOFS & WATERPROOFING | 1999-01-07 | 1999-03-25 | 1998-10-23 | 127019 | 217000 | 1999-08-09 | 2000-01-05 | 1999-11-23 | GI | Q | Queens Team | 11.7521 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -43 | 70.84%
Q452-100MA | UDALLS COVE PARK & AURORA POND - RESTORATION | 2001-12-28 | 2003-04-04 | 1999-08-17 | 623259 | 1261000 | 2004-08-09 | 2005-06-04 | 2006-05-19 | GI | Q | Queens Team | 13.3427 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 349 | 102.3%
Q453-102MA | QUEENS CTY FARM MUSEUM - ADRIANCE FARMHOUSE, GREENHOUSE COMPLEX & EDUCATION BLDG | 2001-10-15 | 2002-04-30 | 2001-07-02 | 287346 | 935000 | 2003-02-18 | 2003-10-15 | 2004-02-11 | GI | Q | Queens Team | 12.5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 119 | 225.4%
Q453-197 | QUEENS COUNTY FARM MUSEUM - COW BARN & FURNISHINGS | 1997-02-15 | 1998-08-10 | 1996-08-20 | 145000 | 150000 | 1999-06-01 | 2000-05-30 | 2000-07-17 | FI | A;QFM | Other | 11.8845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 3.448%
Q453-202M | QUEENS COUNTY FARM MUSEUM - NEW WINDMILL, ROADWAY, LIGHTING & UTILITIES | 2002-03-29 | 2003-04-30 | 2002-02-07 | 438572 | 764000 | 2004-05-10 | 2005-03-05 | 2005-03-11 | GI | Q | Queens Team | 12.9913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 74.2%
Q453-297 | QUEENS COUNTY FARM MUSEUM - HORSE BARN & FURNISHINGS | 1998-12-15 | 1998-12-28 | 1996-08-21 | 98000 | 160000 | 1999-03-01 | 1999-11-25 | 2002-10-02 | FI | A | Architecture | 11.4927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 63.27%
Q456-102M | GENE GRAY PLAYGROUND | 2002-03-29 | 2002-04-30 | 2001-10-15 | 464960 | 623000 | 2003-03-17 | 2003-08-13 | 2003-07-30 | GI | Q | Queens Team | 13.0497 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -14 | 33.99%
Q458-101M | FT. TOTTEN - PORTIONS OF THE BATTERY | 2001-12-19 | 2003-04-10 | 2000-09-07 | 599579 | 935000 | 2004-02-23 | 2005-02-16 | 2005-08-17 | GI | Q | Queens Team | 13.304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 182 | 55.94%
Q458-105M/305M | FORT TOTTEN MUSEUM (BUILDING 502) - ROOF & BATHROOM | 2005-03-15 | 2005-06-20 | 2004-09-08 | 810354 | 980000 | 2006-11-06 | 2007-06-03 | 2007-06-29 | FI | Q | Queens Team | 13.6052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 20.93%
Q458-205M | (ELECTRICAL) FORT TOTTEN MUSEUM (BUILDING 502) - ROOF & BATHROOM | 2005-03-15 | 2005-06-20 | 2005-06-20 | 34705.84 | 35000 | 2007-01-16 | 2007-08-13 | 2007-06-29 | FI | Q | Queens Team | 10.4547 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -45 | 0.8476%
Q458-305M | (PLUMBING) FORT TOTTEN MUSEUM (BUILDING 502) - ROOF & BATHROOM | 2005-03-15 | 2005-06-20 | 2005-06-20 | 47840 | 48000 | 2007-01-02 | 2007-07-30 | 2007-06-29 | FI | Q | Queens Team | 10.7756 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -31 | 0.3344%
Q458-307M | FORT TOTTEN - REMOVAL/DISPOSAL OF ASBESTOS-CONTAINING MATERIALS IN 22 BLDGS |  | 2007-01-24 | 2006-12-18 | 421200 | 568000 | 2007-09-17 | 2008-04-03 | 2008-01-11 | FI | EN | Environmental Control Unit | 12.9509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -83 | 34.85%
Q461-198 | POWELL'S COVE MARSH | 1999-01-15 | 1999-03-03 | 1998-05-18 | 1645294 | 2165000 | 1999-08-02 | 2000-07-31 | 2000-10-17 | GI | Q | Queens Team | 14.3134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 78 | 31.59%
Q465-198 | SOCRATES SCULPTURE PARK - SIDEWALKS & FENCING | 1998-03-15 | 1998-03-16 | 1997-09-18 | 122000 | 223000 | 1998-07-06 | 1998-11-02 | 1999-01-08 | GI | CPM | Construction Project Manager | 11.7118 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 82.79%
Q467-102M | BROAD CHANNEL PARK - ATHLETIC FIELDS & LANDSCAPING | 2003-03-10 | 2004-04-09 | 2001-10-18 | 998458 | 1723000 | 2004-11-29 | 2005-11-23 | 2005-11-03 | GI | Q | Queens Team | 13.814 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -20 | 72.57%
Q467-199 | BROAD CHANNEL PARK - BALLFIELD & WETLANDS | 1999-03-31 | 1999-04-22 | 1998-10-06 | 868397 | 973000 | 1999-10-04 | 2000-06-29 | 2000-07-11 | GI | Q | Queens Team | 13.6744 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 12.05%
Q467-298 | BROAD CHANNEL PARK - ASBESTOS REMOVAL & DEMO OF BLDG. | 1997-12-30 | 1997-12-21 | 1997-12-02 | 548000 | 704000 | 1998-05-04 | 1998-08-01 | 1998-07-30 | GI | Q | Queens Team | 13.214 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -2 | 28.47%
Q470-198/398 | ARROW PARK COMMUNITY CTR. | 1998-03-30 | 1998-05-05 | 1997-09-04 | 397179 | 800000 | 1998-11-30 | 1999-11-24 | 2000-05-22 | GI | CPM | Construction Project Manager | 12.8921 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 101.4%
Q470-298 | ARROW PARK COMMUNITY CTR - MECHANICAL WORK | 1998-03-30 | 1998-04-27 | 1997-04-13 | 124800 | 128000 | 1998-11-30 | 1999-11-24 | 2000-05-22 | GI | CPM | Construction Project Manager | 11.7345 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 2.564%
Q470-398 | ARROW PARK COMMUNITY CTR - ELECTRICAL WORK | 1998-03-30 | 1998-04-27 | 1997-04-13 | 72609 | 105000 | 1998-11-30 | 1999-11-24 | 2000-05-22 | GI | CPM | Construction Project Manager | 11.1928 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 44.61%
Q474-199 | TWU (LOUIS SIMEONE) PARK | 1999-10-30 | 2000-01-03 | 1998-10-06 | 395934 | 500000 | 2000-06-05 | 2000-12-01 | 2001-05-04 | GI | Q | Queens Team | 12.889 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 154 | 26.28%
QG-1000M | QUEENS FLAGPOLES (EMERGENCY) | 2000-07-30 | 2000-07-21 | 2000-05-30 | 1083150 | 1300000 | 2000-08-28 | 2000-12-25 | 2000-12-24 | GI | CPM | Construction Project Manager | 13.8954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 20.02%
QG-1001M | STREET TREE PLANTING - CB 10 & 12-14 - FY 2002 | 2001-06-30 | 2001-06-08 | 2001-05-21 | 327981 | 375000 | 2001-10-29 | 2002-07-25 | 2002-01-23 | GI | T | Tree Unit | 12.7007 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -183 | 14.34%
QG-1001MR | STREET TREE PLANTING - CB 10 & 12-14 - FY 2003 | 2002-07-23 | 2002-07-23 | 2001-05-21 | 324305 | 500000 | 2002-10-31 | 2003-07-27 | 2003-07-24 | GI | T | Tree Unit | 12.6894 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -3 | 54.18%
QG-1005M | CONSTR OF SYNTH TURF @ LIBERTY PK, BROOKVILLE PK & VICTORY FIELD | 2005-02-15 | 2005-03-24 | 2004-09-02 | 4782580 | 6350000 | 2005-08-08 | 2007-01-29 | 2007-07-30 | FI | Q | Queens Team | 15.3805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 182 | 32.77%
QG-1007M PLANYC | QUEENS CB 1-14 - BLOCK PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2007-05-22 | 2007-05-04 | 975000 | 1148000 | 2007-10-29 | 2008-07-24 | 2008-02-25 | FI | T | Tree Unit | 13.7902 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -150 | 17.74%
QG-100M | BOILERS & HEATING SYSTEMS BOROWIDE | 1999-11-30 | 1999-11-10 | 1999-06-22 | 249950 | 352000 | 2000-05-08 | 2000-11-03 | 2000-11-03 | GI | Q | Queens Team | 12.429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40.83%
QG-101M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-07-17 | 323388 | 369000 | 2001-02-19 | 2001-08-17 | 2001-07-27 | GI | T | Tree Unit | 12.6866 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -21 | 14.1%
QG-101MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-07-17 | 307855 | 339000 | 2002-03-18 | 2002-09-13 | 2002-08-05 | GI | T | Tree Unit | 12.6374 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -39 | 10.12%
QG-102M | BOILERS & HEATING SYSTEMS - 3 QUEENS SITES | 2001-10-15 | 2001-10-05 | 2001-07-11 | 244192 | 290000 | 2002-06-17 | 2003-03-13 | 2003-03-19 | GI | Q | Queens Team | 12.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 18.76%
QG-103M | STREET TREE PLANTING - C.B. 1 - 6 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 354098 | 427000 | 2003-03-26 | 2003-09-21 | 2003-08-27 | GI | T | Tree Unit | 12.7773 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -25 | 20.59%
QG-103MR | STREET TREE PLANTING - CB 1-6 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 308000 | 404000 | 2004-04-12 | 2004-10-08 | 2005-02-15 | GI | T | Tree Unit | 12.6379 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 130 | 31.17%
QG-104M | PLAY EQUIPMENT, S.S. HANDBALL CTS, & GENERAL SITE WORK | 2003-12-31 | 2003-12-23 | 2003-08-12 | 1703000 | 2215000 | 2004-05-05 | 2005-05-04 | 2005-09-13 | FI | RCU | Requirements Contract Unit | 14.3479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 132 | 30.06%
QG-105M | PLAY EQUIPMT, S.S., HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 1500000 | 1800000 | 2005-11-21 | 2006-11-20 | 2006-11-21 | FI | RCU | Requirements Contract Unit | 14.221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 20%
QG-107M | STREET TREES - CB 1-8 QUEENS |  | 2007-01-05 | 2006-09-14 | 644000 | 708000 | 2007-03-26 | 2007-09-21 | 2007-09-28 | FI | T | Tree Unit | 13.3755 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 9.938%
QG-1097 | RECONSTR. OF THREE TRIANGLES | 1998-02-03 | 1998-03-05 | 1996-12-19 | 459431 | 672000 | 1998-08-03 | 1999-01-29 | 1999-04-22 | GI | CPM | Construction Project Manager | 13.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 46.27%
QG-1099 | RECONSTR. OF THREE TRIANGLES | 1999-04-17 | 1999-04-19 | 1998-11-24 | 220412 | 450000 | 1999-08-03 | 2000-01-29 | 2000-05-26 | GI | CPM | Construction Project Manager | 12.3033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 104.2%
QG-1100MA | BOILERS & HEATING SYSTEMS AT QUEENS FACILITIES | 2000-12-15 | 2001-01-29 | 2000-07-03 | 296300 | 513000 | 2001-12-17 | 2002-09-12 | 2002-05-22 | GI | CPM | Construction Project Manager | 12.5991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -113 | 73.14%
QG-1101M | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2001-06-30 | 2001-06-07 | 2001-04-25 | 400000 | 475000 | 2001-12-03 | 2002-08-29 | 2003-03-05 | GI | RCU | Requirements Contract Unit | 12.8992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 188 | 18.75%
QG-1101MR | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2002-04-29 | 2002-04-29 | 2001-04-25 | 85000 | 85000 | 2002-12-31 | 2003-09-26 | 2003-04-23 | GI | RCU | Requirements Contract Unit | 11.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -156 | 0%
QG-1105M | CONSTR OF SYNTH TURF @ KISSENA CORRIDOR PK, REV HINTON PK | 2005-02-15 | 2005-03-02 | 2005-03-21 | 1843620.97 | 3049000 | 2005-10-31 | 2006-08-26 | 2006-10-05 | GI | Q | Queens Team | 14.4272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 65.38%
QG-1197 | PLAY EQUIPMENT, SAFETY SURFACE, PAVEMENTS, FENCES & SITEWORK | 1997-04-01 | 1997-04-03 | 1997-03-10 | 1060481 | 1060000 | 1997-08-18 | 1998-03-15 | 1999-04-20 | GI | RCU | Requirements Contract Unit | 13.8742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 401 | -0.04536%
QG-1198 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-26 | 1997-09-15 | 911465 | 1139000 | 1998-05-29 | 1999-05-28 | 1999-07-26 | FI | RCU | Requirements Contract Unit | 13.7228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 59 | 24.96%
QG-1198R | PLAY EQUIP, S.S., HANDBALL CTS., & SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-26 | 1997-09-15 | 911465 | 1093000 | 1999-06-07 | 2000-06-05 | 2000-05-26 | GI | RCU | Requirements Contract Unit | 13.7228 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -10 | 19.92%
QG-1199 | SIDEWALKS, PAVEMENTS, LAWNS, & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-12 | 1999-01-20 | 726300 | 965000 | 1999-08-02 | 2000-04-27 | 2000-06-14 | GI | RCU | Requirements Contract Unit | 13.4957 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 48 | 32.87%
QG-1199R | M & O REQ. CONTRACT F/SIDEWALKS, PAVEMENTS, ETC. | 2000-03-31 | 2000-02-11 | 1999-01-20 | 450000 | 610000 | 2000-05-01 | 2001-01-25 | 2001-05-30 | FI | RCU | Requirements Contract Unit | 13.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 125 | 35.56%
QG-1205M | CONSTR OF SYNTH TURF @ QUEENSBRIDGE PK, REIFF PK & MAFERA PK | 2005-02-15 | 2005-03-03 | 2004-08-23 | 2790929 | 3890000 | 2005-09-12 | 2006-12-10 | 2006-10-06 | GI | Q | Queens Team | 14.8419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -65 | 39.38%
QG-1297 | PLAY EQUIPMENT, SAFETY SURFACE, PAVEMENTS, FENCES & GENERAL SITEWORK IN VARIOUS PARKS & PLGDS. | 1997-04-15 | 1997-04-10 | 1997-03-10 | 791400 | 1021000 | 1997-07-28 | 1998-02-22 | 1998-10-24 | GI | RCU | Requirements Contract Unit | 13.5816 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 244 | 29.01%
QG-1299 | SIDEWALKS, PAVEMENTS, LAWNS, & GENERAL SITE WORK | 1999-02-12 | 1999-03-12 | 1999-01-20 | 744619 | 937000 | 1999-08-02 | 2000-04-27 | 2000-08-30 | GI | RCU | Requirements Contract Unit | 13.5206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 125 | 25.84%
QG-1299R | SIDEWALKS, PAVEMENTS, LAWNS, & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-01-20 | 744619 | 970000 | 2000-11-29 | 2001-08-25 | 2002-07-09 | GI | RCU | Requirements Contract Unit | 13.5206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 318 | 30.27%
QG-1398 | STREET TREE PLANTING F.Y. 1998- C.B. 1-7 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 490066 | 551000 | 1998-05-04 | 1999-05-03 | 1999-04-30 | GI | T | Tree Unit | 13.1023 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -3 | 12.43%
QG-1399 | FENCES, GUIDERAILS, & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-09 | 1999-01-20 | 352416 | 455000 | 1999-06-21 | 2000-03-16 | 2000-07-19 | GI | RCU | Requirements Contract Unit | 12.7726 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 125 | 29.11%
QG-1498 | STREET TREE PLANTING F.Y. 1998 - C.B. 8-14 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 443571 | 551000 | 1998-05-18 | 1999-05-17 | 1999-04-01 | GI | T | Tree Unit | 13.0026 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -46 | 24.22%
QG-1499 | M&O REQ. CONTRACT F/PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 1999-06-15 | 1999-06-07 | 1999-04-09 | 820259 | 1066000 | 1999-10-27 | 2000-10-25 | 2000-11-13 | FI | RCU | Requirements Contract Unit | 13.6174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 19 | 29.96%
QG-1598 | REMOVAL OF DEAD STREET TREES & STUMPS FY 1998 - CB 1-8 | 1998-01-31 | 1998-01-27 | 1998-01-05 | 282870 | 283000 | 1998-07-01 | 1998-09-08 | 1998-09-06 | FI | T | Tree Unit | 12.5527 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 0.04596%
QG-1599 | PLAY EQUIPMENT, S.S., HANDBALL CTS & SITE WORK | 1999-06-30 | 1999-06-09 | 1999-04-09 | 891220 | 1159000 | 2000-01-15 | 2001-01-13 | 2000-11-15 | GI | RCU | Requirements Contract Unit | 13.7003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -59 | 30.05%
QG-1605M | QUEENS - STREET TREES, TREE PITS |  | 2004-12-15 | 2004-11-29 | 1676000 | 1976000 | 2005-05-16 | 2006-05-15 | 2006-03-23 | GI | T | Tree Unit | 14.3319 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -53 | 17.9%
QG-1698 | REMOVAL OF DEAD STREET TREES & STUMPS FY 1998 - CB 9-14 | 1998-01-31 | 1998-01-27 | 1998-01-05 | 268778 | 312000 | 1998-04-20 | 1998-06-28 | 1998-07-22 | FI | T | Tree Unit | 12.5016 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 24 | 16.08%
QG-1699 | SIDEWALKS, PAVEMENTS, LAWNS, GREENSTREETS & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-06-30 | 1999-06-14 | 1999-04-09 | 681784 | 793000 | 1999-11-01 | 2000-10-30 | 2001-04-19 | GI | RCU | Requirements Contract Unit | 13.4325 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 171 | 16.31%
QG-1705M | DEAD TREES & STUMP REMOVALS - CB 1-14 QUEENS | 2004-12-06 | 2004-12-06 | 2004-10-29 | 249978 | 275000 | 2005-06-27 | 2006-03-23 | 2005-09-26 | FI | T | Tree Unit | 12.4291 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -178 | 10.01%
QG-1705MR | DEAD TREES & STUMP REMOVALS - CB 1-14 QUEENS | 2004-12-06 | 2004-12-06 | 2004-10-29 | 249978 | 275000 | 2006-04-10 | 2007-01-04 | 2006-08-18 | FI | T | Tree Unit | 12.4291 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -139 | 10.01%
QG-1798 | PLAY EQUIPMENT, FENCES, PAVEMENTS & GENERAL SITEWORK | 1998-03-31 | 1998-03-18 | 1998-03-06 | 516073 | 600000 | 1998-07-27 | 1999-02-21 | 1999-06-11 | GI | RCU | Requirements Contract Unit | 13.154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 110 | 16.26%
QG-1799 | SIDEWALKS, PAVEMENTS, LAWNS GREENSTREETS & SITE WORK | 1999-06-30 | 1999-06-22 | 1999-04-09 | 676563 | 794000 | 1999-11-01 | 2000-10-30 | 2000-10-10 | GI | RCU | Requirements Contract Unit | 13.4248 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -20 | 17.36%
QG-1799R | SIDEWALKS, PAVEMENTS, LAWNS GREENSTREETS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 676563 | 866000 | 2000-11-08 | 2001-11-07 | 2001-04-19 | GI | RCU | Requirements Contract Unit | 13.4248 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -202 | 28%
QG-1898 | FENCES & PAVEMENTS @ VARIOUS LOCATIONS | 1998-03-27 | 1998-04-04 | 1998-02-09 | 456492 | 537000 | 1998-08-03 | 1999-01-29 | 1999-01-13 | GI | Q | Queens Team | 13.0313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -16 | 17.64%
QG-1899 | RECONSTR. OF FENCES, GUIDERAILS, & GENERAL SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 337639 | 404000 | 1999-11-01 | 2000-07-27 | 2000-08-01 | GI | RCU | Requirements Contract Unit | 12.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 5 | 19.65%
QG-1899R | FENCES, GUIDERAILS, & GENERAL SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 337639 | 535000 | 2000-11-06 | 2001-08-02 | 2001-04-11 | FI | RCU | Requirements Contract Unit | 12.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -113 | 58.45%
QG-198 | STREET TREE PLANTING F/FY 1998 | 1997-08-28 | 1997-08-28 | 1997-07-03 | 552955 | 613000 | 1997-11-26 | 1998-11-25 | 1998-07-20 | GI | T | Tree Unit | 13.223 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -128 | 10.86%
QG-199 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-23 | 1998-07-09 | 559955 | 602000 | 1999-03-15 | 2000-03-13 | 2000-01-05 | GI | T | Tree Unit | 13.2356 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -68 | 7.509%
QG-199R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-07-09 | 500000 | 665000 | 2000-02-29 | 2001-02-27 | 2001-01-29 | GI | T | Tree Unit | 13.1224 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -29 | 33%
QG-200M | STREET TREE PLANTING FY 2000 | 1999-07-29 | 1999-07-29 | 1999-07-20 | 339940 | 409000 | 2000-01-10 | 2000-10-05 | 2000-11-29 | GI | T | Tree Unit | 12.7365 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 55 | 20.32%
QG-201M | STREET TREE REMOVALS - FY 2001 | 2000-10-15 | 2000-10-31 | 2000-07-17 | 250067 | 276000 | 2001-04-23 | 2002-01-17 | 2002-01-04 | FI | T | Tree Unit | 12.4295 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -13 | 10.37%
QG-201MR | STREET TREE REMOVALS - FY 2002 | 2002-03-11 | 2002-03-11 | 2000-07-17 | 215000 | 226000 | 2002-08-12 | 2003-05-08 | 2003-05-08 | FI | T | Tree Unit | 12.2784 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5.116%
QG-202M | GREENSTREET PLANTING - IN & AROUND CUNNINGHAM PARK | 2002-01-31 | 2002-03-15 | 2001-11-08 | 154689 | 211000 | 2002-11-11 | 2003-11-10 | 2003-11-10 | GI | T | Tree Unit | 11.9492 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 36.4%
QG-203M | STREET TREE PLANTING - C.B. 7 - 9 & 11 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 354098 | 427000 | 2003-03-31 | 2003-09-26 | 2003-08-07 | GI | T | Tree Unit | 12.7773 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -50 | 20.59%
QG-204M | BOILERS & HEATING SYSTEMS - QUEENS (FY2004) |  | 2005-01-26 | 2003-09-29 | 162000 | 207000 | 2005-12-19 | 2006-12-18 | 2006-09-28 | GI | Q | Queens Team | 11.9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -81 | 27.78%
QG-205M | PAVEMENTS, SIDEWALKS, HANDBALL CTS, HOCKEY RINKS, FENCES & GENERAL SITEWORK |  | 2005-04-01 | 2004-08-16 | 1300000 | 1560000 | 2005-10-18 | 2006-10-17 | 2007-05-07 | FI | RCU | Requirements Contract Unit | 14.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 202 | 20%
QG-205MR | PAVEMENTS, SIDEWALKS, HANDBALL CTS, HOCKEY RINKS, FENCES & GENERAL SITEWORK |  | 2005-04-01 | 2004-08-16 | 1300000 | 1560000 | 2006-10-04 | 2007-10-03 | 2007-12-06 | FI | RCU | Requirements Contract Unit | 14.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 64 | 20%
QG-207M | STREET TREES - CB 9-14 QUEENS |  | 2007-01-05 | 2006-09-14 | 425000 | 425000 | 2007-04-02 | 2007-09-28 | 2007-10-12 | FI | T | Tree Unit | 12.9598 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 14 | 0%
QG-297 | PLANTING NEW & REPLACEMENT OF STREET TREES IN CB 8-14 | 1996-11-22 | 1997-02-25 | 1996-09-06 | 619625 | 763000 | 1997-05-21 | 1998-05-20 | 1998-05-20 | FI | T | Tree Unit | 13.3369 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 23.14%
QG-298 | STREET TREE PLANTING F/FY 1998 | 1997-08-30 | 1997-08-27 | 1997-07-03 | 447479 | 497000 | 1997-12-15 | 1998-12-14 | 1998-12-14 | GI | T | Tree Unit | 13.0114 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 11.07%
QG-299 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-23 | 1998-07-09 | 598445 | 640000 | 1999-03-29 | 2000-03-27 | 2000-02-03 | GI | T | Tree Unit | 13.3021 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -53 | 6.944%
QG-299R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-07-09 | 500000 | 618000 | 2000-04-03 | 2001-04-02 | 2001-04-02 | GI | T | Tree Unit | 13.1224 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 23.6%
QG-300M | CLEARVIEW, DOUGLASTON, FOREST PARK, KISSENA GOLF COURSES - IRRIGATION SYSTEMS | 1999-12-06 | 1999-12-20 | 1999-10-22 | 5812155 | 10088000 | 2000-03-02 | 2000-07-29 | 2001-06-28 | GI | CPM | Construction Project Manager | 15.5755 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 73.57%
QG-301M | STREET TREE (GREENSTREET PLANTING) IN QUEENS F/FY 2001 | 2000-09-29 | 2000-10-31 | 2000-08-08 | 349012 | 485000 | 2001-04-04 | 2002-04-03 | 2002-01-24 | GI | T | Tree Unit | 12.7629 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -69 | 38.96%
QG-301MR | STREET TREE (GREENSTREET PLANTING) IN QUEENS F/FY 2002 | 2001-07-30 | 2001-07-11 | 2000-08-08 | 349012 | 385000 | 2001-10-01 | 2002-09-30 | 2002-07-17 | GI | T | Tree Unit | 12.7629 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -75 | 10.31%
QG-302MA | PAVEMENTS, HANDBALL CTS, LANDSCAPED AREAS & SITE WORK | 2002-01-31 | 2003-03-26 | 2001-11-27 | 883000 | 1150000 | 2003-08-04 | 2004-08-02 | 2005-06-29 | GI | RCU | Requirements Contract Unit | 13.6911 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 331 | 30.24%
QG-303M | STREET TREE PLANTING - CB 10 & 12-14 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 354098 | 463000 | 2003-04-14 | 2003-10-10 | 2003-06-27 | GI | T | Tree Unit | 12.7773 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -105 | 30.75%
QG-303MR | STREET TREE PLANTING - CB 10 & 12-14 QUEENS | 2002-10-01 | 2002-10-18 | 2002-07-16 | 306000 | 435000 | 2004-04-12 | 2004-10-08 | 2004-09-08 | GI | T | Tree Unit | 12.6313 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -30 | 42.16%
QG-304M | STREET TREES - CB 1-6 QUEENS |  | 2004-05-25 | 2004-03-24 | 304000 | 358000 | 2004-10-25 | 2005-07-21 | 2005-04-14 | GI | T | Tree Unit | 12.6248 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -98 | 17.76%
QG-304MR | STREET TREES - CB 1-6 QUEENS |  | 2005-07-20 | 2004-03-24 | 290000 | 319000 | 2005-10-17 | 2006-07-13 | 2006-02-12 | GI | T | Tree Unit | 12.5776 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -151 | 10%
QG-306MA | SIDEWALKS DAMAGED BY ADJ CITY-OWNED TREES - CBS 8-14 QUEENS |  | 2006-01-09 | 2005-11-25 | 1654000 | 1862000 | 2007-04-09 | 2008-04-07 | 2008-04-01 | FI | T | Tree Unit | 14.3187 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -6 | 12.58%
QG-397 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & SITEWORK | 1996-10-15 | 1996-11-06 | 1996-09-20 | 757575 | 834000 | 1997-03-24 | 1998-03-23 | 1998-06-10 | GI | RCU | Requirements Contract Unit | 13.5379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 79 | 10.09%
QG-398 | STREET & FLOWERING TREE PLANTING IN GREENSTREET TRIANGLES | 1997-09-08 | 1997-09-09 | 1997-07-10 | 224611 | 252000 | 1997-12-13 | 1998-09-08 | 1998-09-08 | FI | T | Tree Unit | 12.3221 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12.19%
QG-399 | REMOVAL OF DEAD TREES - F.Y. 1999 | 1998-11-30 | 1998-11-13 | 1998-10-28 | 216955 | 234000 | 1999-03-29 | 1999-08-25 | 1999-08-23 | FI | T | Tree Unit | 12.2874 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 7.856%
QG-39950-100M | QUEENS BLVD MALLS - 58TH TO 63RD STREETS | 1999-12-30 | 2000-02-27 | 1999-09-23 | 502525 | 620000 | 2000-08-07 | 2000-12-04 | 2000-12-04 | GI | CPM | Construction Project Manager | 13.1274 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.38%
QG-39950-101M | QUEENS BLVD. MALL (QUEENS GATE) @ 84TH DR. & 87TH AVE. | 2001-08-30 | 2001-08-22 | 2001-04-20 | 389006 | 495000 | 2002-05-13 | 2002-11-08 | 2002-10-29 | GI | Q | Queens Team | 12.8714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -10 | 27.25%
QG-399R | REMOVAL OF DEAD TREES - F.Y. 2000 | 1999-12-31 | 1999-10-27 | 1998-10-28 | 200000 | 245000 | 2000-02-15 | 2000-07-13 | 2000-07-07 | FI | T | Tree Unit | 12.2061 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -6 | 22.5%
QG-400M | STREET & FLOWERING TREES IN GREENSTREET TRIANGLES - QUEENS | 1999-11-03 | 1999-11-03 | 1999-10-18 | 384845 | 498000 | 2000-03-29 | 2000-12-23 | 2000-12-07 | FI | T | Tree Unit | 12.8606 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -16 | 29.4%
QG-401M | PLAY EQUIPMENT, SAFETY SURFACING,HANDBALL CTS & SITE WORK | 2000-11-30 | 2000-10-31 | 2000-08-15 | 1477180 | 2028000 | 2001-04-02 | 2002-04-01 | 2002-08-13 | GI | RCU | Requirements Contract Unit | 14.2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 134 | 37.29%
QG-401MR | PLAY EQUIPMENT, SAFETY SURFACING,HANDBALL CTS & SITE WORK | 2001-06-30 | 2001-06-13 | 2000-08-15 | 1477180 | 2058000 | 2002-03-04 | 2003-03-03 | 2004-01-13 | GI | RCU | Requirements Contract Unit | 14.2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 316 | 39.32%
QG-402MA | PLAY EQUIPMENT, S.S. HANDBALL CTS, & SITE WORK | 2002-01-31 | 2003-03-26 | 2001-11-27 | 776000 | 1020000 | 2003-09-15 | 2004-09-13 | 2005-06-24 | FI | RCU | Requirements Contract Unit | 13.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 284 | 31.44%
QG-403M | FENCING, GUIDE RAILS, & GENERAL SITE WORK | 2002-10-31 | 2002-10-07 | 2002-07-15 | 350000 | 455000 | 2003-05-19 | 2004-02-12 | 2005-03-21 | FI | RCU | Requirements Contract Unit | 12.7657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 403 | 30%
QG-404M | STREET TREES - CB 7-9 & 11 QUEENS |  | 2004-05-25 | 2004-03-24 | 326000 | 382000 | 2004-10-25 | 2005-07-21 | 2005-04-01 | GI | T | Tree Unit | 12.6947 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -111 | 17.18%
QG-404MR | STREET TREES - CB'S 7-9 & 11 QUEENS |  | 2005-07-20 | 2004-03-24 | 293000 | 322000 | 2005-10-17 | 2006-07-13 | 2006-03-23 | GI | T | Tree Unit | 12.5879 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -112 | 9.898%
QG-405M | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 600000 | 720000 | 2005-08-29 | 2006-08-28 | 2006-06-28 | FI | RCU | Requirements Contract Unit | 13.3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -61 | 20%
QG-46000-199 | SIDEWALKS & TREE PITS - MYRTLE/WYCKOFF AVES TO FRESH POND RD. | 1999-11-30 | 2000-01-05 | 1999-01-26 | 134659 | 297000 | 2000-08-07 | 2000-11-04 | 2000-11-30 | GI | CPM | Construction Project Manager | 11.8105 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 120.6%
QG-46600-198 | WINFIELD PLAZA (VICTORIOUS AMERICA PARK) | 1998-04-02 | 1998-04-07 | 1997-11-24 | 391798 | 500000 | 1998-09-22 | 1999-05-19 | 1999-07-14 | GI | CPM | Construction Project Manager | 12.8785 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 27.62%
QG-46750-199 | WOODSIDE PARK - BENCHES, PVMTS, PLANTING | 1999-08-01 | 1999-08-31 | 1998-10-01 | 339493 | 442000 | 2000-03-20 | 2000-12-14 | 2000-12-12 | GI | Q | Queens Team | 12.7352 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -2 | 30.19%
QG-46800-101MD | VAN DOREN & 108TH STS. (TEN HEROS PLAZA) TRAFFIC TRIANGLE | 2001-09-30 | 2001-10-26 | 2001-05-24 | 99340 | 194000 | 2004-04-05 | 2004-10-31 | 2004-06-17 | GI | Q | Queens Team | 11.5063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -136 | 95.29%
QG-46850-102M | ASTORIA BLVD MALL (79TH - 111TH STS.) | 2002-04-15 | 2002-10-17 | 2001-08-30 | 707727 | 1010000 | 2003-07-07 | 2004-01-02 | 2003-12-23 | GI | Q | Queens Team | 13.4698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -10 | 42.71%
QG-46900-102M | BEACH CHANNEL MALL (BEACH 116TH ST. ROTARY) - WATER & IRRIGATION SYSTEM | 2001-10-31 | 2001-11-26 | 2001-09-20 | 34882 | 87000 | 2002-08-26 | 2002-12-23 | 2002-11-21 | FI | R | Staten Island Team | 10.4597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -32 | 149.4%
QG-46950-104MA | MEMORIAL MARKER/MONUMENT - HILLCREST VETERANS SQUARE (QZ20) | 2004-01-01 | 2004-02-11 | 2003-08-13 | 96873 | 175000 | 2004-10-25 | 2005-03-23 | 2005-05-03 | GI | Q | Queens Team | 11.4812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41 | 80.65%
QG-47200-106M | LATIMER HOUSE - PERIMETER FENCE | 2006-08-01 | 2006-08-04 | 2006-05-11 | 145630.68 | 200000 | 2007-06-25 | 2007-12-21 | 2007-12-12 | FI | Q | Queens Team | 11.8888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -9 | 37.33%
QG-497 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & SITEWORK | 1996-10-15 | 1996-11-07 | 1996-09-20 | 778570 | 857000 | 1997-04-14 | 1998-04-13 | 1998-04-13 | FI | RCU | Requirements Contract Unit | 13.5652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10.07%
QG-499 | REMOVAL OF STUMPS FY 1999 | 1998-11-15 | 1998-11-10 | 1998-10-28 | 249126 | 266000 | 1999-03-29 | 1999-08-25 | 1999-09-13 | FI | T | Tree Unit | 12.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 19 | 6.773%
QG-499R | REMOVAL OF STUMPS FY 1999 | 1999-12-31 | 1999-10-27 | 1998-10-28 | 249126 | 300000 | 2000-04-17 | 2000-09-13 | 2000-09-08 | FI | T | Tree Unit | 12.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -5 | 20.42%
QG-501M | PLAY EQUIPMENT, S.S, HANDBALL CTS. & SITE WORK | 2001-01-31 | 2001-03-12 | 2001-02-13 | 1173799 | 1650000 | 2001-07-23 | 2002-07-22 | 2002-10-17 | GI | RCU | Requirements Contract Unit | 13.9758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 87 | 40.57%
QG-502MA1 | BROOKVILLE PK & LAURELTON PKWY GREENWAY (147TH & MERRICK BLVD) | 2003-02-27 | 2004-01-06 | 2001-12-07 | 457446.1 | 730000 | 2006-03-20 | 2006-09-15 | 2006-12-04 | GI | Q | Queens Team | 13.0334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 80 | 59.58%
QG-503M | PLAY EQUIP, S.S., HANDBALL CTS, & GENERAL SITE WORK | 2002-12-31 | 2003-02-11 | 2002-07-15 | 1590000 | 2067000 | 2003-08-11 | 2004-08-09 | 2005-06-15 | GI | RCU | Requirements Contract Unit | 14.2792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 310 | 30%
QG-503MR | PLAY EQUIP, S.S., HANDBALL CTS, & GENERAL SITE WORK |  | 2004-02-12 | 2002-07-15 | 836470 | 2008000 | 2004-10-04 | 2005-10-03 | 2006-03-27 | FI | RCU | Requirements Contract Unit | 13.6369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 175 | 140.1%
QG-504M | STREET TREES - CB 10 & 12-14 QUEENS |  | 2004-05-25 | 2004-03-24 | 395000 | 442000 | 2004-10-25 | 2005-07-21 | 2005-03-15 | GI | T | Tree Unit | 12.8866 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -128 | 11.9%
QG-504MR | STREET TREES - CB 10 & 12-14 QUEENS |  | 2005-07-20 | 2004-03-24 | 340000 | 374000 | 2005-10-17 | 2006-07-13 | 2006-07-06 | FI | T | Tree Unit | 12.7367 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -7 | 10%
QG-505M | STREET TREES - CB 1-6 QUEENS | 2004-08-05 | 2004-08-05 | 2004-07-06 | 626000 | 689000 | 2005-03-24 | 2005-09-19 | 2005-09-23 | GI | T | Tree Unit | 13.3471 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 10.06%
QG-505MR | STREET TREES - CB 1-6 QUEENS | 2004-08-05 | 2004-08-05 | 2004-07-06 | 674000 | 674000 | 2006-03-20 | 2006-09-15 | 2006-09-25 | FI | T | Tree Unit | 13.421 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 0%
QG-597R | RECONSTR. OF SIDEWALKS & PAVEMENTS - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 526785 | 632000 | 1998-03-02 | 1999-03-01 | 1999-01-05 | GI | RCU | Requirements Contract Unit | 13.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -55 | 19.97%
QG-599 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 411430 | 440000 | 1999-07-19 | 2000-07-17 | 2000-06-23 | GI | T | Tree Unit | 12.9274 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -24 | 6.944%
QG-599R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 400000 | 484000 | 2000-03-13 | 2001-03-12 | 2001-01-17 | GI | T | Tree Unit | 12.8992 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -54 | 21%
QG-601M | PAVEMENTS, FENCING, LANDSCAPED AREAS & SITE WORK | 2001-01-31 | 2001-04-06 | 2001-02-13 | 1155000 | 1584000 | 2001-07-23 | 2002-07-22 | 2003-11-25 | GI | RCU | Requirements Contract Unit | 13.9596 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 491 | 37.14%
QG-602M | STREET TREE PLANTING - CB 1-6 | 2002-06-30 | 2002-06-21 | 2002-04-23 | 321058 | 495000 | 2002-10-16 | 2003-07-12 | 2003-07-11 | GI | T | Tree Unit | 12.6794 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 54.18%
QG-602MR | STREET TREE PLANTING - CB 1-6 QUEENS | 2002-06-30 | 2002-06-21 | 2002-04-23 | 390200 | 487000 | 2003-10-20 | 2004-07-15 | 2004-07-15 | GI | T | Tree Unit | 12.8744 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 24.81%
QG-603M | STREET TREE REMOVALS IN COMM.BDS 1-14 QUEENS - FY 2003 |  | 2003-03-18 | 2002-10-08 | 250447 | 258000 | 2003-11-05 | 2004-07-31 | 2004-07-30 | FI | T | Tree Unit | 12.431 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 3.016%
QG-605M | STREET TREES - CB 7-9 & 11 QUEENS | 2004-08-05 | 2004-08-05 | 2004-07-06 | 711000 | 802000 | 2005-04-05 | 2005-10-01 | 2005-09-13 | GI | T | Tree Unit | 13.4744 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -18 | 12.8%
QG-605MR | STREET TREES - CB 7-9 & 11 QUEENS | 2004-08-05 | 2004-08-05 | 2004-07-06 | 391000 | 323650 | 2006-05-20 | 2006-11-15 | 2006-07-24 | FI | T | Tree Unit | 12.8765 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -114 | -17.23%
QG-606M | CB 1-8 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 453000 | 453000 | 2006-10-16 | 2007-07-12 | 2007-05-30 | FI | T | Tree Unit | 13.0236 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -43 | 0%
QG-697 | SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1996-11-30 | 1996-12-05 | 1996-09-20 | 610485 | 1671000 | 1997-03-24 | 1998-03-23 | 1998-04-08 | FI | RCU | Requirements Contract Unit | 13.322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 16 | 173.7%
QG-699 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 403185 | 432000 | 1999-08-16 | 2000-08-14 | 2000-05-06 | GI | T | Tree Unit | 12.9072 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -100 | 7.147%
QG-699R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 400000 | 484000 | 2000-03-13 | 2001-03-12 | 2001-03-12 | GI | T | Tree Unit | 12.8992 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 21%
QG-700M | STREET TREE PLANTING - FY 2001 | 2000-07-15 | 2000-07-13 | 2000-05-11 | 373327 | 409000 | 2000-11-08 | 2001-08-04 | 2001-06-08 | GI | T | Tree Unit | 12.8302 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -57 | 9.555%
QG-700MR | STREET TREE PLANTING - FY 2002 | 2001-07-31 | 2001-06-13 | 2000-05-11 | 307855 | 335000 | 2001-10-15 | 2002-07-11 | 2002-02-13 | GI | T | Tree Unit | 12.6374 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -148 | 8.817%
QG-701M | PAVEMENTS, HANDBALL CTS & GENERAL SITE WORK | 2001-05-01 | 2001-05-01 | 2001-04-23 | 816410 | 817000 | 2001-11-05 | 2002-11-04 | 2003-12-23 | GI | RCU | Requirements Contract Unit | 13.6127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 414 | 0.07227%
QG-701MR | PAVEMENTS, HANDBALL CTS & GENERAL SITE WORK | 2002-03-14 | 2002-03-14 | 2001-04-23 | 573000 | 744000 | 2002-10-28 | 2003-10-27 | 2004-06-30 | GI | RCU | Requirements Contract Unit | 13.2586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 247 | 29.84%
QG-703M | BOILERS & HEATING SYSTEMS - QUEENS (FY2003) | 2003-08-26 | 2003-08-10 | 2002-10-30 | 245850 | 324000 | 2004-05-17 | 2005-05-16 | 2004-12-01 | GI | Q | Queens Team | 12.4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -166 | 31.79%
QG-705M | STREET TREES - CB 10 & 12-14 QUEENS |  | 2004-08-05 | 2004-07-06 | 812000 | 893000 | 2005-04-11 | 2005-10-07 | 2005-07-21 | GI | T | Tree Unit | 13.6073 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -78 | 9.975%
QG-705MR | STREET TREES - CB 10 & 12-14 QUEENS |  | 2004-08-05 | 2004-07-06 | 432000 | 432000 | 2006-03-20 | 2006-09-15 | 2006-09-15 | FI | T | Tree Unit | 12.9762 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0%
QG-706M | CB 9-14 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 588000 | 588000 | 2006-10-16 | 2007-07-12 | 2007-01-26 | FI | T | Tree Unit | 13.2845 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -167 | 0%
QG-706MR | CB 9-14 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 750000 | 935000 | 2007-10-11 | 2008-07-06 | 2008-03-12 | FI | T | Tree Unit | 13.5278 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -116 | 24.67%
QG-796 | PARK FACILITIES MAINTENANCE IN DIST.#5 & #6 | 1995-10-13 | 1995-10-12 |  | 174500 | 438000 | 1996-02-21 | 1998-02-19 | 1998-02-19 | FI | RCU | Requirements Contract Unit | 12.0697 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 151%
QG-797R | CHAIN LINK FENCES, GUIDERAILS, & STEEL FENCES - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 322770 | 405000 | 1998-02-09 | 1998-11-05 | 1998-10-22 | GI | RCU | Requirements Contract Unit | 12.6847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -14 | 25.48%
QG-799 | GREENSTREET TRIANGLES - FY 99 TREE PLANTING | 1999-01-29 | 1999-01-11 | 1998-11-02 | 265288 | 290000 | 1999-04-15 | 2000-04-13 | 2000-02-16 | GI | T | Tree Unit | 12.4886 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -57 | 9.315%
QG-800M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-05-11 | 322903 | 356000 | 2001-02-19 | 2001-08-17 | 2001-08-09 | GI | T | Tree Unit | 12.6851 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -8 | 10.25%
QG-800MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-05-11 | 348355 | 384000 | 2002-03-06 | 2002-09-01 | 2002-09-06 | GI | T | Tree Unit | 12.761 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 10.23%
QG-801MA | PAVEMENTS, FENCING, LANDSCAPED AREAS & GENERAL SITE WORK | 2001-05-15 | 2001-10-30 | 2001-04-23 | 1184410 | 1606000 | 2002-05-06 | 2003-05-05 | 2004-07-15 | GI | RCU | Requirements Contract Unit | 13.9848 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 437 | 35.59%
QG-801MAR | PAVEMENTS, FENCING, LANDSCAPED AREAS & GENERAL SITE WORK | 2002-07-10 | 2002-07-10 | 2001-04-23 | 1180000 | 1534000 | 2003-08-11 | 2004-08-09 | 2005-05-24 | GI | RCU | Requirements Contract Unit | 13.981 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 288 | 30%
QG-803M | PAVEMENTS, FENCES & GENERAL SITE WORK | 2003-12-31 | 2003-12-31 | 2003-05-06 | 460000 | 483000 | 2004-07-20 | 2005-04-15 | 2005-03-29 | GI | RCU | Requirements Contract Unit | 13.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -17 | 5%
QG-805M | CB 1-7, SIDEWALKS DAMAGED BY ADJ CITY-OWNED TREES - QUEENS |  | 2004-07-28 | 2004-07-20 | 512000 | 563000 | 2005-06-06 | 2006-06-05 | 2006-05-02 | FI | T | Tree Unit | 13.1461 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -34 | 9.961%
QG-898 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-23 | 1997-09-15 | 836647 | 1105000 | 1998-05-26 | 1999-05-25 | 1999-10-15 | GI | RCU | Requirements Contract Unit | 13.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 143 | 32.07%
QG-898R | PLAY EQUIP, S.S., HANDBALL CTS., & SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-11 | 1997-09-15 | 836647 | 1000000 | 1999-06-07 | 2000-06-05 | 2000-11-08 | GI | RCU | Requirements Contract Unit | 13.6372 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 156 | 19.52%
QG-899 | BOILERS & HEATINGS SYSTEMS IN QUEENS | 1998-12-15 | 1999-01-05 | 1998-11-23 | 198550 | 387000 | 1999-06-14 | 1999-12-10 | 2000-05-23 | GI | CPM | Construction Project Manager | 12.1988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 94.91%
QG-900M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-05-11 | 322938 | 357000 | 2001-03-12 | 2001-09-07 | 2001-08-17 | GI | T | Tree Unit | 12.6852 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -21 | 10.55%
QG-900MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-05-11 | 307855 | 335000 | 2002-03-19 | 2002-09-14 | 2002-06-21 | GI | T | Tree Unit | 12.6374 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -85 | 8.817%
QG-901M | STREET TREE PLANTING - CB 7-9 & 11 - FY 2002 | 2001-06-30 | 2001-06-08 | 2001-05-21 | 317475 | 360000 | 2001-12-01 | 2002-08-27 | 2002-06-10 | GI | T | Tree Unit | 12.6682 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -78 | 13.39%
QG-905M | CB 8-14, SIDEWALKS DAMAGED BY ADJ CITY-OWNED TREES - QUEENS |  | 2004-07-27 | 2004-07-16 | 836000 | 920000 | 2005-06-28 | 2006-06-27 | 2006-11-15 | GI | T | Tree Unit | 13.6364 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 141 | 10.05%
QG-906M | P.S.220 PLGD 62-ASPHALT BALLFIELD & P.S. 175 ANNADALE PLGD-BASKETBALL CTS | 2006-09-01 | 2006-09-12 | 2006-06-15 | 711248 | 1000000 | 2007-07-30 | 2008-04-24 | 2008-02-07 | FI | Q | Queens Team | 13.4748 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -77 | 40.6%
QG-997 | RECONSTR. OF THREE TRIANGLES | 1997-11-24 | 1997-12-01 | 1996-12-06 | 175708 | 427000 | 1998-07-27 | 1999-01-22 | 1999-01-20 | GI | CPM | Construction Project Manager | 12.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 143%
QG-998 | SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1998-03-31 | 1998-02-20 | 1997-09-15 | 808170 | 951000 | 1998-05-26 | 1999-05-25 | 1999-06-22 | GI | RCU | Requirements Contract Unit | 13.6025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 28 | 17.67%
QG-999 | RECONSTR. OF THREE TRIANGLES | 1999-04-11 | 1999-04-13 | 1998-12-02 | 469000 | 763000 | 1999-09-28 | 2000-03-25 | 2000-06-23 | GI | CPM | Construction Project Manager | 13.0584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 62.69%
QT-452-102 | UDALL'S COVE PARK PRESERVE - TOPOGRAPHIC SURVEY | 1999-12-20 | 1999-12-30 | 1999-10-26 | 58400 | 59000 | 2000-05-15 | 2000-09-11 | 2001-11-21 | GI | S | Other | 10.9751 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436 | 1.027%
R003-102M | BARRETT PARK - STATEN ISLAND ZOO - OTTER EXHIBIT |  |  | 2002-04-12 | 435000 | 455000 | 2004-04-19 | 2005-04-18 | 2004-12-22 | GI | R | Staten Island Team | 12.9831 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -117 | 4.598%
R005-189 | CLOVE LAKES SENIOR CITIZEN GARDEN AREA | 1999-03-31 | 1999-04-21 | 1989-09-25 | 971399 | 1246000 | 1999-09-14 | 2000-07-09 | 2001-06-14 | GI | R | Staten Island Team | 13.7865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 340 | 28.27%
R005-198 | AERATION SYSTEM @ CLOVE LAKES PARK | 1997-12-31 | 1998-01-29 | 1997-09-30 | 171170 | 198000 | 1998-09-15 | 1999-01-12 | 1999-04-15 | GI | R | Staten Island Team | 12.0504 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 93 | 15.67%
R006-100M;400M | CONFERENCE HOUSE PARK - CONSTR OF PAVILION | 2000-03-15 | 2000-03-13 | 1999-08-23 | 995900 | 1375000 | 2001-05-07 | 2002-05-06 | 2002-10-21 | GI | R | Staten Island Team | 13.8114 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 168 | 38.07%
R006-101M | CONFERENCE HOUSE PARK - LANDSCAPE & PARKING LOT/ENTRY AREA | 2001-10-15 | 2001-11-28 | 2001-09-15 | 6488999 | 8673000 | 2003-05-12 | 2004-05-05 | 2004-11-09 | GI | R | Staten Island Team | 15.6856 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 188 | 33.66%
R006-400M | CONFERENCE HOUSE PARK - LANDSCAPE WORK ADJ TO PAVILION | 2000-03-15 | 2000-04-21 | 2000-03-28 | 189770 | 190000 | 2001-05-08 | 2002-05-07 | 2002-10-21 | GI | R | Staten Island Team | 12.1536 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 167 | 0.1212%
R006-502MA | CONFERENCE HOUSE PARK - DEMOLITION OF HOUSES | 2001-10-15 | 2003-01-03 | 2001-09-27 | 244671 | 245000 | 2003-08-18 | 2003-12-15 | 2004-03-31 | FI | R | Staten Island Team | 12.4077 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 107 | 0.1345%
R016-104M | GREAT KILLS (CEDAR GROVE) PK - CONSTR OF PATHS & SIDEWALKS | 2005-02-15 | 2005-10-30 | 2004-06-01 | 1261017.5 | 1747000 | 2006-08-01 | 2007-04-27 | 2007-07-19 | FI | R | Staten Island Team | 14.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 83 | 38.54%
R016-198 | OAKWOOD BEACH BERM | 1998-03-30 | 1998-04-03 | 1997-09-04 | 1742693 | 2906000 | 1998-08-10 | 1999-08-09 | 2000-03-31 | GI | R | Staten Island Team | 14.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 235 | 66.75%
R017-102M/402M | NATIVE PLANT CENTER - GREENHOUSE & SITE IMPROVEMENT | 2002-11-04 | 2003-03-18 | 2001-08-06 | 968825 | 1823000 | 2004-03-24 | 2005-03-23 | 2005-06-30 | GI | R | Staten Island Team | 13.7838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 99 | 88.17%
R017-202M | (ELECTRICAL) NATIVE PLANT CENTER - GREENHOUSE & SITE IMPROVEMENT | 2002-02-28 | 2003-05-06 | 2001-08-06 | 70985 | 71000 | 2004-03-24 | 2005-03-23 | 2005-06-30 | GI | R | Staten Island Team | 11.1702 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 99 | 0.02113%
R017-302M | (PLUMBING) NATIVE PLANT CENTER - GREENHOUSE & SITE IMPROVEMENT | 2002-02-28 | 2003-05-07 | 2001-08-06 | 102320 | 103000 | 2004-03-24 | 2005-03-23 | 2005-06-30 | GI | R | Staten Island Team | 11.5359 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 99 | 0.6646%
R017-402M | (HVAC) NATIVE PLANT CENTER - GREENHOUSE & SITE IMPROVEMENT | 2002-02-28 | 2003-05-07 | 2001-08-06 | 64995 | 65000 | 2004-03-24 | 2005-03-23 | 2005-06-30 | GI | R | Staten Island Team | 11.0821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 99 | 0.007693%
R030-197A/297 | WILLOWBROOK PK-NEW CAROUSEL PAVILION & SURROUNDING LANDSCAPE | 1997-04-03 | 1997-08-25 | 1995-09-15 | 1342231 | 2216000 | 1997-12-08 | 1998-12-02 | 1999-05-13 | GI | R | Staten Island Team | 14.1098 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 162 | 65.1%
R030-297 | (ELECTRICAL) WILLOWBROOK PK - CAROUSEL PAVILION | 1997-03-15 | 1997-04-03 | 1995-10-27 | 98000 | 98000 | 1997-12-08 | 1998-12-02 | 1999-05-13 | GI | R | Staten Island Team | 11.4927 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 162 | 0%
R030-396 | WILLOWBROOK PARK - FURNISH & INSTALL CAROUSEL | 1996-05-01 | 1996-05-01 | 1995-10-27 | 650000 | 650000 | 1996-07-08 | 1998-03-07 | 1999-04-27 | GI | A | Architecture | 13.3847 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 0%
R031-101M | WOLFE'S POND PARK - CONSTR. OF THE BATTLE OF THE BULGE PLAZA | 2001-06-08 | 2001-06-06 | 2000-07-12 | 356285 | 456000 | 2001-10-15 | 2002-01-12 | 2001-12-14 | GI | R | Staten Island Team | 12.7835 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -29 | 27.99%
R031-194 | WOLFE'S POND PARK - TENNIS CTS. & TOT LOT | 1996-04-01 | 1996-10-10 | 1993-10-28 | 1397108 | 2132000 | 1997-06-02 | 1998-03-28 | 1998-11-30 | GI | R | Staten Island Team | 14.1499 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 247 | 52.6%
R043-100M | CROMWELL REC CTR - EMERGENCY CLEAN UP OF FUEL OIL SPILL | 1999-07-20 | 1999-09-21 | 1999-08-27 | 164000 | 164000 | 1999-01-20 | 1999-02-18 | 1999-02-03 | GI | E | Engineering | 12.0076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0%
R043-101M | CROMWELL RECREATION CTR - EMERGENCY PIER STABILIZATION | 2000-08-15 | 2000-08-15 | 2000-07-26 | 2526510 | 6803000 | 2000-08-21 | 2001-02-16 | 2002-04-02 | GI | R | Staten Island Team | 14.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 410 | 169.3%
R046-100M/400M | OCEAN BREEZE (MIDLAND BEACH) - CONSTR OF RECREATION PIER, C.S.,ETC. | 2001-03-15 | 2001-04-11 | 2000-06-23 | 6859377 | 8902000 | 2002-01-22 | 2003-04-16 | 2004-06-29 | FI | R | Staten Island Team | 15.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 440 | 29.78%
R046-101M | MIDLAND BEACH - ENTRANCE PLAZA | 2001-03-15 | 2001-04-11 | 2000-08-15 | 848351 | 990000 | 2001-07-30 | 2002-03-26 | 2002-09-24 | GI | R | Staten Island Team | 13.651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 182 | 16.7%
R046-104M | AMERICAN CIRCLE AT SOUTH BEACH/BDWLK OVERLOOK | 2004-03-15 | 2004-03-03 | 2003-09-18 | 606805 | 855000 | 2004-08-02 | 2005-02-27 | 2005-06-14 | GI | R | Staten Island Team | 13.316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 107 | 40.9%
R046-105MA | FDR BOARDWALK - RAILINGS, BENCHES & MISC WORK | 2004-11-15 | 2004-12-08 | 2004-08-18 | 896431 | 2144000 | 2006-03-15 | 2006-12-09 | 2007-12-04 | FI | R | Staten Island Team | 13.7062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 360 | 139.2%
R046-196 | SO. BEACH BOARDWALK - FIRE DAMAGE | 1996-03-31 | 1996-04-04 | 1996-02-05 | 592090 | 895000 | 1996-08-06 | 1997-05-02 | 1998-02-09 | GI | R | Staten Island Team | 13.2914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 283 | 51.16%
R046-197 | CONSTR OF FOUNTAIN IN SOUTH BEACH @ SAND LANE | 1996-11-30 | 1997-04-03 | 1996-07-16 | 906769 | 1318000 | 1997-09-10 | 1998-03-08 | 1998-06-17 | GI | R | Staten Island Team | 13.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 101 | 45.35%
R046-198/498 | SOUTH BEACH COMFORT STATION ON FA. CAPODANNO BLVD | 1998-01-31 | 1998-03-23 | 1997-09-23 | 393788 | 602000 | 1998-12-01 | 1999-11-30 | 2000-06-29 | GI | R | Staten Island Team | 12.8836 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 212 | 52.87%
R046-200M | (ELECTRICAL) SOUTH (MIDLAND) BEACH - CONSTR OF C.S. | 2001-03-15 | 2001-04-12 | 2001-03-26 | 258734 | 259000 | 2002-04-02 | 2003-06-25 | 2004-06-29 | GI | R | Staten Island Team | 12.4636 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 370 | 0.1028%
R046-201M | SOUTH BEACH - GAZEBO, SHADE STRUCTURE, FENCING | 2000-12-31 | 2001-04-02 | 2000-12-29 | 1292676 | 1675000 | 2002-03-04 | 2002-08-30 | 2003-04-28 | GI | R | Staten Island Team | 14.0722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 241 | 29.58%
R046-203M | MIDLAND BEACH - SOCCER FIELD (SYNTHETIC TURF) | 2003-03-03 | 2004-05-04 | 2002-12-02 | 817911 | 1129000 | 2005-03-14 | 2005-09-09 | 2005-10-04 | FI | R | Staten Island Team | 13.6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 25 | 38.03%
R046-298 | (ELECTRICAL) SOUTH BEACH COMFORT STATION ON FA. CAPODANNO BLVD | 1998-01-31 | 1998-03-23 | 1997-09-23 | 19986 | 20000 | 1998-12-01 | 1999-11-30 | 2000-06-29 | GI | R | Staten Island Team | 9.9028 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 212 | 0.07005%
R046-301MA1 | F.D.R.(SOUTH BEACH) BOARDWALK, RAMPS, STAIRS, BENCHES | 2001-12-15 | 2002-10-23 | 2001-06-01 | 772000 | 2042000 | 2003-05-27 | 2004-02-20 | 2005-10-05 | FI | R | Staten Island Team | 13.5567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 593 | 164.5%
R046-303M | MIDLAND BEACH SKATE BOARD RINK | 2003-12-31 | 2003-07-18 | 2003-05-06 | 460510 | 553000 | 2004-07-29 | 2005-04-24 | 2005-01-05 | GI | RCU | Requirements Contract Unit | 13.0401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -109 | 20.08%
R046-398 | (PLUMBING) SOUTH BEACH COMFORT STATION ON FA. CAPODANNO BLVD | 1998-01-31 | 1998-03-24 | 1997-09-23 | 59280 | 59000 | 1998-12-01 | 1999-11-30 | 2000-06-29 | GI | R | Staten Island Team | 10.99 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 212 | -0.4723%
R046-400M | (H&V) SOUTH (MIDLAND) BEACH - CONSTR OF C.S. | 2001-03-15 | 2001-04-12 | 2001-03-26 | 24350 | 25000 | 2002-04-02 | 2003-06-25 | 2004-06-29 | GI | R | Staten Island Team | 10.1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 370 | 2.669%
R046-498 | (H&V) SOUTH BEACH COMFORT STATION ON FA. CAPODANNO BLVD | 1998-01-31 | 1998-03-23 | 1997-09-23 | 13900 | 14000 | 1998-12-01 | 1999-11-30 | 2000-06-29 | GI | R | Staten Island Team | 9.5396 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 212 | 0.7194%
R046-598 | SOUTH BEACH PLAYGROUND & ROLLER HOCKEY RINK | 1998-03-31 | 1998-04-15 | 1997-09-23 | 893431 | 1014000 | 1998-09-21 | 1999-06-17 | 1999-06-22 | GI | R | Staten Island Team | 13.7028 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 13.5%
R046-698 | MIDLAND BEACH PLAYGROUND | 1998-12-31 | 1999-03-30 | 1997-09-23 | 496203 | 625000 | 1999-08-02 | 1999-12-29 | 2000-03-21 | GI | R | Staten Island Team | 13.1147 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 83 | 25.96%
R059-100M | ARTHUR VON BRIESEN PARK | 2000-03-22 | 2000-03-31 | 1999-08-13 | 775790 | 1010000 | 2000-09-18 | 2001-06-14 | 2001-09-18 | GI | R | Staten Island Team | 13.5616 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 96 | 30.19%
R065-100MA | GREENBELT NATURE CENTER - LANDSCAPE & RELATED SITE WORK | 2001-03-31 | 2001-05-08 | 2000-05-15 | 1502490 | 1942000 | 2002-03-11 | 2003-03-10 | 2004-05-04 | GI | R | Staten Island Team | 14.2226 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 421 | 29.25%
R065-198A/498 | GREENBELT NATURE CENTER @ ROCKLAND & BRIELLE AVES. | 2000-02-23 | 2000-09-05 | 1998-04-20 | 1372175 | 2475000 | 2002-03-04 | 2003-04-27 | 2004-04-14 | GI | R | Staten Island Team | 14.1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 353 | 80.37%
R065-298 | (ELECTRICAL) GREENBELT NATURE CENTER @ ROCKLAND & BRIELLE AVES | 2000-02-23 | 2000-03-15 | 1998-04-20 | 135536 | 136000 | 2002-03-04 | 2003-04-27 | 2004-04-14 | GI | R | Staten Island Team | 11.817 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 353 | 0.3423%
R065-398A | (PLUMBING) GREENBELT NATURE CENTER @ ROCKLAND & BRIELLE AVES | 2001-10-30 | 2001-11-26 | 1998-04-20 | 297565 | 298000 | 2002-07-29 | 2003-07-23 | 2004-04-14 | GI | R | Staten Island Team | 12.6034 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 266 | 0.1462%
R065-498 | (H&V) GREENBELT NATURE CENTER @ ROCKLAND & BRIELLE AVES | 2000-02-23 | 2000-03-15 | 1998-04-20 | 90793 | 91000 | 2002-03-04 | 2003-04-27 | 2004-04-14 | GI | R | Staten Island Team | 11.4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 353 | 0.228%
R075-195 | FATHER MACRIS BALLFIELD | 1995-11-30 | 1996-11-07 | 1995-10-25 | 533314 | 924000 | 1997-05-05 | 1998-01-29 | 1999-07-29 | GI | R | Staten Island Team | 13.1869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 546 | 73.26%
R079-101M | LEMON CREEK PARK - DREDGING OF ACCESS CANAL & BULKHEAD RECONSTR. | 2001-10-31 | 2002-03-15 | 2001-06-14 | 545650 | 800000 | 2002-12-09 | 2003-04-07 | 2003-06-24 | GI | R | Staten Island Team | 13.2097 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 78 | 46.61%
R079-190 | LEMON CREEK PARK | 1996-03-31 | 1996-04-29 | 1990-08-29 | 2675987 | 3735000 | 1997-02-03 | 1998-02-02 | 1999-02-11 | GI | R | Staten Island Team | 14.7998 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 374 | 39.57%
R086-105MA | P.S. 31 (DAVIS) PLAYGROUND | 2004-02-15 | 2004-02-15 | 2004-07-09 | 1281631 | 1775000 | 2006-04-17 | 2007-04-11 | 2008-01-10 | FI | R | Staten Island Team | 14.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 274 | 38.5%
R106-106M | BLOOMINGDALE PARK - SOCCER FIELD | 2006-10-01 | 2006-10-01 | 2006-05-02 | 769300 | 1200000 | 2007-09-24 | 2008-09-17 | 2008-01-16 | FI | R | Staten Island Team | 13.5532 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -245 | 55.99%
R114-195/495 | GRANITEVILLE PK. (PS 51) RECREATION BLDG. (GC) | 1996-03-31 | 1996-04-08 | 1995-05-01 | 717077 | 940000 | 1997-03-03 | 1998-03-02 | 1998-11-16 | GI | R | Staten Island Team | 13.4829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 259 | 31.09%
R114-295A | (ELECTRICAL) GRANITEVILLE PARK (PS 51) RECREATION BLDG | 1996-03-31 | 1996-04-01 | 1995-05-01 | 57000 | 57000 | 1997-03-03 | 1998-03-02 | 1998-11-16 | GI | R | Staten Island Team | 10.9508 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 259 | 0%
R114-395 | (PLUMBING) GRANITEVILLE PK (PS 51) RECREATION BLDG | 1996-03-31 | 1996-03-29 | 1995-05-01 | 82800 | 93000 | 1997-03-03 | 1998-03-02 | 1998-11-16 | GI | R | Staten Island Team | 11.3242 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 259 | 12.32%
R114-495A | (HVAC) GRANITEVILLE PARK RECREATION BLDG | 1996-03-31 | 1996-08-16 | 1995-09-08 | 52582 | 54000 | 1997-03-03 | 1998-03-02 | 1998-11-16 | GI | R | Staten Island Team | 10.8701 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 259 | 2.697%
R116-102M/402M | SAILOR'S SNUG HARBOR - S.I. BOTANICAL GARDEN - BUILDING "P" | 2002-12-31 | 2004-03-22 | 2001-08-03 | 2479467.33 | 3827000 | 2005-03-14 | 2006-09-04 | 2008-02-19 | FI | R | Staten Island Team | 14.7236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 533 | 54.35%
R116-104M | S.I. BOTANICAL GARDEN - WETLAND RESTORATION | 2004-03-15 | 2004-03-04 | 2003-09-05 | 924950.9 | 1438000 | 2004-10-29 | 2005-10-23 | 2005-10-21 | GI | R | Staten Island Team | 13.7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -2 | 55.47%
R116-198/199/299 | S.I. BOTANICAL GARDEN & SAILORS'SNUG HARBOR - A BARN COMPLEX | 1998-06-25 | 1998-08-04 | 1998-01-14 | 893222 | 1384000 | 1999-06-21 | 2000-06-14 | 2000-10-11 | GI | R | Staten Island Team | 13.7026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 119 | 54.94%
R116-202M | (ELECTRICAL) SAILOR'S SNUG HARBOR - S.I. BOTANICAL GARDEN - BUILDING P | 2002-12-31 | 2004-05-11 | 2001-08-03 | 240000 | 240000 | 2005-03-14 | 2006-09-04 | 2008-02-19 | FI | R | Staten Island Team | 12.3884 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 533 | 0%
R116-297A | SAILORS SNUG HARBOR PARK - FERRY LANDING TERMINAL | 1997-04-21 | 1997-08-04 | 1997-01-09 | 629370 | 818000 | 1998-07-27 | 1999-01-22 | 1999-11-18 | GI | R | Staten Island Team | 13.3525 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 300 | 29.97%
R116-298/598 | SAILORS SNUG HARBOR -"GRILLO" GREENHOUSE @ BOTANICAL GARDENS | 1998-11-30 | 1998-12-03 | 1998-02-15 | 830018 | 1305000 | 1999-04-15 | 2000-04-13 | 2001-04-03 | GI | R | Staten Island Team | 13.6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 355 | 57.23%
R116-299 | (PLUMBING) S.I. BOTANICAL GARDEN @ SAILORS'SNUG HARBOR - BARN COMPLEX | 1998-06-25 | 1998-11-30 | 1998-01-14 | 33050 | 38000 | 1999-06-21 | 2000-03-16 | 2000-10-11 | GI | R | Staten Island Team | 10.4058 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 209 | 14.98%
R116-302M | (PLUMBING) SAILOR'S SNUG HARBOR - S.I. BOTANICAL GARDEN - BUILDING P | 2002-12-31 | 2004-03-22 | 2001-08-03 | 187000 | 187000 | 2005-03-14 | 2006-09-04 | 2008-02-19 | FI | R | Staten Island Team | 12.1389 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 533 | 0%
R116-398 | (ELECTRICAL) SAILORS SNUG HARBOR - GREENHOUSE @ BOTANICAL GARDENS | 1998-10-30 | 1998-12-02 | 1998-02-15 | 111216 | 123000 | 1999-05-06 | 2000-05-04 | 2001-04-03 | GI | R | Staten Island Team | 11.6192 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 334 | 10.6%
R116-402M | (H&V) SAILOR'S SNUG HARBOR - S.I. BOTANICAL GARDEN - BUILDING P | 2002-12-31 | 2004-03-24 | 2001-08-03 | 293186.2 | 293186 | 2005-03-14 | 2006-09-04 | 2008-02-19 | FI | R | Staten Island Team | 12.5886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 533 | -6.822e-05%
R116-498 | (PLUMBING) SAILORS SNUG HARBOR - GREENHOUSE @ BOTANICAL GARDENS | 1998-10-30 | 1998-12-02 | 1998-02-15 | 139204 | 153000 | 1999-05-06 | 2000-05-04 | 2001-04-03 | GI | R | Staten Island Team | 11.8437 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 334 | 9.911%
R116-598 | (H&V) SAILORS SNUG HARBOR - GREENHOUSE @ BOTANICAL GARDENS | 1998-10-30 | 1998-12-02 | 1998-02-15 | 315000 | 326000 | 1999-05-06 | 2000-05-04 | 2001-04-03 | GI | R | Staten Island Team | 12.6603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 334 | 3.492%
R117-198 | BUONO BEACH - MATTHEW J. BUONO MONUMENT | 1999-08-31 | 1999-12-10 | 1997-11-17 | 634500 | 779000 | 2000-09-17 | 2001-06-13 | 2002-04-04 | GI | R | Staten Island Team | 13.3606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 295 | 22.77%
R119-195A1/495 | BLUE HERON PK. LANDSCAPE & POND RESTORATION | 1995-03-31 | 1995-04-11 | 1995-09-18 | 948991 | 2313000 | 1996-10-07 | 1997-10-06 | 1998-01-29 | GI | R | Staten Island Team | 13.7632 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 115 | 143.7%
R119-196;295/495 | BLUE HERON PK - CONSTR OF ENVIRONMENTAL CTR | 1995-09-30 | 1995-09-29 | 1995-09-19 | 1078970 | 1079000 | 1996-10-21 | 1997-10-20 | 1998-11-30 | GI | R | Staten Island Team | 13.8915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 406 | 0.00278%
R119-295 | (ELECTRICAL) BLUE HERON PK - CONSTR OF ENVIRONMENTAL CTR | 1995-08-31 | 1995-08-22 | 1994-08-18 | 159216 | 166000 | 1996-10-21 | 1997-10-20 | 1998-11-30 | GI | R | Staten Island Team | 11.978 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 406 | 4.261%
R119-395 | (PLUMBING) BLUE HERON PK - CONSTR OF ENVIRONMENTAL CTR | 1995-08-31 | 1995-08-18 | 1994-08-18 | 63790 | 64000 | 1996-10-21 | 1997-10-20 | 1998-11-30 | GI | R | Staten Island Team | 11.0634 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 406 | 0.3292%
R119-495A | (H&V) BLUE HERON PK - CONSTR OF ENVIRONMENTAL CTR | 1995-08-31 | 1995-08-18 | 1994-08-18 | 141000 | 143000 | 1996-10-21 | 1997-10-20 | 1998-11-30 | GI | R | Staten Island Team | 11.8565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 406 | 1.418%
R129-101MA1/401M | BLOOD ROOT VALLEY (SEAVIEW HOSPITAL) - REC CTR & SURROUNDING LANDSCAPE | 2001-10-05 | 2003-01-08 | 2000-09-21 | 3932110.5 | 8361000 | 2004-07-07 | 2006-01-07 | 2007-03-30 | GI | R | Staten Island Team | 15.1847 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 447 | 112.6%
R129-105M | BLOOD ROOT VALLEY - CONSTR OF SYNTH TURF SOCCER FIELD |  | 2004-11-12 | 2004-07-21 | 775692 | 1050000 | 2005-08-01 | 2006-01-27 | 2006-06-30 | FI | R | Staten Island Team | 13.5615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 154 | 35.36%
R129-201MA | (ELECTRICAL) BLOOD ROOT VALLEY - RECREATION CENTER | 2001-09-15 | 2002-07-11 | 2000-09-21 | 472260 | 472260 | 2004-07-07 | 2006-01-07 | 2007-03-30 | GI | R | Staten Island Team | 13.0653 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 447 | 0%
R129-301M | (PLUMBING) BLOOD ROOT VALLEY - RECREATION CENTER | 2001-09-15 | 2001-11-27 | 2000-09-21 | 159619 | 160000 | 2004-07-07 | 2006-01-07 | 2007-03-30 | GI | R | Staten Island Team | 11.9805 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 447 | 0.2387%
R129-401M | (H&V) BLOOD ROOT VALLEY - RECREATION CENTER | 2001-09-15 | 2001-11-27 | 2000-09-21 | 356000 | 356000 | 2004-07-07 | 2006-01-07 | 2007-03-30 | GI | R | Staten Island Team | 12.7827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 447 | 0%
R130-100M | SAW MILL CREEK - SALT MARSH | 2001-11-15 | 2001-11-30 | 2000-09-30 | 211732 | 395000 | 2003-03-17 | 2003-07-04 | 2004-11-08 | FI | R | Staten Island Team | 12.2631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 493 | 86.56%
R130-196 | WETLAND MITIGATION @ CHELSEA RD, SAW MILL CREEK PK. | 1997-03-31 | 1997-03-31 | 1996-02-16 | 111954 | 145000 | 1996-10-28 | 1998-10-27 | 1998-10-27 | GI | R | Staten Island Team | 11.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 29.52%
RG-100M | BOILERS & HEATING SYSTEMS BOROWIDE | 1999-11-30 | 1999-11-30 | 1999-06-22 | 176500 | 269000 | 2000-05-15 | 2000-11-10 | 2000-11-08 | GI | R | Staten Island Team | 12.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -2 | 52.41%
RG-101M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-07-17 | 249937 | 275000 | 2001-02-26 | 2001-08-24 | 2001-06-25 | GI | T | Tree Unit | 12.429 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -60 | 10.03%
RG-101MR | STREET TREE PLANTING - FY 2002 | 2001-10-30 | 2001-10-24 | 2000-07-17 | 243059 | 268000 | 2002-03-18 | 2002-09-13 | 2002-07-15 | GI | T | Tree Unit | 12.4011 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -60 | 10.26%
RG-102M | PAVEMENTS, FENCING, LANDSCAPED AREAS & SITE WORK | 2002-05-31 | 2002-05-06 | 2002-03-28 | 558000 | 650000 | 2003-01-27 | 2004-01-26 | 2003-10-01 | GI | RCU | Requirements Contract Unit | 13.2321 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -117 | 16.49%
RG-102MR | PAVEMENTS, FENCING, LANDSCAPED AREAS & SITE WORK | 2002-05-31 | 2002-05-06 | 2002-03-28 | 558000 | 650000 | 2004-02-24 | 2005-02-22 | 2004-10-26 | GI | RCU | Requirements Contract Unit | 13.2321 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -119 | 16.49%
RG-105M | P.E., S.S., PAVEMENTS, WALLS, STEPS, HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 750000 | 796000 | 2005-09-19 | 2006-09-18 | 2006-06-19 | GI | RCU | Requirements Contract Unit | 13.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -91 | 6.133%
RG-105MR | P.E., S.S., PAVEMENTS, WALLS, STEPS, HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 750000 | 900000 | 2006-07-17 | 2007-07-16 | 2006-09-14 | GI | RCU | Requirements Contract Unit | 13.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -305 | 20%
RG-107M | STREET TREES - CB 1-3 STATEN ISLAND |  | 2007-01-05 | 2006-09-14 | 284000 | 284000 | 2007-03-26 | 2007-09-21 | 2007-07-24 | FI | T | Tree Unit | 12.5567 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -59 | 0%
RG-12400-102M | PARK CONSTRUCTION @ DRUMGOOLE RD. BET VERNON & WOODHULL AVES. | 2002-03-15 | 2004-03-29 | 2001-11-13 | 711381 | 987000 | 2005-03-21 | 2005-10-16 | 2005-10-24 | GI | R | Staten Island Team | 13.475 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 8 | 38.74%
RG-198 | STREET TREE PLANTING F/FY 1998 | 1997-09-15 | 1997-09-12 | 1997-07-03 | 429455 | 479000 | 1997-12-04 | 1998-12-03 | 1998-07-02 | GI | T | Tree Unit | 12.9703 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -154 | 11.54%
RG-199 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-23 | 1998-07-09 | 443051 | 478000 | 1999-03-29 | 2000-03-27 | 1999-12-29 | GI | T | Tree Unit | 13.0014 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -89 | 7.888%
RG-199R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-07-09 | 275000 | 325000 | 2000-03-13 | 2001-03-12 | 2000-07-14 | GI | T | Tree Unit | 12.5245 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -241 | 18.18%
RG-200M | LATOURETTE, SILVER LAKE, SOUTH SHORE GOLF COURSES - IRRIGATION SYSTEMS | 1999-12-04 | 1999-12-20 | 1999-10-22 | 4607237 | 8908000 | 2000-03-02 | 2000-07-14 | 2001-04-18 | GI | CPM | Construction Project Manager | 15.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 93.35%
RG-201M | PAVEMENTS, HANDBALL COURTS, LANDSCAPED AREAS & SITE WORK | 2001-02-28 | 2001-02-28 | 2001-02-17 | 680000 | 876000 | 2001-07-30 | 2002-07-29 | 2002-06-27 | GI | RCU | Requirements Contract Unit | 13.4298 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -32 | 28.82%
RG-201MR | PAVEMENTS, HANDBALL COURTS, LANDSCAPED AREAS & SITE WORK | 2002-02-28 | 2002-02-28 | 2002-02-28 | 592000 | 661000 | 2002-07-15 | 2003-07-14 | 2002-10-17 | GI | RCU | Requirements Contract Unit | 13.2913 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -270 | 11.66%
RG-202M | STREET TREE PLANTING - CB 1-3 | 2002-06-30 | 2002-06-25 | 2002-04-23 | 401211 | 473000 | 2002-10-31 | 2003-07-27 | 2003-04-08 | GI | T | Tree Unit | 12.9022 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -110 | 17.89%
RG-202MR | STREET TREE PLANTING - CB 1-3 | 2002-06-30 | 2002-06-25 | 2002-04-23 | 180000 | 445000 | 2003-10-20 | 2004-07-15 | 2004-04-13 | GI | T | Tree Unit | 12.1007 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -93 | 147.2%
RG-203M | FENCING, PAVING, SAFETY SURFACING & GENERAL SITE WORK IN S.I. | 2002-10-31 | 2002-10-09 | 2002-07-15 | 310000 | 403000 | 2003-04-16 | 2004-01-10 | 2004-05-24 | GI | RCU | Requirements Contract Unit | 12.6443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 135 | 30%
RG-203MR | FENCING, PAVING, SAFETY SURFACING & GENERAL SITE WORK IN S.I. |  | 2004-02-12 | 2002-07-15 | 188660 | 189000 | 2004-06-21 | 2005-03-17 | 2005-04-15 | GI | RCU | Requirements Contract Unit | 12.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 29 | 0.1802%
RG-204M | PAVEMENTS, FENCES & GENERAL SITE WORK |  | 2004-02-23 | 2003-10-29 | 514000 | 639000 | 2004-07-29 | 2005-07-28 | 2005-06-27 | FI | RCU | Requirements Contract Unit | 13.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -31 | 24.32%
RG-205M | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 250000 | 300000 | 2005-08-15 | 2006-08-14 | 2006-06-30 | FI | RCU | Requirements Contract Unit | 12.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -45 | 20%
RG-205MR | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 218000 | 265000 | 2006-07-17 | 2007-07-16 | 2007-06-06 | FI | RCU | Requirements Contract Unit | 12.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -40 | 21.56%
RG-206M | CB 1-3 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 332000 | 332000 | 2006-10-23 | 2007-07-19 | 2007-02-12 | FI | T | Tree Unit | 12.7129 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -157 | 0%
RG-297 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & SITEWORK | 1996-10-15 | 1996-11-04 | 1996-09-20 | 562825 | 563000 | 1997-03-17 | 1998-03-16 | 1998-04-01 | GI | RCU | Requirements Contract Unit | 13.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 16 | 0.03109%
RG-298 | STREET & FLOWERING TREE PLANTING IN GREENSTREET TRIANGLES | 1997-09-16 | 1997-09-16 | 1997-07-10 | 128889 | 143000 | 1997-12-10 | 1998-09-05 | 1998-05-05 | FI | T | Tree Unit | 11.7667 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -123 | 10.95%
RG-299 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 340375 | 368000 | 1999-09-13 | 2000-09-11 | 2000-06-29 | GI | T | Tree Unit | 12.7378 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -74 | 8.116%
RG-299R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 275000 | 275000 | 2000-04-03 | 2001-04-02 | 2001-02-27 | GI | T | Tree Unit | 12.5245 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -34 | 0%
RG-301MA | PLAY EQUIP, S.S., HANDBALL CTS, & GENERAL SITE WORK | 2001-05-30 | 2001-10-30 | 2001-02-17 | 280000 | 364000 | 2002-04-17 | 2003-04-16 | 2003-10-14 | GI | RCU | Requirements Contract Unit | 12.5425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 181 | 30%
RG-303M | STREET TREE PLANTING - C.B. 1 - 3 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 302473 | 365000 | 2003-03-24 | 2003-09-19 | 2003-06-12 | GI | T | Tree Unit | 12.6197 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -99 | 20.67%
RG-303MR | STREET TREE PLANTING - CB 1-3 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 190000 | 241000 | 2004-04-12 | 2004-10-08 | 2004-07-02 | GI | T | Tree Unit | 12.1548 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -98 | 26.84%
RG-304M | STREET TREES - CB 1-3 STATEN ISLAND |  | 2004-05-24 | 2004-03-24 | 392000 | 431000 | 2004-11-01 | 2005-07-28 | 2005-07-05 | FI | T | Tree Unit | 12.879 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -23 | 9.949%
RG-304MR | STREET TREES - STATEN ISLAND |  | 2005-07-20 | 2004-03-24 | 319000 | 351000 | 2005-10-17 | 2006-07-13 | 2006-02-01 | FI | T | Tree Unit | 12.6729 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -162 | 10.03%
RG-305M | STREET TREES - CB 1-3 STATEN ISLAND |  | 2004-08-05 | 2004-07-06 | 475000 | 523000 | 2005-04-11 | 2005-10-07 | 2005-07-26 | FI | T | Tree Unit | 13.0711 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -73 | 10.11%
RG-305MR | STREET TREES - CB 1-3 STATEN ISLAND |  | 2004-08-05 | 2004-07-06 | 386000 | 386000 | 2006-03-20 | 2006-09-15 | 2006-09-20 | FI | T | Tree Unit | 12.8636 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0%
RG-397 | RECONSTR.OF SIDEWALKS, PATHS, PAVEMENTS, & GENERAL SITEWORK | 1996-11-30 | 1996-12-05 | 1996-09-20 | 314464 | 345000 | 1997-03-24 | 1998-03-23 | 1998-04-23 | FI | RCU | Requirements Contract Unit | 12.6586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 31 | 9.71%
RG-397R | RECONSTR. OF SIDEWALKS & PAVEMENTS - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 314464 | 407000 | 1998-03-24 | 1999-03-23 | 1999-01-07 | GI | RCU | Requirements Contract Unit | 12.6586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -75 | 29.43%
RG-399 | BOILERS & HEATINGS SYSTEMS IN STATEN ISLAND | 1998-12-15 | 1998-12-30 | 1998-11-23 | 115074 | 115000 | 1999-06-14 | 1999-12-10 | 2000-03-31 | GI | CPM | Construction Project Manager | 11.6533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | -0.06431%
RG-400M | STREET TREE PLANTING - FY 2001 | 2000-07-15 | 2000-07-13 | 2000-05-11 | 249894 | 275000 | 2000-11-03 | 2001-07-30 | 2001-04-13 | GI | T | Tree Unit | 12.4288 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -108 | 10.05%
RG-400MR | STREET TREE PLANTING - FY 2002 | 2001-06-26 | 2001-06-26 | 2000-05-11 | 334000 | 367000 | 2001-10-15 | 2002-07-11 | 2002-01-23 | GI | T | Tree Unit | 12.7189 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -169 | 9.88%
RG-497R | CHAIN LINK FENCES, GUIDERAILS, & STEEL FENCES - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 313460 | 406000 | 1998-02-02 | 1998-10-29 | 1999-02-05 | GI | RCU | Requirements Contract Unit | 12.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 99 | 29.52%
RG-500M | S.I. BIKEWAY & CULTURAL TRAIL - BET. FT. WADSWORTH & GREAT KILLS PARK | 2001-04-16 | 2004-03-01 | 2000-06-27 | 498381 | 696000 | 2005-12-05 | 2006-06-02 | 2006-06-01 | GI | R | Staten Island Team | 13.1191 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 39.65%
RG-597 | STREET TREE PLANTING FY 97 | 1997-02-15 | 1997-02-25 | 1996-09-03 | 289975 | 430000 | 1997-09-01 | 1998-08-31 | 1998-06-11 | GI | T | Tree Unit | 12.5775 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -81 | 48.29%
RG-599 | FENCES, GUIDERAILS, SIDEWALKS, PAVEMENTS, LAWNS, & SITE WORK | 1999-02-15 | 1999-03-10 | 1999-01-20 | 288350 | 300000 | 1999-06-28 | 2000-03-23 | 2000-07-25 | GI | RCU | Requirements Contract Unit | 12.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 124 | 4.04%
RG-599R | M & O REQ. CONTRACT F/FENCES, GUIDERAILS, ETC. | 2000-03-31 | 2000-02-11 | 1999-01-20 | 130000 | 238000 | 2000-05-15 | 2001-02-08 | 2000-12-08 | GI | RCU | Requirements Contract Unit | 11.7753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -62 | 83.08%
RG-600M | BOILERS & HEATING SYSTEMS @ DE MATTI PLGD. & CLOVE LAKE GARAGE | 2000-11-15 | 2000-11-20 | 2000-06-27 | 191000 | 229000 | 2001-05-14 | 2002-05-13 | 2002-09-11 | GI | R | Staten Island Team | 12.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 121 | 19.9%
RG-699 | FENCES, GUIDERAILS, SIDEWALKS, PAVEMENTS, LAWNS & SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 330295 | 360000 | 1999-11-01 | 2000-07-27 | 2000-10-11 | GI | RCU | Requirements Contract Unit | 12.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 76 | 8.993%
RG-699R | FENCES, GUIDERAILS, SIDEWALKS, PAVEMENTS, LAWNS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 330295 | 430000 | 2000-11-08 | 2001-08-04 | 2001-06-13 | GI | RCU | Requirements Contract Unit | 12.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -52 | 30.19%
RG-798 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-23 | 1997-09-15 | 342361 | 455000 | 1998-06-15 | 1999-06-14 | 1999-04-16 | FI | RCU | Requirements Contract Unit | 12.7436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -59 | 32.9%
RG-798R | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1999-01-29 | 1999-02-26 | 1997-09-15 | 342361 | 410000 | 1999-05-24 | 2000-05-22 | 1999-08-12 | GI | RCU | Requirements Contract Unit | 12.7436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -284 | 19.76%
RG-799 | M&O REQ. CONTRACT F/PLAY EQUIP, S.S., HANDBALL CTS., & SITEWORK | 1999-06-11 | 1999-06-07 | 1999-04-09 | 328850 | 437000 | 1999-12-06 | 2000-12-04 | 2000-10-26 | GI | RCU | Requirements Contract Unit | 12.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -39 | 32.89%
RG-799R | PLAY EQUIP, S.S., HANDBALL CTS., & SITEWORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 328850 | 450000 | 2000-11-06 | 2001-11-05 | 2001-10-23 | FI | RCU | Requirements Contract Unit | 12.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -13 | 36.84%
RG-899 | PLAY EQUIP, S.S., PVMTS, FENCES, LAWNS, GREEN STREETS & SITEWORK IN VARIOUS PARKS & PLGDS. | 1999-07-31 | 1999-06-10 | 1999-06-30 | 244582 | 325000 | 1999-12-06 | 2000-12-04 | 2000-09-26 | GI | RCU | Requirements Contract Unit | 12.4073 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -69 | 32.88%
RG-998 | STREET TREE PLANTING F.Y. 1998 - C.B. 1-3 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 216036 | 216000 | 1998-04-20 | 1999-04-19 | 1999-04-19 | GI | T | Tree Unit | 12.2832 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -0.01666%
X001-197 | AQUEDUCT LANDS/MORTON PLGD. | 1997-10-15 | 1997-11-21 | 1996-12-09 | 493371 | 641000 | 1998-05-04 | 1998-11-29 | 1998-11-25 | GI | X | Bronx Team | 13.109 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 29.92%
X002-100M | ROSEWOOD PLAYGROUND | 2000-11-30 | 2001-01-17 | 2000-05-11 | 364000 | 526000 | 2001-08-16 | 2001-12-13 | 2002-04-30 | GI | CPM | Construction Project Manager | 12.8049 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 44.51%
X002-101M | BRONX PARK - FLOODPLAIN & CHANNEL OF THE BRONX RIVER | 2002-09-26 | 2003-04-24 | 2001-03-16 | 2314968 | 2875000 | 2004-07-12 | 2005-04-07 | 2005-06-24 | GI | X | Bronx Team | 14.6549 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 24.19%
X002-103M/403M | BRONX ZOO - TIGER MOUNTAIN | 2003-03-31 | 2003-03-31 | 2002-09-03 | 8100000 | 7441000 | 2002-12-07 | 2003-12-06 | 2003-08-25 | FI | X | Bronx Team | 15.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -103 | -8.136%
X002-105M | BRONX PARK/RIVER PARK - PLGD | 2006-01-13 | 2006-03-09 | 2005-01-21 | 1085671.5 | 1420000 | 2006-08-15 | 2007-08-14 | 2007-09-27 | FI | CROT | Croton Unit | 13.8977 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 30.79%
X002-195A1 | BRONX PARK - "WIGWAM" E. STORAGE BLDG. - BX ADMIN. COMPLEX | 1995-02-24 | 1995-03-29 | 1994-06-27 | 977700 | 2499000 | 1997-05-12 | 1998-05-11 | 1999-03-26 | GI | X | Bronx Team | 13.793 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 155.6%
X002-198 | BRONX PARK EAST - BX ADMIN BLDG. E. STORAGE FACILITY RAMP | 1998-08-24 | 1998-08-24 | 1998-06-12 | 274934 | 395000 | 1999-03-15 | 1999-05-13 | 1999-06-18 | GI | X | Bronx Team | 12.5243 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 43.67%
X002-295 | (ELECTRICAL) BRONX PARK "WIGWAM" E. STORAGE BLDG - BX ADMIN COMPLEX | 1995-02-24 | 1995-03-29 | 1994-06-27 | 184035 | 236000 | 1995-11-01 | 1996-10-30 | 1999-03-12 | GI | X | Bronx Team | 12.1229 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 28.24%
X002-395A1 | (PLUMBING) BRONX PARK "WIGWAM" E. STORAGE BLDG - BX ADMIN COMPLEX | 1995-02-24 | 1996-09-20 | 1994-06-27 | 562607 | 568000 | 1997-05-12 | 1998-05-11 | 2000-08-31 | GI | X | Bronx Team | 13.2403 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843 | 0.9586%
X002-495A | (HVAC) BRONX PARK - "WIGWAM" E. STORAGE BLDG - ADMIN COMPLEX | 1995-02-24 | 1995-03-29 | 1994-06-27 | 280000 | 295000 | 1997-05-12 | 1998-05-11 | 1999-03-26 | GI | X | Bronx Team | 12.5425 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 5.357%
X002-503MA | NORTH BIKEWAYS & PATHS IN BRONX PARK | 2004-09-14 | 2004-01-09 | 2002-10-01 | 842412 | 1085000 | 2007-02-12 | 2007-11-08 | 2007-06-29 | FI | X | Bronx Team | 13.644 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132 | 28.8%
X004-103M | BRONX RIVER - GREENWAY WESTCHESTER CONNECTION/MUSKRAT COVE | 2004-09-15 | 2005-05-30 | 2003-01-27 | 996642.3 | 1363000 | 2007-03-19 | 2007-12-23 | 2007-12-07 | FI | X | Bronx Team | 13.8121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 36.76%
X008-104M | CLAREMONT PARK - STAIRCASES & ADJ PATHWAYS |  | 2004-03-08 | 2003-12-01 | 561162 | 726000 | 2004-09-13 | 2005-03-11 | 2004-11-19 | GI | X | Bronx Team | 13.2378 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -112 | 29.37%
X010-102M | CROTONA PARK - INDIAN LAKE & ADJACENT SITE WORK | 2002-03-15 | 2004-03-18 | 2001-11-19 | 1324622 | 1766000 | 2005-05-16 | 2006-05-15 | 2006-11-08 | GI | X | Bronx Team | 14.0966 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 33.32%
X010-104M/404M | CROTONA PARK TENNIS HOUSE | 2004-03-01 | 2004-05-21 | 2003-11-10 | 839504 | 1606000 | 2004-12-20 | 2005-07-17 | 2006-05-03 | GI | X | Bronx Team | 13.6406 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 91.3%
X010-105M | CROTONA PARK - CONSTR OF GREENWAY | 2005-02-15 | 2006-02-06 | 2004-07-15 | 755876 | 1091000 | 2006-11-15 | 2007-08-11 | 2007-08-09 | FI | X | Bronx Team | 13.5356 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 44.34%
X010-197 | CROTONA PK. PLGD.#6 & JIMMY CARTER (#7) PLGD. | 1998-03-31 | 1998-04-08 | 1996-07-08 | 1175365 | 1480000 | 1998-10-05 | 1999-09-29 | 2000-02-16 | GI | CPM | Construction Project Manager | 13.9771 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 25.92%
X010-198 | CROTONA PARK - PLAYGROUNDS #1 & #3 | 1998-03-19 | 1998-03-26 | 1997-11-24 | 565421 | 737000 | 1998-09-21 | 1999-06-17 | 1999-05-06 | GI | CPM | Construction Project Manager | 13.2453 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42 | 30.35%
X010-204M | (ELECTRICAL) CROTONA PARK TENNIS HOUSE |  | 2004-05-21 | 2003-11-10 | 127795 | 159000 | 2005-02-14 | 2005-07-29 | 2006-05-03 | GI | X | Bronx Team | 11.7582 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 24.42%
X010-205M | CROTONA PARK BALLFIELD #1 | 2005-01-15 | 2005-03-09 | 2004-10-18 | 647000 | 920000 | 2005-08-01 | 2006-03-08 | 2006-05-17 | GI | X | Bronx Team | 13.3801 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 42.19%
X010-297 | CROTONA PARK - PLGD.#10 | 1997-07-07 | 1997-10-28 | 1996-07-08 | 489677 | 661000 | 1998-06-29 | 1998-12-25 | 1999-03-31 | FI | CPM | Construction Project Manager | 13.1015 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 34.99%
X010-304M | (PLUMBING) CROTONA PARK TENNIS HOUSE |  | 2004-08-05 | 2003-11-10 | 153020.4 | 186000 | 2005-03-03 | 2005-07-29 | 2006-05-03 | GI | X | Bronx Team | 11.9383 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 21.55%
X010-404M | (H&V) CROTONA PARK TENNIS HOUSE |  | 2004-05-21 | 2003-11-10 | 89960 | 190000 | 2005-02-14 | 2005-07-29 | 2006-05-03 | GI | X | Bronx Team | 11.4071 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 111.2%
X011-105M | CROTONA PARKWAY MALLS - PORTION OF | 2005-02-15 | 2005-03-25 | 2004-10-13 | 578112 | 825000 | 2005-09-12 | 2006-06-08 | 2005-12-12 | GI | X | Bronx Team | 13.2675 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -178 | 42.71%
X013-102M | DEVOE PARK - BASKETBALL COURTS | 2002-02-28 | 2002-11-19 | 2001-10-16 | 328260 | 593000 | 2003-12-01 | 2004-04-28 | 2004-10-27 | GI | X | Bronx Team | 12.7016 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 80.65%
X013-198 | DEVOE PK. REC. CTR. SANITARY HOUSE SEWER | 1997-10-23 | 1997-10-28 | 1997-08-05 | 54470 | 74000 | 1998-03-30 | 1998-07-27 | 1998-05-14 | FI | X | Bronx Team | 10.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74 | 35.85%
X019-198 | EWEN PARK - STAIRWAY & MISCELLANEOUS SITEWORK | 1998-12-15 | 1999-02-04 | 1998-06-15 | 516324 | 702000 | 1999-08-09 | 2000-02-04 | 2001-02-23 | GI | X | Bronx Team | 13.1545 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 35.96%
X026-105M | HINES PARK | 2005-01-15 | 2005-03-02 | 2004-08-24 | 577712.12 | 819000 | 2005-09-19 | 2006-03-17 | 2006-07-14 | GI | X | Bronx Team | 13.2668 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 41.77%
X028-101MA | JOYCE KILMER PARK - PHASE III | 2001-03-30 | 2001-11-13 | 2000-11-21 | 1149877 | 1784000 | 2002-09-03 | 2003-09-02 | 2004-06-30 | GI | X | Bronx Team | 13.9552 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 55.15%
X028-103M | JOYCE KILMER PARK - PLGD CONSTRUCTION | 2003-02-28 | 2004-01-16 | 2003-01-02 | 271023 | 397000 | 2005-03-01 | 2005-08-27 | 2005-11-17 | GI | X | Bronx Team | 12.51 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 46.48%
X028-198A | JOYCE KILMER PK. - HEINRICH HEINE MEM.FOUNTAIN & LANDSCAPE | 1998-03-30 | 1998-05-01 | 1997-12-12 | 1441677 | 1870000 | 1998-10-13 | 1999-10-07 | 1999-12-10 | GI | X | Bronx Team | 14.1813 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 29.71%
X028-199 | JOYCE KILMER PARK II | 1999-03-31 | 1999-04-16 | 1998-10-19 | 1100324 | 1525000 | 1999-10-26 | 2000-09-19 | 2001-06-22 | GI | X | Bronx Team | 13.9111 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276 | 38.6%
X030-104M | MACOMBS DAM PARK - RUNNING TRACK | 2003-12-19 | 2003-12-16 | 2003-09-24 | 143600 | 225000 | 2004-07-12 | 2004-10-09 | 2004-09-16 | GI | X | Bronx Team | 11.8748 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23 | 56.69%
X030-105MA | MACOMBS DAM PARK - TERRACE AREA SURROUNDING FOUNTAIN | 2005-01-15 | 2005-03-23 | 2004-11-10 | 566304.1 | 505000 | 2006-02-21 | 2006-08-19 | 2006-12-21 | GI | X | Bronx Team | 13.2469 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | -10.83%
X030-106M | MACOMBS DAM PARK - CONSTR OF TRACK & FIELD ON PKG LOT #1 |  | 2006-07-21 | 2006-06-16 | 1144325 | 1770000 | 2006-12-06 | 2007-04-04 | 2007-05-17 | FI | X | Bronx Team | 13.9503 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 54.68%
X030-196 | MACOMBS DAM PARK BLEACHER @ 162 ST & JEROME & RIVER AVES. | 1997-07-15 | 1997-08-22 | 1996-06-21 | 267832 | 395000 | 1998-05-04 | 1998-10-30 | 1999-10-29 | GI | X | Bronx Team | 12.4981 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 47.48%
X030-304M | MACOMBS DAM PARK WATER - FOUNTAIN & TERRACE AREA | 2004-09-15 | 2005-05-06 | 2003-09-29 | 327551 | 547000 | 2006-02-13 | 2006-08-11 | 2007-04-26 | FI | X | Bronx Team | 12.6994 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 67%
X032-196 | MELROSE PARK PLGD | 1997-10-27 | 1997-10-27 | 1995-10-23 | 588274 | 756000 | 1998-04-13 | 1998-10-09 | 1998-12-22 | FI | X | Bronx Team | 13.2849 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 28.51%
X033-195 | FRISCH FIELD | 1996-09-30 | 1996-09-30 | 1995-05-03 | 188846 | 312000 | 1997-08-04 | 1998-01-30 | 1998-01-30 | FI | X | Bronx Team | 12.1487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.21%
X034-197 | MULLALY RECREATION CENTER - ELECTRICAL WORK | 1996-12-15 | 1997-03-05 | 1996-07-31 | 167500 | 466000 | 1997-06-30 | 1998-08-28 | 1999-12-23 | GI | X | Bronx Team | 12.0287 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482 | 178.2%
X034-198 | MULLALY REC. CTR. - LEAD PAINT ABATEMENT (EMERGENCY) | 1998-03-31 | 1998-03-25 | 1998-03-13 | 168164 | 283000 | 1998-04-06 | 1998-05-05 | 1998-05-04 | GI | X | Bronx Team | 12.0327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 68.29%
X034-199 | MULLALY REC. CTR. - SPRINKLER & A/C SECURITY CAGES | 1998-11-30 | 1999-03-08 | 1998-09-09 | 595000 | 889000 | 1999-07-27 | 1999-12-23 | 1999-12-23 | GI | X | Bronx Team | 13.2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.41%
X034-297 | MULLALY RECREATION CENTER - PLUMBING WORK | 1996-12-15 | 1997-03-05 | 1996-07-31 | 356625 | 458000 | 1997-06-30 | 1998-08-28 | 1999-12-02 | GI | X | Bronx Team | 12.7844 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461 | 28.43%
X034-299 | MULLALY PARK - E. 164TH ST & MCCLELLAN ST. | 2000-01-10 | 2000-02-18 | 1999-03-02 | 2175364 | 2905000 | 2000-07-31 | 2001-07-30 | 2001-09-21 | GI | X | Bronx Team | 14.5927 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 33.54%
X038-197 | OLD FORT FOUR PARK - PLAY EQUIPMENT | 1997-12-17 | 1998-01-07 | 1996-10-03 | 807864 | 1055000 | 1998-07-20 | 1999-02-14 | 1999-08-06 | GI | X | Bronx Team | 13.6021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 30.59%
X039-101MA | PELHAM BAY PARK - BRONX VICTORY MEM. MONUMENT LANDSCAPING | 2001-01-31 | 2001-04-03 | 2000-08-07 | 698794 | 800000 | 2002-05-06 | 2002-12-01 | 2002-11-29 | GI | X | Bronx Team | 13.4571 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 14.48%
X039-102M/402M | ORCHARD BEACH - CONCESSION AREA | 2002-12-20 | 2003-03-24 | 2001-10-28 | 382236 | 800000 | 2003-11-17 | 2004-04-14 | 2004-05-24 | GI | X | Bronx Team | 12.8538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 109.3%
X039-103MA | AMERICAN BOY SCULPTURE - PEDESTAL DESIGN & RELOCATION |  | 2003-03-27 | 2003-02-24 | 164000 | 308000 | 2004-07-12 | 2004-11-18 | 2004-11-18 | GI | X | Bronx Team | 12.0076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.8%
X039-105M | BARTOW-PELL MANSION - SEPTIC TANK REPLACEMENT | 2005-02-15 | 2005-09-15 | 2004-10-07 | 167502.5 | 265000 | 2006-05-22 | 2006-09-18 | 2006-09-18 | GI | X | Bronx Team | 12.0288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.21%
X039-194 | PELHAM BAY PARK - PORTIONS OF THE BARTOW-PELL MANSION | 1997-02-15 | 1997-04-11 | 1995-07-17 | 172780 | 254000 | 1997-08-25 | 1998-02-20 | 1998-02-18 | FI | X | Bronx Team | 12.0598 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 47.01%
X039-197/497 | PORTIONS OF ORCHARD BEACH BATHHOUSE | 1998-03-30 | 1998-05-01 | 1996-10-17 | 1373773 | 5878000 | 1999-09-13 | 2001-01-04 | 2000-10-05 | GI | CPM | Construction Project Manager | 14.1331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91 | 327.9%
X039-198 | ORCHARD BEACH PLGD. - PORTION OF | 1997-12-31 | 1998-02-17 | 1997-09-11 | 1932424 | 2489000 | 1998-07-06 | 1999-08-29 | 1999-11-04 | GI | X | Bronx Team | 14.4743 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 28.8%
X039-199A | PELHAM BAY PARK - BRONX VICTORY MEMORIAL MONUMENT RESTORATION | 1999-02-28 | 1999-07-28 | 1998-08-26 | 735635 | 877000 | 2000-03-20 | 2000-12-14 | 2001-11-05 | GI | X | Bronx Team | 13.5085 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326 | 19.22%
X039-200M | PELHAM BAY PARK - BALLFIELDS & PATHS | 2000-02-28 | 2000-02-18 | 1999-09-28 | 317151 | 675000 | 2000-08-01 | 2000-11-28 | 2001-06-15 | GI | CPM | Construction Project Manager | 12.6671 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 112.8%
X039-202M | (ELECTRICAL) ORCHARD BEACH - CONCESSION AREA | 2002-03-15 | 2003-03-24 | 2001-10-28 | 48821 | 48821 | 2003-11-17 | 2004-04-14 | 2004-05-24 | GI | X | Bronx Team | 10.7959 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0%
X039-297 | (ELECTRICAL) PORTIONS OF BATH HOUSE @ ORCHARD BEACH | 1998-03-30 | 1998-05-01 | 1996-10-17 | 280980 | 281000 | 1999-09-13 | 2001-01-04 | 2002-05-20 | FI | CPM | Construction Project Manager | 12.546 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501 | 0.007118%
X039-298/498 | PELHAM BAY PARK - PLGD FOR ALL CHILDREN | 1998-03-31 | 1998-05-01 | 1997-10-01 | 1979371.75 | 2249000 | 1999-07-06 | 2000-07-03 | 2001-01-10 | GI | X | Bronx Team | 14.4983 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 13.62%
X039-299 | ORCHARD BEACH BATHHOUSE - ACM REMOVAL F/UNITS 1-5 | 1998-12-29 | 1998-12-29 | 1998-12-04 | 239725 | 349000 | 1999-06-02 | 1999-08-30 | 1999-09-08 | GI | AS | Other | 12.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 45.58%
X039-301M | PELHAM BAY PARK - BRIDLE PATHS | 2001-03-15 | 2001-03-12 | 2000-09-07 | 366700 | 540000 | 2001-10-29 | 2002-04-26 | 2002-04-26 | GI | CPM | Construction Project Manager | 12.8123 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.26%
X039-302M | (PLUMBING) ORCHARD BEACH - CONCESSION AREA | 2002-03-15 | 2003-03-25 | 2001-10-28 | 54800 | 54800 | 2003-11-17 | 2004-04-14 | 2004-05-24 | GI | X | Bronx Team | 10.9114 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0%
X039-397 | (PLUMBING) PORTIONS OF BATH HOUSE @ ORCHARD BEACH | 1998-03-30 | 1998-05-01 | 1996-10-17 | 632820 | 633000 | 1999-09-13 | 2001-01-04 | 2001-01-04 | GI | CPM | Construction Project Manager | 13.3579 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02844%
X039-398 | PELHAM BAY PARK LAGOON - SALT MARSH | 1999-03-29 | 1999-04-06 | 1998-03-03 | 562926 | 1172000 | 2000-03-13 | 2000-06-10 | 2000-09-19 | GI | CPM | Construction Project Manager | 13.2409 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 108.2%
X039-496 | BRONX-PELHAM PARKWAY BIKEWAY EXTENSION | 1997-12-22 | 1998-03-24 | 1996-09-19 | 1409438 | 1743000 | 1998-11-23 | 1999-08-19 | 1999-10-29 | GI | X | Bronx Team | 14.1587 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 23.67%
X039-497 | (H&V) PORTIONS OF BATH HOUSE @ ORCHARD BEACH | 1998-03-30 | 1998-05-01 | 1996-10-17 | 253870 | 254000 | 1999-09-13 | 2001-01-04 | 2001-01-04 | GI | CPM | Construction Project Manager | 12.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05121%
X039-498 | (MECHANICAL) PELHAM BAY PARK - PLGD FOR ALL CHILDREN | 1998-03-31 | 1998-05-01 | 1997-10-01 | 71526 | 72000 | 1999-07-06 | 2000-07-03 | 2001-04-05 | GI | X | Bronx Team | 11.1778 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276 | 0.6627%
X039-502M | PELHAM BAY PARK - BRIDLE PATHS | 2002-12-02 | 2002-12-20 | 2001-11-02 | 330631 | 526000 | 2003-12-01 | 2004-04-28 | 2004-05-19 | GI | X | Bronx Team | 12.7088 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 59.09%
X039-602M | PELHAM BAY PARK - RUNNING TRACK & INTERIOR FIELD | 2003-03-01 | 2003-04-21 | 2001-12-24 | 1482000 | 2403000 | 2004-02-02 | 2004-09-28 | 2004-09-28 | GI | X | Bronx Team | 14.2089 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.15%
X040-100M | POE PARK | 2000-03-22 | 2000-03-31 | 1999-08-30 | 877832 | 1052000 | 2000-10-11 | 2001-07-07 | 2002-02-28 | GI | X | Bronx Team | 13.6852 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 19.84%
X040-104M;604M | POE PARK - PORTIONS OF BANDSTAND | 2004-03-12 | 2004-03-30 | 2004-03-18 | 179786 | 365000 | 2005-03-07 | 2005-09-02 | 2005-06-29 | GI | X | Bronx Team | 12.0995 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65 | 103%
X040-604M | (ELECTRICAL) POE PARK - PORTIONS OF BANDSTAND | 2004-03-12 | 2004-04-14 | 2004-03-18 | 21258 | 22000 | 2005-03-07 | 2005-09-02 | 2005-06-29 | GI | X | Bronx Team | 9.9645 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65 | 3.49%
X044-100M | ST. JAMES RECREATION CTR. - GYM FLOOR | 1999-12-30 | 2000-01-19 | 1999-08-06 | 49875 | 84000 | 2000-05-30 | 2000-08-27 | 2000-07-26 | GI | X | Bronx Team | 10.8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32 | 68.42%
X044-101M/401M | ST. JAMES PARK - RECREATION CENTER | 2002-01-31 | 2002-05-20 | 2001-08-14 | 505777 | 1751000 | 2003-05-14 | 2005-12-31 | 2007-05-07 | FI | X | Bronx Team | 13.1339 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 246.2%
X044-196/296 | ST. JAMES GOLDEN AGE CTR - KITCHEN | 1997-01-30 | 1997-02-04 | 1995-09-06 | 94600 | 304000 | 1997-06-23 | 1997-10-20 | 1998-12-17 | GI | X | Bronx Team | 11.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 221.4%
X044-197 | ST. JAMES PARK | 1997-11-14 | 1998-03-30 | 1996-10-03 | 487879 | 657000 | 1998-08-10 | 1999-02-05 | 1999-01-20 | GI | X | Bronx Team | 13.0978 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 34.66%
X044-301MD | (PLUMBING) ST. JAMES PARK - RECREATION CENTER | 2002-01-31 | 2004-07-27 | 2001-08-14 | 142272 | 142272 | 2005-06-06 | 2005-11-02 | 2007-05-07 | FI | X | Bronx Team | 11.8655 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 0%
X044-401MD | (H&V) ST. JAMES PARK - RECREATION CENTER | 2002-01-31 | 2004-07-27 | 2001-08-14 | 58906 | 59000 | 2005-06-06 | 2005-11-02 | 2007-05-07 | FI | X | Bronx Team | 10.9837 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 0.1596%
X045-105M | ST. MARY'S PARK - CONSTR OF SYNTHETIC TURF | 2004-12-15 | 2005-01-31 | 2004-08-16 | 287340 | 346000 | 2005-08-22 | 2006-02-17 | 2006-04-14 | GI | X | Bronx Team | 12.5684 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 20.41%
X045-198/498 | ST. MARY'S PARK - COMFORT STATION | 1998-01-31 | 1998-03-23 | 1997-09-09 | 395093 | 557000 | 1998-10-05 | 1999-10-04 | 2000-04-11 | GI | X | Bronx Team | 12.8869 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 40.98%
X045-298 | (ELECTRICAL) ST. MARY'S PARK - COMFORT STATION | 1998-01-31 | 1998-03-23 | 1997-09-09 | 18000 | 23000 | 1998-10-05 | 1999-10-04 | 2000-04-11 | GI | X | Bronx Team | 9.7981 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 27.78%
X045-398 | (PLUMBING) ST. MARY'S PARK - COMFORT STATION | 1998-01-31 | 1998-03-23 | 1997-09-09 | 60749 | 61000 | 1998-10-05 | 1999-10-04 | 2000-04-11 | GI | X | Bronx Team | 11.0145 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 0.4132%
X045-498 | (H&V) ST. MARY'S PARK - COMFORT STATION | 1998-01-31 | 1998-03-23 | 1997-09-09 | 14358 | 14000 | 1998-10-05 | 1999-10-04 | 2000-04-11 | GI | X | Bronx Team | 9.5721 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | -2.493%
X045-598A | ST. MARY'S REC. CTR. - GYMNASIUM FLOORS | 1998-04-17 | 1998-06-18 | 1998-03-25 | 89997 | 152000 | 1999-01-15 | 1999-03-15 | 1999-02-19 | GI | X | Bronx Team | 11.4075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24 | 68.89%
X046-101MA | SETON FALLS PARK - FRESHWATER MARSH | 2001-03-23 | 2001-08-06 | 2000-08-17 | 292991 | 473000 | 2002-01-17 | 2002-10-13 | 2002-10-11 | GI | X | Bronx Team | 12.5879 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 61.44%
X046-102M | SETON FALLS PARK - BASKETBALL & TENNIS COURTS | 2002-03-29 | 2002-04-05 | 2001-08-24 | 402261 | 666000 | 2002-12-10 | 2003-06-07 | 2003-07-02 | GI | X | Bronx Team | 12.9049 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 65.56%
X046-105M | SETON FALLS PARK - PATHS & NATURE TRAILS | 2005-08-25 | 2006-11-15 | 2005-01-28 | 772942 | 1171000 | 2006-09-05 | 2007-03-03 | 2007-07-10 | FI | X | Bronx Team | 13.558 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 51.5%
X046-201MA | SETON FALLS PARK - GROTTO, PERIMETER PATHS, & FENCES | 2001-06-02 | 2001-10-25 | 2000-11-09 | 219996 | 424000 | 2002-04-29 | 2002-09-25 | 2002-09-25 | GI | X | Bronx Team | 12.3014 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.73%
X04A-198 | PARQUE DE LOS NINOS | 1998-03-31 | 1998-04-02 | 1997-12-01 | 432373 | 575000 | 1998-09-28 | 1999-03-26 | 1999-03-26 | GI | CPM | Construction Project Manager | 12.977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.99%
X081-106M | PORTIONS OF THE MOUNT EDEN MALLS (ON MT EDEN PKWY & E. MT EDEN AVE, EAST OF WALTON AVE) | 2006-03-31 | 2006-04-04 | 2005-12-05 | 370166.59 | 805000 | 2006-11-13 | 2007-05-11 | 2007-06-28 | FI | X | Bronx Team | 12.8217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 117.5%
X085-100M | SLATTERY PLAYGROUND | 2000-03-31 | 2000-03-21 | 1999-09-01 | 867496 | 1125000 | 2000-10-30 | 2001-04-27 | 2001-08-13 | GI | CPM | Construction Project Manager | 13.6734 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 29.68%
X088-101M | PUGSLEY CREEK PARK - FIELD OF DREAMS BALLFIELD - CONSTR OF WATER SERVICE | 2000-10-30 | 2000-12-30 | 2000-10-19 | 46500 | 75000 | 2001-05-21 | 2001-09-17 | 2001-10-12 | GI | X | Bronx Team | 10.7472 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 61.29%
X092-100M | VAN CORTLANDT PARK - PORTION OF CLASSIC PLGD. | 2001-03-30 | 2001-04-05 | 1999-10-05 | 715743 | 954000 | 2001-09-17 | 2002-03-15 | 2002-03-21 | GI | X | Bronx Team | 13.4811 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 33.29%
X092-196 | VCP - SO.WEST CORNER PLAY AREA | 1996-10-31 | 1996-10-30 | 1995-09-26 | 1295450 | 1646000 | 1997-05-05 | 1998-05-04 | 1998-05-04 | GI | X | Bronx Team | 14.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.06%
X092-197 | VAN CORTLANDT PARK STADIUM RUNNING TRACK & RELATED SITE WORK | 1997-02-28 | 1997-07-08 | 1996-11-26 | 872434 | 1181000 | 1998-05-11 | 1999-02-19 | 1998-11-23 | GI | X | Bronx Team | 13.679 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88 | 35.37%
X092-198A | VAN CORTLANDT PARK - LAKES RESTORATION & ACCESS | 2000-02-08 | 2000-11-20 | 1997-07-23 | 6630105 | 8751000 | 2001-10-04 | 2003-04-06 | 2003-07-03 | GI | X | Bronx Team | 15.7071 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 31.99%
X092-199 | VAN CORTLANDT PARK - ELM POND - EP TOXICITY TESTING | 1998-11-15 | 1998-11-09 | 1998-10-15 | 50732 | 51000 | 1999-05-03 | 1999-06-16 | 1999-06-08 | GI | X | Bronx Team | 10.8343 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 0.5283%
X092-200M | VAN CORTLANDT PARK - PADDY'S FIELD | 2000-02-28 | 2000-03-13 | 1999-10-15 | 418871 | 688000 | 2000-08-09 | 2000-12-16 | 2001-06-25 | GI | X | Bronx Team | 12.9453 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 64.25%
X092-201M | VAN CORTLANDT PARK - INDIAN FIELDS - 8 TENNIS COURTS | 2001-03-30 | 2001-03-30 | 2000-10-11 | 749517 | 1000000 | 2001-07-09 | 2002-01-04 | 2002-01-04 | GI | X | Bronx Team | 13.5272 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.42%
X092-203M | VAN CORTLAND PARK/PARADE GROUND CROSS COUNTRY RUNNING TRACK - CONSTR OF SHADE STRUCTURE & SITE WORK | 2003-12-31 | 2004-07-07 | 2003-05-06 | 174326 | 175000 | 2005-05-23 | 2005-11-18 | 2005-11-28 | GI | RCU | Requirements Contract Unit | 12.0687 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 10 | 0.3866%
X092-300M | VAN CORTLANDT PARK - INDIAN FIELD BOCCI CTS. (LIGHTING) | 1999-11-26 | 1999-12-25 | 1999-10-25 | 59264 | 125000 | 2000-09-18 | 2001-01-15 | 2001-01-17 | GI | X | Bronx Team | 10.9898 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 110.9%
X092-303M | VAN CORTLANDT PARK - OLD TIBBETS BROOK WETLAND RESTORATION | 2003-10-20 | 2004-02-20 | 2003-05-16 | 388203 | 529000 | 2004-09-13 | 2005-06-09 | 2005-06-09 | GI | X | Bronx Team | 12.8693 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.27%
X092-400MA/700MA | VAN CORTLANDT PARK/SATURN PLGD - CONSTR OF A PLGD & COMFORT STATION | 2000-10-30 | 2001-01-19 | 2005-06-01 | 1929041 | 2776000 | 2005-10-18 | 2006-10-17 | 2007-03-09 | FI | CROT | Croton Unit | 14.4725 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 43.91%
X092-500MA | (ELECTRICAL) VAN CORTLANDT PARK - CONSTR OF A PLGD & COMFORT STATION | 2000-10-30 | 2001-01-16 | 2005-06-01 | 59988 | 59988 | 2006-01-30 | 2007-01-29 | 2007-03-09 | FI | CROT | Croton Unit | 11.0019 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0%
X092-600MA | (PLUMBING) VAN CORTLANDT PARK - CONSTR OF A PLGD & COMFORT STATION | 2000-10-30 | 2001-01-16 | 2005-06-01 | 92419.6 | 93000 | 2006-01-30 | 2007-01-29 | 2007-03-09 | FI | CROT | Croton Unit | 11.4341 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0.628%
X092-700MA | (H&V) VAN CORTLANDT PARK - CONSTR OF A PLGD & COMFORT STATION | 2000-10-30 | 2001-01-16 | 2005-06-01 | 51272 | 20180 | 2006-01-30 | 2007-01-29 | 2007-03-09 | FI | CROT | Croton Unit | 10.8449 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | -60.64%
X101-195D2/197T/297T | CO-OP CITY LITTLE LEAGUE FIELDS FACILITY | 1997-02-01 | 1999-01-21 | 1998-02-02 | 250191 | 518000 | 1999-09-13 | 2000-06-08 | 2000-06-08 | GI | X | Bronx Team | 12.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107%
X101-197T | (ELECTRICAL) CO-OP CITY LITTLE LEAGUE FACILITY | 1998-12-31 | 1999-01-19 | 1997-03-26 | 27899 | 28000 | 1999-09-13 | 2000-06-08 | 2000-06-08 | GI | X | Bronx Team | 10.2363 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.362%
X101-199 | HUTCHINSON RIVER PKWY - BIKEWAY/WALKWAYS | 2001-03-31 | 2004-03-01 | 1999-06-07 | 683178 | 946000 | 2004-11-17 | 2005-05-15 | 2006-04-26 | GI | X | Bronx Team | 13.4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | 38.47%
X101-297T | (MECHANICAL) CO-OP CITY LITTLE LEAGUE FACILITY | 1998-12-31 | 1999-01-19 | 1997-03-26 | 71840 | 72000 | 1999-09-13 | 2000-06-08 | 2000-06-08 | GI | X | Bronx Team | 11.1822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2227%
X102-105M | VINCENT CICCARONE PLGD | 2005-01-15 | 2005-06-30 | 2005-06-08 | 1751899 | 2798000 | 2006-05-15 | 2007-05-14 | 2007-07-20 | FI | X | Bronx Team | 14.3762 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 59.71%
X103-101M | PEOPLES PARK PLAYGROUND | 2001-03-31 | 2001-03-23 | 2000-08-22 | 735588 | 828000 | 2001-08-20 | 2002-02-15 | 2002-02-13 | GI | X | Bronx Team | 13.5084 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 12.56%
X103-102M | PEOPLES PLGD - BALLFIELD & BASKETBALL CTS. | 2002-03-29 | 2002-02-22 | 2001-10-17 | 333031 | 464000 | 2002-09-23 | 2003-02-19 | 2003-06-19 | GI | X | Bronx Team | 12.716 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 39.33%
X104-101M | WILLIAMSBRIDGE OVAL - TENNIS CTS & ADJACENT SLOPES | 2001-02-19 | 2001-03-14 | 2000-08-28 | 1112583 | 1410000 | 2001-07-30 | 2002-03-26 | 2002-07-03 | GI | X | Bronx Team | 13.9222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 26.73%
X104-102M | WILLIAMSBRIDGE OVAL - PHASE I | 2002-07-24 | 2003-03-26 | 2001-10-03 | 320144 | 534000 | 2005-07-11 | 2005-12-07 | 2006-03-16 | GI | X | Bronx Team | 12.6765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 66.8%
X104-198 | WILLIAMSBURG OVAL ROOF | 1997-09-30 | 1997-10-23 | 1997-07-01 | 397251 | 533000 | 1998-03-02 | 1998-10-27 | 1998-10-08 | GI | X | Bronx Team | 12.8923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 34.17%
X108-196/296 | PORTION OF BELMONT PK.& C.S. | 1996-12-31 | 1997-02-13 | 1995-09-21 | 1033278 | 1439000 | 1997-07-21 | 1998-06-15 | 1998-06-16 | GI | X | Bronx Team | 13.8482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 39.27%
X108-296 | PORTION OF BELMONT PK & C.S. MECHANICAL WORK | 1996-12-31 | 1997-02-18 | 1996-12-17 | 41340 | 50000 | 1997-07-21 | 1998-06-15 | 1998-06-16 | GI | X | Bronx Team | 10.6296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 20.95%
X115-101M | MOTT PLAYGROUND RECONSTRUCTION | 2000-11-30 | 2001-02-23 | 2000-07-18 | 716114 | 887000 | 2001-07-16 | 2002-03-12 | 2002-03-11 | GI | X | Bronx Team | 13.4816 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 23.86%
X118-198 | SOUNDVIEW PARK - BICYCLE/PEDESTRIAN WATERFRONT PATH | 1998-02-15 | 1998-04-15 | 1997-07-22 | 1028407 | 1615000 | 1999-04-19 | 2000-01-13 | 2000-06-08 | GI | X | Bronx Team | 13.8435 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 57.04%
X120-106M | HIGHBRIDGE GATEHOUSE - PORTIONS OF |  | 2005-11-14 | 2005-09-21 | 659958 | 843000 | 2006-09-18 | 2007-04-15 | 2007-08-14 | FI | X | Bronx Team | 13.3999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 27.74%
X120-199 | HIGHBRIDGE PK - ENTRANCE WALK & SEATING AREA @ UNIVERSITY AVE. | 1999-11-08 | 1999-12-17 | 1999-06-07 | 476568 | 637000 | 2000-09-25 | 2001-03-23 | 2001-12-28 | GI | X | Bronx Team | 13.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 33.66%
X121-199 | BUFANO (WATERBURY) PARK - ROLLER HOCKEY RINK & BASKETBALL CTS | 1999-11-08 | 1999-11-10 | 1999-04-08 | 458567 | 785000 | 2000-04-25 | 2001-01-19 | 2001-07-16 | GI | X | Bronx Team | 13.0359 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 71.19%
X124-197 | WATSON GLEASON PLGD. | 1997-07-15 | 1997-12-22 | 1996-11-19 | 509540 | 676000 | 1998-05-11 | 1998-11-06 | 1998-10-30 | GI | X | Bronx Team | 13.1413 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 32.67%
X124-199 | WATSON & GLEASON PLGD. - COURT AREAS, PAVEMENTS, SITE WORK | 2001-03-26 | 2001-03-28 | 1998-12-02 | 803972 | 1015000 | 2001-07-30 | 2002-03-26 | 2002-03-26 | GI | CPM | Construction Project Manager | 13.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.25%
X136-197 | HARRIS PARK BALLFIELD LIGHTING | 1997-03-31 | 1997-04-07 | 1996-11-13 | 419230 | 554000 | 1998-02-02 | 1998-07-01 | 1998-07-01 | GI | X | Bronx Team | 12.9462 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.15%
X141-196/396 | P.S. 21 ("PLAYGROUND 21") PLGD. & C.S. | 1996-10-19 | 1997-04-02 | 1995-10-11 | 569000 | 871000 | 1997-08-04 | 1998-03-31 | 1998-06-25 | GI | CPM | Construction Project Manager | 13.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 53.08%
X141-296 | (ELECTRICAL) P.S. 21 (PLAYGROUND 21) PLGD & C.S. | 1996-10-19 | 1997-04-02 | 1995-10-11 | 9964 | 10000 | 1997-08-04 | 1998-03-31 | 1998-06-25 | GI | CPM | Construction Project Manager | 9.2067 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0.3613%
X141-396 | (PLUMBING) P.S.21 (PLAYGROUND 21) PLGD & C.S. | 1996-10-19 | 1997-04-02 | 1995-10-11 | 27560 | 38000 | 1997-08-04 | 1998-03-31 | 1998-06-25 | GI | CPM | Construction Project Manager | 10.2241 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 37.88%
X142-101M | RIVERDALE PARK - FRESHWATER WETLAND & ADJACENT SLOPES | 2002-02-18 | 2002-05-15 | 2001-06-14 | 241084 | 480000 | 2003-03-24 | 2003-09-19 | 2003-09-19 | GI | X | Bronx Team | 12.3929 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.1%
X151-197 | PORTION OF CASTLE HILL PLAYGROUND | 1997-03-31 | 1997-04-02 | 1996-12-17 | 386276 | 529000 | 1997-11-03 | 1998-04-01 | 1998-03-31 | GI | X | Bronx Team | 12.8643 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 36.95%
X155-102M | PATTERSON PLAYGROUND | 2002-03-29 | 2002-12-02 | 2001-10-29 | 612125 | 892000 | 2004-03-22 | 2004-09-17 | 2005-02-22 | GI | X | Bronx Team | 13.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 45.72%
X157-199 | MAZZEI PLAYGROUND | 1999-04-12 | 1999-04-15 | 1998-12-02 | 479937 | 622000 | 1999-08-09 | 2000-04-04 | 2000-04-11 | GI | CPM | Construction Project Manager | 13.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 29.6%
X163-103MA | LORETO PARK - CONSTR OF ROLLER HOCKEY RINK | 2004-02-18 | 2004-10-15 | 2003-09-28 | 974227 | 1333000 | 2005-06-06 | 2005-12-02 | 2006-02-23 | GI | X | Bronx Team | 13.7894 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 36.83%
X168-195 | RECONSTR OF PLGD. BET. NELSON & WOODYCREST AVE. | 1996-12-27 | 1997-01-22 | 1995-04-19 | 939021 | 1722000 | 1997-06-02 | 1998-02-26 | 1998-05-26 | GI | CPM | Construction Project Manager | 13.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 83.38%
X174-105M | WEBSTER PLGD | 2005-12-31 | 2006-03-20 | 2005-01-21 | 1367802.5 | 1817000 | 2006-07-10 | 2007-07-09 | 2007-06-13 | FI | CROT | Croton Unit | 14.1287 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26 | 32.84%
X177-100M | PARKER (I.S. 127) PLAYGROUND - PORTION OF PLGD. | 2000-03-03 | 2000-03-15 | 1999-09-24 | 374518 | 466000 | 2001-04-05 | 2001-08-02 | 2001-10-26 | GI | X | Bronx Team | 12.8334 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 24.43%
X178-104M | MATTHEWS/MULINER PLAYGROUND | 2004-03-01 | 2004-03-05 | 2003-09-02 | 1234096 | 1536000 | 2005-03-28 | 2005-12-22 | 2006-11-30 | FI | X | Bronx Team | 14.0258 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343 | 24.46%
X182-106MA | MILLBROOK HOUSES PLGD - PORTION OF | 2006-03-01 | 2006-03-01 | 2005-12-05 | 947000 | 1425000 | 2007-05-30 | 2008-02-23 | 2007-11-16 | FI | X | Bronx Team | 13.7611 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99 | 50.48%
X183-104MA | PLGD ADJ TO P.S. 101/BRUCKNER PLGD - SKATE PARK | 2005-02-28 | 2004-02-19 | 2003-11-25 | 382671.66 | 491000 | 2005-08-03 | 2006-01-29 | 2006-02-24 | GI | X | Bronx Team | 12.8549 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 28.31%
X191-105M | BICENTENNIAL VETERAN'S MEMORIAL PARK - BALLFIELDS | 2005-03-15 | 2005-03-25 | 2004-11-01 | 633783.1 | 868000 | 2005-08-29 | 2006-02-04 | 2006-11-16 | GI | X | Bronx Team | 13.3595 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 36.96%
X195-101M | COLGATE CLOSE PLAYGROUND CONSTRUCTION | 2001-03-31 | 2001-03-23 | 2000-07-19 | 837434 | 1017000 | 2001-10-03 | 2002-04-30 | 2002-08-28 | GI | X | Bronx Team | 13.6381 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 21.44%
X195-102M | COLGATE CLOSE PARK- BASKETBALL HALF COURTS | 2002-03-29 | 2002-03-11 | 2002-01-16 | 214103 | 325000 | 2002-08-14 | 2003-01-10 | 2002-12-11 | GI | X | Bronx Team | 12.2742 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | 51.8%
X195-198 | COLGATE CLOSE PARK - MASTER PLAN, BALLFIELD & SITTING AREA | 1999-03-31 | 1999-04-27 | 1998-11-17 | 821587 | 1040000 | 1999-09-07 | 2000-06-02 | 2000-05-31 | GI | X | Bronx Team | 13.619 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 26.58%
X196-105M | HAFFEN PARK - ATHLETIC FIELD | 2005-05-30 | 2005-06-20 | 2005-01-11 | 822351.76 | 1267000 | 2005-12-19 | 2006-06-16 | 2006-07-21 | GI | X | Bronx Team | 13.6199 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 54.07%
X196-199 | HAFFEN PARK - BALLFIELD LIGHTING & SITE WORK | 2000-01-31 | 2000-03-21 | 1998-07-23 | 667000 | 906000 | 2000-09-11 | 2001-03-09 | 2001-07-06 | GI | CPM | Construction Project Manager | 13.4105 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 35.83%
X201-106M | SETON PARK - ONE BASEBALL INFIELD | 2006-03-01 | 2006-02-09 | 2005-12-14 | 524347 | 837000 | 2006-08-21 | 2007-02-16 | 2007-05-17 | FI | X | Bronx Team | 13.1699 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 59.63%
X202-106M | MARBLE HILL PARK - SYNTH TURF | 2005-12-31 | 2006-03-15 | 2006-01-27 | 413259 | 500000 | 2006-09-11 | 2007-06-07 | 2007-05-04 | FI | X | Bronx Team | 12.9318 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34 | 20.99%
X222-100M | GOUVERNEUR MORRIS PLAYGROUND - BASKETBALL CTS LIGHTING | 1999-12-22 | 1999-11-30 | 1999-08-09 | 187325 | 328000 | 2000-06-05 | 2000-12-01 | 2001-06-29 | GI | X | Bronx Team | 12.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 75.1%
X222-199 | GOVERNEUR MORRIS PLAYGROUND | 1999-03-31 | 1999-03-31 | 1998-07-21 | 781504 | 1169000 | 1999-09-13 | 2000-06-08 | 2000-07-13 | GI | X | Bronx Team | 13.569 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 49.58%
X232-103M | LOIS B. BURNS PLGD - RECONSTR. OF A PORTION | 2003-03-28 | 2003-03-21 | 2002-09-19 | 577788 | 803000 | 2003-09-03 | 2004-05-29 | 2004-10-28 | GI | X | Bronx Team | 13.267 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 38.98%
X237-100M | YANKEE STADIUM - CONCRETE SURFACES & SEALER & STRUCTURAL STEEL | 1999-09-30 | 1999-09-21 | 1999-07-30 | 538427 | 1026000 | 2000-01-18 | 2001-01-16 | 2001-01-17 | GI | TS | Technical Services (Randalls Isl.) | 13.1964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 90.56%
X237-101M | YANKEE STADIUM - ASPHALT PAVEMENTS, DRAINAGE & MISC. WORK | 2001-09-19 | 2001-09-18 | 2001-06-13 | 738655 | 934000 | 2002-07-15 | 2003-07-14 | 2003-07-10 | FI | TS | Technical Services (Randalls Isl.) | 13.5126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -4 | 26.45%
X237-103MA | YANKEE STADIUM - PAVEMENTS/CLF/SEATS/STAIRS/ETC. |  | 2003-09-11 | 2003-04-14 | 798691 | 964000 | 2004-03-19 | 2005-03-18 | 2005-03-14 | FI | TS | Technical Services (Randalls Isl.) | 13.5907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -4 | 20.7%
X237-104M | YANKEE STADIUM |  | 2004-01-23 | 2004-01-06 | 300000 | 360000 | 2004-07-26 | 2005-07-25 | 2005-07-13 | FI | TS | Technical Services (Randalls Isl.) | 12.6115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -12 | 20%
X237-198 | YANKEE STADIUM - TICKET BOOTHS & FLOORING | 1998-03-31 | 1998-05-01 | 1998-02-13 | 469150 | 610000 | 1998-08-24 | 1999-03-21 | 1999-03-17 | GI | X | Bronx Team | 13.0587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 30.02%
X237-200M | YANKEE STADIUM - ASPHALT/CONCRETE SURFACES & MISC. WORK | 2000-09-13 | 2000-11-06 | 2000-06-12 | 789800 | 1015000 | 2001-03-19 | 2002-03-18 | 2002-10-31 | FI | TS | Technical Services (Randalls Isl.) | 13.5795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 227 | 28.51%
X237-296T | YANKEE STADIUM EXPANSION JOINTS, WATERPROOFING, ETC. @ #3 | 1997-03-25 | 1997-03-25 | 1996-01-17 | 1053084 | 1246000 | 1997-07-31 | 1998-07-30 | 1998-07-24 | GI | X | Bronx Team | 13.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | 18.32%
X237-497 | YANKEE STADIUM -SCOREBOARD & SEATING AREA | 1997-04-30 | 1997-04-28 | 1997-01-08 | 838690 | 1499000 | 1998-02-24 | 1999-02-23 | 1999-02-23 | GI | X | Bronx Team | 13.6396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.73%
X237-797 | YANKEE STADIUM PARKING STRUCTURE #8 | 1997-03-31 | 1997-03-31 | 1997-01-08 | 1063165 | 1365000 | 1997-08-04 | 1998-04-30 | 1998-03-26 | GI | X | Bronx Team | 13.8768 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35 | 28.39%
X237-897 | YANKEE STADIUM HANDICAP ACCESSIBLE RESTROOMS | 1997-03-20 | 1997-03-20 | 1997-01-08 | 467418 | 570000 | 1997-07-29 | 1998-04-24 | 1998-04-03 | GI | X | Bronx Team | 13.055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21 | 21.95%
X241-100M | HOE PARK - CONSTR. OF PLAYGROUND | 2000-01-27 | 2000-02-02 | 1999-09-21 | 535832 | 785000 | 2000-11-15 | 2001-05-13 | 2001-07-25 | GI | CPM | Construction Project Manager | 13.1916 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 46.5%
X250-197 | KINGSBRIDGE HTS COMMUNITY CTR - EXT CORNICE & MISC WORK | 1996-12-20 | 1997-02-21 | 1996-08-19 | 241031 | 308000 | 1997-06-09 | 1997-12-05 | 1998-06-19 | GI | X | Bronx Team | 12.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 27.78%
X252-102MA | BATHGATE AVENUE PARK - BALLFIELD & MISCELLANEOUS WORK | 2002-07-16 | 2003-03-26 | 2001-10-22 | 499908 | 769000 | 2004-04-05 | 2004-08-02 | 2005-06-24 | GI | X | Bronx Team | 13.1222 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326 | 53.83%
X252-197 | BATHGATE PARK PLGD | 1998-04-01 | 1998-04-04 | 1997-03-18 | 891280 | 1130000 | 1998-11-30 | 1999-08-26 | 1999-08-23 | GI | CPM | Construction Project Manager | 13.7004 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 26.78%
X253-105M | AMBROSINI PLGD & BALLFIELD |  | 2006-03-20 | 2005-01-21 | 1402025 | 1965000 | 2006-12-11 | 2007-12-10 | 2007-11-16 | FI | CROT | Croton Unit | 14.1534 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24 | 40.15%
X255-101MA | RAINEY PARK - PORTION OF THE ATHLETIC FIELDS | 2001-03-30 | 2001-09-13 | 2000-08-08 | 552178 | 819000 | 2002-09-09 | 2003-03-07 | 2003-05-19 | GI | CPM | Construction Project Manager | 13.2216 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 48.32%
X261-193/493 | CONSTR. OF WEST BRONX (HIGHBRIDGE HTS.) REC. CTR. | 1997-03-31 | 1997-04-10 | 1993-10-15 | 2678130 | 4278000 | 1997-10-13 | 1999-06-04 | 1999-05-26 | GI | X | Bronx Team | 14.8006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9 | 59.74%
X261-293 | (ELECTRICAL) CONSTR OF WEST BRONX (HIGHBRIDGE HTS) REC CTR | 1997-03-02 | 1997-04-02 | 1993-10-15 | 179840 | 180000 | 1997-10-13 | 1999-06-04 | 1999-05-26 | GI | X | Bronx Team | 12.0998 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9 | 0.08897%
X261-393 | (PLUMBING) CONSTR OF WEST BRONX (HIGHBRIDGE HTS) REC CTR | 1997-03-02 | 1997-04-02 | 1993-10-15 | 126560 | 127000 | 1997-10-13 | 1999-06-04 | 1999-05-26 | GI | X | Bronx Team | 11.7485 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9 | 0.3477%
X263-197 | QUARRY RD. BALLFIELDS | 1998-01-16 | 1998-03-30 | 1997-06-16 | 739956 | 917000 | 1998-08-10 | 1999-02-05 | 1998-12-23 | GI | CPM | Construction Project Manager | 13.5143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | 23.93%
X263-199/499 | QUARRY ROAD BALLFIELDS - CONSTR OF COMFORT STATION | 1999-03-31 | 1999-04-02 | 1998-08-03 | 387272 | 639000 | 1999-09-20 | 2000-09-13 | 2000-12-20 | GI | X | Bronx Team | 12.8669 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 65%
X263-299 | (ELECTRICAL) QUARRY ROAD BALLFIELDS - CONSTR OF COMFORT STATION | 1999-03-31 | 1999-04-02 | 1998-08-03 | 18607 | 30000 | 1999-10-18 | 2000-10-11 | 2000-12-20 | GI | X | Bronx Team | 9.8313 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 61.23%
X263-399 | (PLUMBING) QUARRY ROAD BALLFIELDS - CONSTR OF COMFORT STATION | 1999-03-31 | 1999-04-05 | 1998-08-03 | 106845 | 112000 | 1999-09-20 | 2000-09-13 | 2000-12-20 | GI | X | Bronx Team | 11.5791 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 4.825%
X263-499 | (H&V) QUARRY ROAD BALLFIELDS - CONSTR OF COMFORT STATION | 1999-03-31 | 1999-04-05 | 1998-08-03 | 19400 | 19000 | 1999-09-20 | 2000-09-13 | 2000-12-20 | GI | X | Bronx Team | 9.873 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | -2.062%
X265-196 | MACOMBS RD PARK @ W 175-176 STS | 1998-03-30 | 1998-05-04 | 1996-07-03 | 1354527 | 1743000 | 1998-08-24 | 1999-08-23 | 1999-11-23 | GI | X | Bronx Team | 14.119 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 28.68%
X266-100M/400M | VIDALIA (WEST FARMS) PARK & COMFORT STATION | 2000-03-31 | 2000-02-22 | 1999-10-21 | 1898666 | 3634000 | 2000-09-18 | 2001-09-12 | 2001-12-20 | GI | CPM | Construction Project Manager | 14.4567 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 91.4%
X266-200M | (ELECTRICAL) VIDALIA (WEST FARMS) PARK COMFORT STATION | 2000-03-31 | 2000-02-28 | 1999-10-21 | 15470 | 16000 | 2000-09-18 | 2001-09-12 | 2001-12-20 | GI | CPM | Construction Project Manager | 9.6467 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 3.426%
X266-300M | (PLUMBING) VIDALIA (WEST FARMS) PARK COMFORT STATION | 2000-03-31 | 2000-02-28 | 1999-10-21 | 79309 | 79000 | 2000-09-18 | 2001-09-12 | 2001-12-20 | GI | CPM | Construction Project Manager | 11.2811 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | -0.3896%
X266-400M | (H&V) VIDALIA (WEST FARMS) PARK COMFORT STATION | 2000-03-31 | 2000-02-18 | 1999-10-21 | 16626 | 17000 | 2000-09-18 | 2001-09-12 | 2001-12-20 | GI | CPM | Construction Project Manager | 9.7187 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2.249%
X267-196 | CONSTR. OF MITCHELL MALL @ E. 174TH ST. | 1996-12-31 | 1997-01-02 | 1996-01-02 | 186643 | 316000 | 1997-05-20 | 1997-11-15 | 1998-03-18 | GI | X | Bronx Team | 12.137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 69.31%
X271-102MA | GRANT AVE PARK - NORTHEAST PORTION | 2002-08-09 | 2002-08-21 | 2005-01-21 | 886373 | 3491000 | 2005-07-05 | 2006-01-30 | 2006-01-26 | GI | X | Bronx Team | 13.6949 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 293.9%
X271-198T | GRANT PLAYGROUND CONSTRUCTION | 2001-09-30 | 2001-09-21 | 1999-09-29 | 1127808 | 1553000 | 2002-09-08 | 2003-06-04 | 2003-09-04 | GI | X | Bronx Team | 13.9358 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 37.7%
X273-198 | COMMUNITY ROCK GARDEN PARK (HIAWATHA FALLS) | 1998-04-11 | 1998-04-17 | 1997-10-29 | 1211329 | 1587000 | 1999-01-04 | 1999-10-10 | 2000-06-21 | GI | CPM | Construction Project Manager | 14.0072 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 31.01%
X273-199A2 | COMMUNITY ROCK GARDEN (HIAWATHA FALLS) PARK - PHASE II | 1999-03-27 | 2001-09-24 | 1998-11-02 | 1028421 | 1486000 | 2002-08-12 | 2003-08-06 | 2003-10-16 | GI | CPM | Construction Project Manager | 13.8435 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 44.49%
X275-198A | MOSAIC SUCCESS GARDEN - WATER SV & SITE WORK | 1998-02-27 | 1999-02-10 | 1998-11-24 | 63798 | 68000 | 1999-06-28 | 1999-09-25 | 1999-09-24 | GI | X | Bronx Team | 11.0635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 6.586%
X280-199 | WASHINGTON PLAYGROUND @ 183RD & WASHINGTON AVE. | 1999-03-27 | 1999-12-10 | 1998-07-30 | 771917 | 929000 | 2000-05-30 | 2001-01-24 | 2001-05-03 | GI | X | Bronx Team | 13.5566 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 20.35%
X281-101M | STOP & GO (BATHGATE-CES 236) PLAYGROUND - NEW PLGD.F/SCHOOL | 2001-08-30 | 2001-08-22 | 2000-09-12 | 388529 | 606000 | 2002-05-28 | 2002-10-24 | 2002-10-24 | GI | X | Bronx Team | 12.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.97%
X283-199 | BILLINGSLEY TERRACE PLAYGROUND - CONSTRUCTION OF | 1999-01-31 | 1999-03-05 | 1998-07-01 | 653716 | 932000 | 1999-08-02 | 2000-04-27 | 2000-09-07 | GI | X | Bronx Team | 13.3904 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 42.57%
X286-198A | UNITY PARK | 1999-12-30 | 2000-03-27 | 1998-05-07 | 658685 | 1025000 | 2001-04-16 | 2001-11-11 | 2002-11-14 | GI | X | Bronx Team | 13.398 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 55.61%
X292-104M | MORRIS GARDEN PLAYGROUND | 2003-05-10 | 2004-03-01 | 2003-09-03 | 544845 | 778000 | 2004-11-08 | 2005-05-06 | 2005-06-30 | GI | X | Bronx Team | 13.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 42.79%
X300-101M | DAVIDSON AVENUE COMMUNITY PLGD - NEW CONSTRUCTION | 2001-12-30 | 2002-02-21 | 2001-05-01 | 474593 | 820000 | 2003-03-10 | 2003-11-04 | 2004-12-09 | GI | X | Bronx Team | 13.0702 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 72.78%
X302-101M | THORPE FAMILY PARK (PARK AVE & E.183 ST) - CONSTRUCT PLGD | 2002-03-29 | 2005-12-31 | 2001-05-01 | 1012467.5 | 1765000 | 2006-07-05 | 2007-07-04 | 2007-05-03 | FI | X | Bronx Team | 13.8279 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -62 | 74.33%
X307-102MA/402MA | BARRETTO POINT PARK & COMFORT STATION | 2001-12-15 | 2004-04-12 | 2001-04-27 | 4425280 | 7003000 | 2005-03-28 | 2006-09-18 | 2006-09-07 | GI | X | Bronx Team | 15.3028 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11 | 58.25%
X307-202MA | (ELECTRICAL) BARRETTO POINT PARK & COMFORT STATION | 2001-12-15 | 2001-12-21 | 2001-04-27 | 22963.2 | 22963 | 2005-03-28 | 2006-09-18 | 2006-09-07 | FI | X | Bronx Team | 10.0416 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11 | -0.000871%
X307-302MA | (PLUMBING) BARRETTO POINT PARK & COMFORT STATION | 2001-12-15 | 2001-12-21 | 2001-04-27 | 58200 | 58200 | 2005-03-28 | 2006-09-18 | 2006-09-07 | FI | X | Bronx Team | 10.9716 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11 | 0%
X307-402MA | (H&V) BARRETTO POINT PARK & COMFORT STATION | 2001-12-15 | 2003-11-25 | 2001-04-27 | 15955 | 15955 | 2005-03-28 | 2006-09-18 | 2006-09-07 | FI | X | Bronx Team | 9.6775 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11 | 0%
X334-104M | TRIANGLE (MOHEGAN AVE, CROTONA PKWY & E 179TH ST) - CONSTR OF SITTING AREA | 2004-10-15 | 2004-10-15 | 2004-04-26 | 684884 | 984000 | 2006-07-10 | 2007-01-05 | 2007-04-05 | FI | X | Bronx Team | 13.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 43.67%
XG-1005M | CBS 6-12 - PLANTING OF NEW & REPLACEMENT STREET TREES | 2005-03-11 | 2005-03-11 | 2005-01-07 | 364000 | 400000 | 2005-09-09 | 2006-06-05 | 2006-01-12 | FI | T | Tree Unit | 12.8049 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -144 | 9.89%
XG-100MA | BOILERS & HEATING SYSTEMS BOROWIDE | 1999-11-30 | 1999-12-13 | 1999-06-22 | 563797 | 686000 | 2001-04-30 | 2001-10-26 | 2002-01-24 | GI | X | Bronx Team | 13.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 21.68%
XG-101M | STREET TREE PLANTING - FY 2001 | 2000-07-31 | 2000-07-31 | 2000-07-17 | 318941 | 517000 | 2001-02-12 | 2001-08-10 | 2001-07-20 | GI | T | Tree Unit | 12.6728 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -21 | 62.1%
XG-101MR | STREET TREE PLANTING - FY 2002 | 2001-10-31 | 2001-10-24 | 2000-07-17 | 317578 | 359000 | 2002-03-11 | 2002-09-06 | 2002-07-22 | GI | T | Tree Unit | 12.6685 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -46 | 13.04%
XG-102M | BOILERS & HEATING SYSTEMS - 2 BRONX SITES | 2001-10-15 | 2001-10-05 | 2001-07-13 | 203825 | 273000 | 2002-05-21 | 2003-02-14 | 2003-10-23 | GI | X | Bronx Team | 12.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 33.94%
XG-103M | PAVEMENTS, LAWNS, LANDSCAPED AREAS & GENERAL SITE WORK | 2002-11-30 | 2002-12-05 | 2002-06-27 | 500000 | 780000 | 2003-06-02 | 2004-05-31 | 2004-06-16 | GI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 16 | 56%
XG-103MR | PAVEMENTS, LAWNS, LANDSCAPED AREAS & GENERAL SITE WORK | 2002-11-30 | 2002-12-05 | 2002-06-27 | 264200 | 316000 | 2004-08-16 | 2005-08-15 | 2005-06-10 | GI | RCU | Requirements Contract Unit | 12.4845 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -66 | 19.61%
XG-105M | PAVEMENTS, SIDEWALKS, LAWNS & GENERAL SITEWORK |  | 2005-03-31 | 2004-06-21 | 500000 | 600000 | 2005-09-19 | 2006-09-18 | 2006-10-18 | FI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 30 | 20%
XG-105MR | PAVEMENTS, SIDEWALKS, LAWNS & GENERAL SITEWORK |  | 2005-03-31 | 2004-06-21 | 500000 | 600000 | 2006-08-28 | 2007-08-27 | 2007-06-26 | FI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -62 | 20%
XG-1097 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & SITEWORK | 1997-01-31 | 1997-01-28 | 1996-11-14 | 1146418 | 1644000 | 1997-05-19 | 1998-05-18 | 1998-01-20 | GI | RCU | Requirements Contract Unit | 13.9522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -118 | 43.4%
XG-1098 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS. & SITEWORK | 1998-03-31 | 1998-02-26 | 1997-09-15 | 808891 | 1079000 | 1998-05-26 | 1999-05-25 | 1999-10-27 | GI | RCU | Requirements Contract Unit | 13.6034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 155 | 33.39%
XG-1098R | PLAY EQUIP, S.S., HANDBALL CTS., & SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-11 | 1997-09-15 | 809891 | 929000 | 1999-06-07 | 2000-06-05 | 2000-10-13 | GI | RCU | Requirements Contract Unit | 13.6047 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 130 | 14.71%
XG-1099 | FENCES, PAVEMENTS, LAWNS, GREENSTREETS & SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 427897 | 734000 | 2000-03-01 | 2000-11-25 | 2000-12-08 | GI | RCU | Requirements Contract Unit | 12.9666 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 13 | 71.54%
XG-1099R | FENCES, PAVEMENTS, LAWNS, GREENSTREETS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 426000 | 627000 | 2000-11-13 | 2001-08-09 | 2002-01-29 | GI | RCU | Requirements Contract Unit | 12.9622 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 173 | 47.18%
XG-1197 | PLAY EQUIPMENT, SAFETY SURFACE, PAVEMENTS, FENCES, & SITEWORK | 1997-04-15 | 1997-04-11 | 1997-03-12 | 430395 | 550000 | 1997-07-07 | 1998-01-02 | 1998-06-18 | FI | RCU | Requirements Contract Unit | 12.9725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 167 | 27.79%
XG-1198 | STREET TREE PLANTING F.Y. 1998 - C.B. 1-12 | 1997-12-31 | 1998-01-09 | 1997-11-28 | 237381 | 68000 | 1998-06-29 | 1999-06-28 | 1999-06-16 | GI | T | Tree Unit | 12.3774 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -12 | -71.35%
XG-198 | STREET TREE PLANTING F/FY 1998 | 1997-08-28 | 1997-08-28 | 1997-07-03 | 401035 | 924000 | 1997-12-10 | 1998-12-09 | 1998-11-12 | GI | T | Tree Unit | 12.9018 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -27 | 130.4%
XG-199 | STREET TREE PLANTING - F.Y. 1999 | 1998-10-30 | 1998-10-27 | 1998-07-09 | 320529 | 1438000 | 1999-03-29 | 2000-03-27 | 2000-03-24 | GI | T | Tree Unit | 12.6777 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -3 | 348.6%
XG-200MA | PELHAM BAY, SPLIT ROCK, VAN CORTLANDT GOLF COURSES - IRRIGATION SYSTEMS | 2000-01-04 | 1999-12-20 | 1999-10-22 | 12088350 | 13819000 | 2000-09-05 | 2001-03-03 | 2002-06-20 | FI | CPM | Construction Project Manager | 16.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474 | 14.32%
XG-201M | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2000-11-30 | 2000-10-06 | 2000-08-15 | 712804 | 932000 | 2001-02-21 | 2002-02-20 | 2002-03-21 | GI | RCU | Requirements Contract Unit | 13.477 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 29 | 30.75%
XG-201MR | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2001-06-30 | 2001-06-13 | 2001-06-13 | 700000 | 910000 | 2001-10-15 | 2002-10-14 | 2002-12-24 | GI | RCU | Requirements Contract Unit | 13.4588 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 71 | 30%
XG-202M | STREET TREE PLANTING IN CB 1-12 | 2002-06-30 | 2002-06-25 | 2002-04-23 | 316885 | 378000 | 2002-10-10 | 2003-07-06 | 2003-01-22 | GI | T | Tree Unit | 12.6663 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -165 | 19.29%
XG-202MR | STREET TREE PLANTING - CB 1-12 | 2002-06-30 | 2002-06-25 | 2002-04-23 | 188500 | 223000 | 2003-10-20 | 2004-07-15 | 2004-03-09 | GI | T | Tree Unit | 12.1469 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -128 | 18.3%
XG-203M | STEPS, WALLS, PAVEMENTS & GENERAL SITE WORK | 2002-10-31 | 2002-10-31 | 2002-06-26 | 750000 | 975000 | 2004-03-01 | 2005-02-28 | 2005-06-15 | GI | RCU | Requirements Contract Unit | 13.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 107 | 30%
XG-203MR | STEPS, WALLS, PAVEMENTS & GENERAL SITE WORK | 2002-10-31 | 2002-10-31 | 2002-06-26 | 750000 | 1226000 | 2005-04-25 | 2006-04-24 | 2006-11-20 | GI | RCU | Requirements Contract Unit | 13.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 210 | 63.47%
XG-204M | PAVEMENTS, FENCES, PLANTINGS & GENERAL SITE WORK |  | 2004-03-02 | 2003-10-29 | 726000 | 871000 | 2004-07-26 | 2005-07-25 | 2006-06-30 | FI | RCU | Requirements Contract Unit | 13.4953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 340 | 19.97%
XG-205M | PAVEMENTS, SIDEWALKS, LAWNS & GENERAL SITEWORK |  | 2005-04-01 | 2004-06-21 | 500000 | 600000 | 2005-08-18 | 2006-08-17 | 2006-01-25 | GI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -204 | 20%
XG-205MR | PAVEMENTS, SIDEWALKS, LAWNS & GENERAL SITEWORK |  | 2005-04-01 | 2004-06-21 | 500000 | 600000 | 2006-07-19 | 2007-07-18 | 2007-11-21 | FI | RCU | Requirements Contract Unit | 13.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 126 | 20%
XG-207M | STREET TREES - CB 1-12 BRONX |  | 2007-01-05 | 2006-09-14 | 440000 | 550000 | 2007-09-17 | 2008-03-14 | 2008-03-13 | FI | T | Tree Unit | 12.9945 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 25%
XG-297 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & SITEWORK | 1996-10-15 | 1996-11-08 | 1996-09-20 | 601595 | 662000 | 1997-03-03 | 1998-03-02 | 1998-03-20 | GI | RCU | Requirements Contract Unit | 13.3073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 18 | 10.04%
XG-298 | STREET & FLOWERING TREE PLANTING IN GREENSTREET TRIANGLES | 1997-09-15 | 1997-09-08 | 1997-07-10 | 231218 | 467000 | 1997-12-10 | 1998-09-05 | 1998-08-03 | FI | T | Tree Unit | 12.3511 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -33 | 102%
XG-299 | STREET TREE PLANTING - F.Y. 1999 | 1999-01-29 | 1999-01-21 | 1998-11-02 | 436750 | 467000 | 1999-09-01 | 2000-08-30 | 2000-08-18 | GI | T | Tree Unit | 12.9871 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -12 | 6.926%
XG-299R | STREET TREE PLANTING - F.Y. 2000 | 1999-12-31 | 2000-01-31 | 1998-11-02 | 425000 | 405000 | 2000-03-22 | 2001-03-21 | 2001-03-21 | FI | T | Tree Unit | 12.9598 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -4.706%
XG-301M | PLAY EQUIPMENT, S.S., HANDBALL CTS & SITE WORK | 2000-11-01 | 2000-12-27 | 2000-11-01 | 1402000 | 1795000 | 2001-05-21 | 2002-05-20 | 2003-07-11 | GI | RCU | Requirements Contract Unit | 14.1534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 417 | 28.03%
XG-303M | PLAY EQUIP, S.S., HANDBALL CTS. & GENERAL SITE WORK | 2002-12-31 | 2003-02-11 | 2002-06-27 | 650000 | 1667000 | 2003-08-04 | 2004-08-02 | 2004-12-23 | GI | RCU | Requirements Contract Unit | 13.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 143 | 156.5%
XG-303MR | PLAY EQUIP, S.S., HANDBALL CTS. & GENERAL SITE WORK | 2002-12-31 | 2003-02-11 | 2002-06-27 | 650000 | 780000 | 2004-08-16 | 2005-08-15 | 2006-03-13 | GI | RCU | Requirements Contract Unit | 13.3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 210 | 20%
XG-304M | STREET TREES - CB 1-12 BRONX |  | 2004-05-25 | 2004-03-24 | 404000 | 453000 | 2004-10-07 | 2005-07-03 | 2005-05-09 | GI | T | Tree Unit | 12.9092 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -55 | 12.13%
XG-304MR | STREET TREES - BRONX |  | 2005-07-20 | 2005-07-20 | 325000 | 358000 | 2005-10-17 | 2006-07-13 | 2006-02-03 | FI | T | Tree Unit | 12.6916 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -160 | 10.15%
XG-305M | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 800000 | 960000 | 2005-08-22 | 2006-08-21 | 2006-09-12 | GI | RCU | Requirements Contract Unit | 13.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 22 | 20%
XG-305MR | FENCING, GUIDERAILS, BASEBALL BACKSTOPS & GENERAL SITEWORK |  | 2005-03-21 | 2004-06-21 | 700000 | 840000 | 2006-08-21 | 2007-08-20 | 2007-09-06 | FI | RCU | Requirements Contract Unit | 13.4588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 17 | 20%
XG-307M | STREET TREES & FLOWERING TREES - BRONX |  | 2006-12-29 | 2006-09-14 | 1750000 | 1750000 | 2007-04-16 | 2008-01-10 | 2008-01-08 | FI | T | Tree Unit | 14.3751 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -2 | 0%
XG-31650-101M | BISSEL GARDENS - PATHWAYS & WATER SUPPLY | 2001-07-15 | 2001-07-09 | 2000-08-08 | 124210 | 165000 | 2002-03-04 | 2002-06-01 | 2002-05-01 | GI | X | Bronx Team | 11.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31 | 32.84%
XG-31700-101M | BRONX RIVER GREENWAY - EDGEWATER RD ALONG LAFAYETTE AVE. | 2001-12-15 | 2003-01-22 | 2001-04-20 | 2506469 | 3270000 | 2004-05-17 | 2005-11-07 | 2006-09-15 | GI | X | Bronx Team | 14.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 30.46%
XG-31700-205M | BRONX RIVER GREENWAY (CONCRETE PLANT)-DEMOLITION, REMOVAL OF EXISTING STRUC. & ENVMTL REMEDIATION | 2004-10-04 | 2004-10-08 | 2004-09-20 | 959375 | 960000 | 2005-08-22 | 2006-04-18 | 2007-02-13 | GI | X | Bronx Team | 13.774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 0.06515%
XG-397 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & SITEWORK | 1996-10-15 | 1996-11-08 | 1996-09-20 | 546800 | 602000 | 1997-03-10 | 1998-03-09 | 1998-03-10 | GI | RCU | Requirements Contract Unit | 13.2118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 10.1%
XG-399 | BOILERS & HEATING SYSTEMS IN THE BRONX | 1998-12-15 | 1998-12-18 | 1998-11-23 | 462475 | 623000 | 1999-06-14 | 2000-03-09 | 2001-01-11 | GI | X | Bronx Team | 13.0443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 34.71%
XG-400M | STREET TREES PLANTING F/FY 2000 IN CB 1-12 | 1999-11-10 | 2000-01-24 | 1999-10-18 | 310652 | 376000 | 2000-11-20 | 2001-11-19 | 2001-07-25 | GI | T | Tree Unit | 12.6464 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -117 | 21.04%
XG-401M | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2000-11-30 | 2001-01-30 | 2000-11-01 | 1551416 | 2373000 | 2001-06-04 | 2002-06-03 | 2003-10-01 | GI | RCU | Requirements Contract Unit | 14.2547 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 485 | 52.96%
XG-401MR | PAVEMENTS, HANDBALL COURTS, LANDSCAPE AREAS & SITE WORK | 2002-10-21 | 2002-10-21 | 2000-11-01 | 192000 | 304000 | 2004-03-22 | 2005-03-21 | 2004-12-15 | GI | RCU | Requirements Contract Unit | 12.1653 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -96 | 58.33%
XG-403M | STREET TREE PLANTING - C.B. 1 - 12 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 277925 | 334000 | 2003-03-24 | 2003-09-19 | 2003-07-23 | GI | T | Tree Unit | 12.5351 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -58 | 20.18%
XG-403MR | STREET TREE PLANTING - C.B. 1-12 | 2002-10-01 | 2002-10-18 | 2002-07-16 | 198695 | 229000 | 2004-04-12 | 2004-10-08 | 2004-07-29 | GI | T | Tree Unit | 12.1995 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -71 | 15.25%
XG-405M | P.E., S.S., HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 800000 | 960000 | 2005-09-26 | 2006-09-25 | 2006-12-19 | FI | RCU | Requirements Contract Unit | 13.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 85 | 20%
XG-405MR | P.E., S.S., HANDBALL CTS & GENERAL SITEWORK |  | 2005-04-08 | 2004-06-21 | 800000 | 960000 | 2006-09-25 | 2007-09-24 | 2008-01-25 | FI | RCU | Requirements Contract Unit | 13.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 123 | 20%
XG-497 | SIDEWALKS, PATHS, PAVEMENTS & GENERAL SITEWORK | 1996-11-30 | 1996-12-05 | 1996-09-20 | 493414 | 493000 | 1997-03-24 | 1998-03-23 | 1998-01-12 | FI | RCU | Requirements Contract Unit | 13.1091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -70 | -0.08391%
XG-501M | PAVEMENTS, HANDBALL CTS, LANDSCAPED AREAS & GENERAL SITE WORK | 2001-09-30 | 2001-11-15 | 2001-04-25 | 552000 | 712000 | 2002-07-15 | 2003-07-14 | 2004-01-21 | FI | RCU | Requirements Contract Unit | 13.2213 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 191 | 28.99%
XG-501MR | PAVEMENTS, HANDBALL CTS, LANDSCAPED AREAS & GENERAL SITE WORK | 2001-09-30 | 2003-12-31 | 2001-04-25 | 100000 | 712000 | 2004-07-14 | 2005-07-13 | 2005-03-22 | FI | RCU | Requirements Contract Unit | 11.5129 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -113 | 612%
XG-503M | BOILERS & HEATING SYSTEMS - BRONX | 2003-08-19 | 2003-08-20 | 2002-11-12 | 138520 | 263000 | 2004-05-10 | 2005-09-30 | 2006-05-03 | FI | X | Bronx Team | 11.8388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 89.86%
XG-505M | STREET TREES - CB 1-12 BRONX |  | 2004-08-05 | 2004-07-06 | 403000 | 565000 | 2005-03-28 | 2005-09-23 | 2005-08-19 | FI | T | Tree Unit | 12.9067 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -35 | 40.2%
XG-505MR | STREET TREES - CB 1-12 BRONX |  | 2004-08-05 | 2004-07-06 | 383000 | 459000 | 2006-03-20 | 2006-09-15 | 2006-08-30 | FI | T | Tree Unit | 12.8558 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -16 | 19.84%
XG-597R | SIDEWALKS & PAVEMENTS - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 371325 | 518000 | 1998-01-27 | 1999-01-26 | 1998-12-11 | GI | RCU | Requirements Contract Unit | 12.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -46 | 39.5%
XG-599 | FENCES, GUIDERAILS, SIDEWALKS, PAVEMENTS, LAWNS, & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-02-12 | 1999-03-10 | 1999-01-20 | 356641 | 458000 | 1999-06-14 | 2000-03-09 | 2000-04-05 | GI | RCU | Requirements Contract Unit | 12.7845 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 27 | 28.42%
XG-600M | STREET TREE PLANTING - FY 2001 | 2000-07-15 | 2000-07-13 | 2000-05-11 | 317134 | 350000 | 2000-11-13 | 2001-08-09 | 2001-03-21 | GI | T | Tree Unit | 12.6671 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -141 | 10.36%
XG-600MR | STREET TREE PLANTING - FY 2002 | 2001-06-26 | 2001-06-26 | 2000-05-11 | 359625 | 410000 | 2001-10-02 | 2002-06-28 | 2002-02-08 | GI | T | Tree Unit | 12.7928 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -140 | 14.01%
XG-601M | PLAY EQUIP, S.S. HANDBALL CTS. & GENERAL SITE WORK | 2001-08-31 | 2001-08-10 | 2001-04-25 | 1100000 | 1667000 | 2002-04-03 | 2003-04-02 | 2004-06-30 | GI | RCU | Requirements Contract Unit | 13.9108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 455 | 51.55%
XG-697R | CHAIN LINK FENCES, GUIDERAILS, & STEEL FENCES - PHASE 2 RENEWAL | 1997-10-06 | 1997-10-06 | 1997-10-03 | 310195 | 569000 | 1998-01-26 | 1998-10-22 | 1999-02-23 | GI | RCU | Requirements Contract Unit | 12.645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 124 | 83.43%
XG-699D | PLAY EQUIPMENT, PAVEMENTS, FENCES AND GENERAL SITE WORK | 1999-02-15 | 1999-03-09 | 1998-12-28 | 926744 | 1250000 | 2000-03-15 | 2001-03-14 | 2002-04-19 | GI | RCU | Requirements Contract Unit | 13.7394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 401 | 34.88%
XG-700M | BRONX FLAGPOLES (EMERGENCY) | 2000-07-30 | 2000-07-21 | 2000-05-30 | 1116350 | 1287000 | 2000-08-28 | 2000-12-25 | 2000-12-24 | GI | CPM | Construction Project Manager | 13.9256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 15.29%
XG-701M | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2001-06-30 | 2001-06-04 | 2001-04-25 | 530000 | 689000 | 2001-11-15 | 2002-08-11 | 2002-11-13 | GI | RCU | Requirements Contract Unit | 13.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 94 | 30%
XG-701MR | FENCES, GUIDE RAILS & GENERAL SITE WORK | 2002-06-14 | 2002-06-14 | 2001-04-25 | 530000 | 761000 | 2003-04-23 | 2004-01-17 | 2004-06-22 | FI | RCU | Requirements Contract Unit | 13.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 157 | 43.58%
XG-706M | CB 1-12 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 345000 | 345000 | 2006-10-16 | 2007-07-12 | 2007-01-17 | FI | T | Tree Unit | 12.7513 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -176 | 0%
XG-706MR | CB 1-12 - PLANTING OF NEW & REPLACEMENT STREET TREES |  | 2006-07-06 | 2006-05-08 | 750000 | 1050000 | 2007-09-17 | 2008-06-12 | 2008-03-20 | FI | T | Tree Unit | 13.5278 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -84 | 40%
XG-797 | STREET TREE PLANTING FY 97 | 1997-02-15 | 1997-02-24 | 1996-09-03 | 314000 | 428000 | 1997-06-02 | 1998-06-01 | 1998-05-28 | GI | T | Tree Unit | 12.6571 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -4 | 36.31%
XG-798 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS., & SITEWORK | 1998-03-31 | 1998-02-23 | 1997-09-15 | 797344 | 1058000 | 1998-05-26 | 1999-05-25 | 1999-05-14 | GI | RCU | Requirements Contract Unit | 13.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -11 | 32.69%
XG-798R | PLAY EQUIP, S.S., HANDBALL CTS., & SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-11 | 1997-09-15 | 797344 | 958000 | 1999-06-07 | 2000-06-05 | 1999-11-19 | GI | RCU | Requirements Contract Unit | 13.589 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -199 | 20.15%
XG-799 | M&O REQ.CONTRACT F/PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 1999-06-30 | 1999-06-09 | 1999-04-09 | 780197 | 1047000 | 1999-11-22 | 2000-11-20 | 2000-11-03 | GI | RCU | Requirements Contract Unit | 13.5673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -17 | 34.2%
XG-799R | PLAY EQUIPMENT, S.S., HANDBALL CTS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 780197 | 1100000 | 2000-11-02 | 2001-11-01 | 2001-12-12 | GI | RCU | Requirements Contract Unit | 13.5673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 41 | 40.99%
XG-800M | BOILERS & HEATING SYSTEMS @ ST. JAMES C.S. & OWEN DOLAN GOLDEN AGE CTR. | 2000-12-10 | 2000-12-15 | 2000-07-19 | 204060 | 302000 | 2001-05-21 | 2002-02-14 | 2002-05-02 | GI | X | Bronx Team | 12.2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 48%
XG-898 | SIDEWALKS, PATHS, PAVEMENTS & SITEWORK | 1998-03-31 | 1998-02-20 | 1997-09-15 | 570399 | 735000 | 1998-05-13 | 1999-05-12 | 1999-04-15 | GI | RCU | Requirements Contract Unit | 13.2541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -27 | 28.86%
XG-898R | SIDEWALKS, PATHS, PAVEMENTS & SITEWORK IN VARIOUS PARKS & PLAYGROUNDS | 1999-01-29 | 1999-02-11 | 1997-09-15 | 570399 | 684000 | 1999-06-02 | 2000-05-31 | 2000-11-21 | GI | RCU | Requirements Contract Unit | 13.2541 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 174 | 19.92%
XG-899 | M&O REQ. CONTRACT F/PLAY EQUIP, S.S., HANDBALL CTS & SITE WORK | 1999-06-30 | 1999-06-10 | 1999-04-09 | 832097 | 1048000 | 1999-11-22 | 2000-11-20 | 2000-08-03 | GI | RCU | Requirements Contract Unit | 13.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -109 | 25.95%
XG-905M | PAVEMENTS, SIDEWALKS, WALLS, FENCES, TENNIS CTS, HANDBALL CTS, LAWNS, GENERAL SITE WORK |  | 2005-01-11 | 2004-12-22 | 4700000 | 6331000 | 2005-06-13 | 2006-12-12 | 2007-01-25 | FI | X | Bronx Team | 15.3631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 34.7%
XG-906M | STREET TREES - NEW & REPLACEMENTS |  | 2006-08-01 | 2006-06-08 | 345000 | 1198000 | 2006-11-20 | 2007-11-19 | 2007-01-10 | FI | T | Tree Unit | 12.7513 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -313 | 247.2%
XG-997 | PLAY EQUIPMENT, SAFETY SURFACE, HANDBALL CTS, & GENERAL SITEWORK | 1997-03-31 | 1997-01-28 | 1996-11-14 | 956005 | 1120000 | 1997-05-05 | 1998-05-04 | 1998-02-12 | GI | RCU | Requirements Contract Unit | 13.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -81 | 17.15%
XG-999 | SIDEWALKS, PAVEMENTS, LAWNS & SITE WORK IN VARIOUS PARKS AND PLAYGROUNDS | 1999-06-30 | 1999-06-10 | 1999-04-09 | 532702 | 1123000 | 1999-11-29 | 2000-11-27 | 2000-10-12 | GI | RCU | Requirements Contract Unit | 13.1857 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -46 | 110.8%
XG-999R | SIDEWALKS, PAVEMENTS, LAWNS & SITE WORK | 2000-07-26 | 2000-07-26 | 1999-04-09 | 532000 | 683000 | 2000-10-30 | 2001-10-29 | 2001-09-21 | FI | RCU | Requirements Contract Unit | 13.1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -38 | 28.38%

## Codes
CITY OF NEW YORK
PARKS & RECREATION
CAPITAL PROJECTS
STATUS REPORT - LEGEND SHEET
| STATUS | TRANSLATION |  | DSN/CON UNIT | Team
| ACD | ANTICIPATED OR ACTUAL COMPLETION DATE |  | X | Bronx Team
| ACQ | LAND ACQUISITIONS |  | B | Brooklyn Team
| ADV | DESIGN COMPLETED. READY FOR ADVERTISEMENT |  | M | Manhattan Team
| AWD | BIDS COMPLETED. PENDING AWARD |  | Q | Queens Team
| BID | BID CYCLE: BID DATE ESTABLISHED |  | R | Staten Island Team
| CE | COMPUTER EQUIPMENT |  | (boro letter/C = Consultant selected for this project.)
| CFY | FISCAL YEAR FOR REGISTRATION/CONSTRUCTION
| COM | COMMUNICATION EQUIPMENT CONTRACTS |  | A | Architecture
| CON | IN CONSTRUCTION. OTW ISSUED. |  | CR | Construction Resources
| CSU | CONSULTANT CONTRACT |  | CROT | Croton Unit
| DC | DESIGN COMPLETED. |  | E | Engineering
| DSN | DESIGN: IN DESIGN OR PLANNING TO DESIGN |  | EN | Environmental Control Unit
| DEF | CONTRACTOR DEFAULTED |  | RCU | Requirements Contract Unit
| EME | EMERGENCY CONTRACT |  | T | Tree Unit
| EQP | EQUIPMENT |  | TS | Technical Services (Randalls Isl.)
| FI | FINAL INSPECTION TOOK PLACE.
| FUT | POSSIBLE FUTURE DESIGN
| GI | GUARANTEE INSPECTION TOOK PLACE.
| OTW | REGISTRATION APPROVED. PENDING ORDER-TO-WORK DATE.
| OFY | ORIGINAL FUNDING YEAR
| RC | REQUIREMENT CONTRACT
| REBID | PROJECT TO BE RE-BID.
| RESC | CONTRACT RESCINDED
| REG | CONTRACT AWARDED. PENDING REGISTRATION
| SCD | SCHEDULED COMPLETION DATE
| SCON | CONSTRUCTION CONTRACT SUPERVISED BY A CONSULTANT
| SS | SOLE SOURCE CONTRACT
| TERM | CONTRACT TERMINATED. PENDING RE-BID AND/OR DE-REGISTRATION OF CONTRACT.
| UI | USE INSPECTION TOOK PLACE.
· INDIVIDUAL SITES UNDER A REQUIREMENT CONTRACT
FMS Updated = Last time Budget Office updated fund information.
BUDGET LINE CODES:
P-NUMBER OR P-NUMBER+LETTER MAYORAL FUNDS
P-D+NUMBER CITY COUNCIL FUNDS
P-LETTER+NUMBER | BOROUGH PRESIDENT FUNDS
The letter represents the borough for which monies are funded: K=BROOKLYN;M=MANHATTAN;Q=QUEENS;R=STATEN ISLAND;X=BRONX
Revised 11/20/06, 01/18/07, 10/23/07, 01/04/08a ml

## _STDS_DGFAB159F (hidden)
Name | Data Set #1 | StatTools Version that generated sheet, Major | 6 | StatTools Version that generated sheet, Minor | 1 | StatTools Version that generated sheet, Revision | 2 | Min. StatTools Version to Read Sheet, Major (note ST versions before 1.1.1 don't perform forward compatibility check) | 1 | Min. StatTools Version to Read Sheet, Minor | 0 | Min. StatTools Version to Read Sheet, Revision | 0 | Min. StatTools version to not put up warning about extra info, Major | 1 | Min. StatTools version to not put up warning about extra info, Minor | 0 | Min. StatTools version to not put up warning about extra info, Revision | 0
GUID | DGFAB159F
Format Range | FALSE
Variable Layout | Columns
Variable Names In Cells | TRUE
Variable Names In 2nd Cells | TRUE
Data Set Ranges | BROWER PARK - CONSTR. OF COMFORT STATION
Data Sheet Format | 1
Formula Eval Cell | 1
Num Stored Vars | 37
1 : Info | VG2A5A87F5176119D3 | var1 | ST_ProjectNo | TRUE | 0 | 4
1 : Ranges | B017-105M
1 : MultiRefs
2 : Info | VGF47DCF6341A1EB6 | var2 | ST_ProjectTitle | TRUE | 0 | 4
2 : Ranges | PLGD. @ LAFAYETTE AVE. BET. MALCOLM X BLVD. & PATCHEN AVE.
2 : MultiRefs
3 : Info | VG227251D5DE0E5BC | var3 | ST_DesignScheduleandCompletionDate | TRUE | 0 | 4
3 : Ranges | 36949
3 : MultiRefs
4 : Info | VG27241B1F959310D | var4 | ST_DesignActualCompletionDate | TRUE | 0 | 4
4 : Ranges | 35514
4 : MultiRefs
5 : Info | VG1F859CDADE0AB0F | var5 | ST_TitleRequest | TRUE | 0 | 4
5 : Ranges | 34592
5 : MultiRefs
6 : Info | VG14C3C07BF4E7F76 | var6 | ST_ConstructionRegisteredAmount | TRUE | 0 | 4
6 : Ranges | 172325
6 : MultiRefs
7 : Info | VG38DA14AB1FD2AFA | var7 | ST_TotalBudget | TRUE | 0 | 4
7 : Ranges | 1604000
7 : MultiRefs
8 : Info | VG39D79B2421F326C1 | var8 | ST_RegistrationApprovedPendingOrdertoWorkDate | TRUE | 0 | 4
8 : Ranges | 35912
8 : MultiRefs
9 : Info | VG2B6DB17930D9E308 | var9 | ST_ScheduledCompletionDate | TRUE | 0 | 4
9 : Ranges | 39440
9 : MultiRefs
10 : Info | VG1F970E141705D721 | var10 | ST_FinalInspection | TRUE | 0 | 4
10 : Ranges | 36959
10 : MultiRefs
11 : Info | VG2887B4731D6EB50 | var11 | ST_Status | TRUE | 0 | 4
11 : Ranges | GI
11 : MultiRefs
12 : Info | VG32FDBAAA1FD4C798 | var12 | ST_ConstructionUnit | TRUE | 0 | 4
12 : Ranges | B
12 : MultiRefs
13 : Info | VG1C64A1B391EA116 | var13 | ST_CodedUnit | TRUE | 0 | 4
13 : Ranges | Brooklyn Team
13 : MultiRefs
14 : Info | VG11DE06B5FE869DB | var14 | ST_lncost | TRUE | 0 | 4
14 : Ranges | 14.3499
14 : MultiRefs
15 : Info | VG13B7543E289411FA | var15 | ST_Electrical | TRUE | 0 | 4
15 : Ranges | 0
15 : MultiRefs
16 : Info | VG295160FA18358CBC | var16 | ST_Tree | TRUE | 0 | 4
16 : Ranges | 0
16 : MultiRefs
17 : Info | VGC2C31131A075D9B | var17 | ST_Landscape | TRUE | 0 | 4
17 : Ranges | 0
17 : MultiRefs
18 : Info | VG20982C3C2B95750F | var18 | ST_Plumbing | TRUE | 0 | 4
18 : Ranges | 0
18 : MultiRefs
19 : Info | VG30F1164F39241BF | var19 | ST_Park | TRUE | 0 | 4
19 : Ranges | 1
19 : MultiRefs
20 : Info | VG1E21D4C424F50719 | var20 | ST_Station | TRUE | 0 | 4
20 : Ranges | 0
20 : MultiRefs
21 : Info | VG68DDBCB226A3EFF | var21 | ST_Playground | TRUE | 0 | 4
21 : Ranges | 0
21 : MultiRefs
22 : Info | VG30A7E6B38056C71 | var22 | ST_CodedUnitArchitecture | TRUE | 0 | 4
22 : Ranges | 0
22 : MultiRefs
23 : Info | VG1FAEA36118FEA5EB | var23 | ST_CodedUnitBronxTeam | TRUE | 0 | 4
23 : Ranges | 0
23 : MultiRefs
24 : Info | VG1B20211FB32B069 | var24 | ST_CodedUnitBrooklynTeam | TRUE | 0 | 4
24 : Ranges | 0
24 : MultiRefs
25 : Info | VG27283BB528D3A6B4 | var25 | ST_CodedUnitConstructionProjectManager | TRUE | 0 | 4
25 : Ranges | 0
25 : MultiRefs
26 : Info | VG3A92D1EF348CF2FA | var26 | ST_CodedUnitConstructionResources | TRUE | 0 | 4
26 : Ranges | 0
26 : MultiRefs
27 : Info | VG3B5A418027382F53 | var27 | ST_CodedUnitCrotonUnit | TRUE | 0 | 4
27 : Ranges | 0
27 : MultiRefs
28 : Info | VG1491B08DBEBAE2A | var28 | ST_CodedUnitEngineering | TRUE | 0 | 4
28 : Ranges | 0
28 : MultiRefs
29 : Info | VG46C0F54221E0233 | var29 | ST_CodedUnitEnvironmentalControlUnit | TRUE | 0 | 4
29 : Ranges | 0
29 : MultiRefs
30 : Info | VG18041B5C340F75F0 | var30 | ST_CodedUnitManhattanTeam | TRUE | 0 | 4
30 : Ranges | 0
30 : MultiRefs
31 : Info | VG2D7C43E5256D5755 | var31 | ST_CodedUnitQueensTeam | TRUE | 0 | 4
31 : Ranges | 0
31 : MultiRefs
32 : Info | VG71DB1F5135D0EA3 | var32 | ST_CodedUnitRequirementsContractUnit | TRUE | 0 | 4
32 : Ranges | 0
32 : MultiRefs
33 : Info | VG330A5AD2F3F2FFE | var33 | ST_CodedUnitStatenIslandTeam | TRUE | 0 | 4
33 : Ranges | 0
33 : MultiRefs
34 : Info | VG2D7FB830396FDDC | var34 | ST_CodedUnitTechnicalServicesRandallsIsl | TRUE | 0 | 4
34 : Ranges | 0
34 : MultiRefs
35 : Info | VG358E61ED25CEBAD7 | var35 | ST_CodedUnitTreeUnit | TRUE | 0 | 4
35 : Ranges | 0
35 : MultiRefs
36 : Info | VG159A7DA9126BF7E4 | var36 | ST_DaysLate | TRUE | 0 | 4
36 : Ranges | 375
36 : MultiRefs
37 : Info | VGFB5E9011B15E49D | var37 | ST_CostEscalations | TRUE | 0 | 4
37 : Ranges | 0.6367
37 : MultiRefs